19-June-2006

ATLAS Tracking at SLHC: Development of a Stave Readout Structure:

FY2006 Report and FY2007 Plan

Lawrence Berkeley National Lab

Brookhaven National Lab

Hampton University

Yale University

This document describes the US ATLAS stave development plan for FY2007.  The FY2006 effort is within budget. The basic stave construction and test efforts at LBNL are on schedule.  We have not however moved some of activities out of LBNL as originally scheduled yet.  This reflects a re-adjustment of priorities as the project has evolved.   The plans for a follow-on effort (this document) reflect conclusions reached in FY2006 reflecting the Genoa Meeting and discussions with other non-US ATLAS colleagues. The plan is also informed by the concurrent proposal for stave development submitted to the ATLAS Upgrade Steering Group.  That proposal supplements this report as well.

Completion of FY2006 milestones.

Here we give a status and update on the prior years milestones.  The last column entries are status or new dates.

Phase 1 Milestones (completion dates given):

- full electrical specification and schematic for Phase 1 stave	10/04	done

- establishment of test stands at LBNL, BNL, and Hampton	11/04	done

- validation of test stand operation on test parts		12/04	done

- design and layout of Phase 1 hybrid				12/04	done

- fabrication of hybrid						03/05	done

- assembly and test of hybrid					04/05	done

- re-commission and tests with existing fixtures		03/05	done

- assembly of ATLAS staves					06/05	done

- initial test of ATLAS staves at LBNL 			07/05	done

- transfer to and test of staves at BNL/Hampton		12/05	8/06

- irradiation studies of staves					2/06	12/06

- transfer of assembly methods to BNL			12/05	9/06

Conclusions from Genoa and ATLAS wide discussions

We left Genoa with a basic concept for an ATLAS tracker (outside the pixel region).  The concept is shown in Figure 1.  The tracker consists of only two types of staves, described below.

- Inner layer stave: This stave is (approx) 1 meter long.  It carries (approx) 3 cm long “short-strip” detectors.  These are tiled alternately on the two faces to give full coverage along the z-axis.  Each stave holds (approx) 32 detectors, 16 on each side.  The pitch is 80 microns and there are 768 or 896 strips per detector.  The hybrids and fanouts are adjacent to the detectors. The scheme is shown in Figure 2.

- Outer layer stave: This stave is (approx) 2 meters long.  It carries (approx) 10 cm long detectors in a stereo u-v configuration (like SCT).   Each stave holds (approx) 20 detectors per side (a total of 40 detectors).  There are small (3 mm ) z gaps between each crystal.  The hybrids and fanouts are glued on top of the crystals.  The scheme is shown in Figure 2.

- Alternate powering (serial or DC-DC conversion) are seen as an integral aspect of future stave development.  Evaluating these as part of the stave testing is of equal priority to the mechanical, assembly, and packaging aspects.

Review of Plan from FY2006 with comments and accomplishments in italics

Below we remark specifically on the items in the 2006 plan.  Beyond these items, a number of modules were assembled and tested on and off the parallel powered stave.  They worked as expected and showed, if anything, improved noise performance on the stave.  In particular modules were operated concurrently with control, clock, and data flowing to and from other modules.  We presume the engineered and compact ground and power configuration of the stave is a key aspect to this good  performance. See figure below.

Hybrid + detector in 3rd position mounted on stave with concurrent operation of detector in position 1.

Studies of multi-drop LVDS clock distribution on the stave were also completed. See figure below.

LVDS signal integrity with significant DC bus cable resistance is still acceptable for timing and data transmission requirements

Abstracts describing all aspects of the project have been submitted to the 2006 IEEE NSS conference and the 2006 Hiroshima (Carmel) Silicon Detector conference.

The basic plan for FY2006 was:

- Advance the stave design to study alternative powering schemes: As discussed in Genoa, a significant reduction in services is likely to come from a change in power distribution.  Two basic schemes can be considered, serial powering or local DC-DC conversion.  Serial powering has been studied at RAL using existing SCT modules with good results.  Voltage conversion is the subject of an IC design effort at Berkeley.  To incorporate these schemes into the stave will require a modification to the hybrid and stave bus cable as well as the development or procurement of the basic components.

  - Development of serial powering components (LBNL): Serial powering can be implemented on the FY2005 stave with the addition of a new “power-interface” hybrid.  This hybrid would be placed between the existing hybrid and the bus cable bond pads.  The scheme is shown in Figure 4.  This hybrid will be designed and fabricated in the FY2006 project.

In FY2006 this effort became an active collaboration with RAL.  The “power-interface” hybrid was designed collaboratively.  RAL had it fabricated and it is scheduled to be tested in modules and stave in late June 2006 at LBNL.  A serial powering bus cable was also designed and is currently in fabrication.

  - Development of DC-DC converter circuit (LBNL): As stated, design effort is underway with separate funding.  The viability of this approach will be reviewed.   If viewed as promising a second power-interface hybrid could be developed as well.  (We will explore the possibility that a single interface hybrid could be used for DC-DC and serial powering tests.

The IC development effort did not proceed far enough to lead to a DC-DC “power-interface” hybrid.  The serial version of the hybrid pin-out was designed to also be compatible with DC-DC conversion.

  - System level studies of serial and DC-DC powering (BNL):  A number of critical issues need to be addressed using test boards and available components.  Also fail-safe schemes need to be studied and evaluated.  A system level design and specification will be derived.

Some preliminary engineering work on this aspect has occurred.

- Development of special control and readout electronics to test multi-module deadtimeless operation (BNL): The present SCT test electronics (MUSTARD-SLOC-CLOAC) are best suited for sequential testing of modules.  We will explore the development of a multi-modular test board which is particularly suited for stave-like objects.

We have chosen a solution the utilizes a commercial module, the National Instruments PXI based 6151 wave generator/analyzer card to control and read out multiple hybrid modules. A single card is capable of controlling and simultaneously acquiring data from at least 14 modules, while two modules can simultaneously read out 30 modules. The system is further expandable in readout capability in multiplies of 16 modules.

Software development has begun at LBL, with further development taking place at BNL.

LabView(LV)  and C are the software platforms in use.  A full set of control and acquisition routines have been written in LV and are in the process of being debugged. A breakout card has been configured to connect SCT hybrids and modules to 6151.

A simple card containing just two ABCD chips is being developed at BNL  to facilitate the software development. It is envisioned these cards will be provided to other institutions to aid in their setting up duplicate DAQ system. A preliminary, but almost final layout of one layer of the card is shown below.

Simple ABCD test card

- Development of detectors (BNL): For the outer layer staves the existing CDF Run IIb detectors are well suited and still available.  For the inner layer (SCT region) staves a new short strip detector is required.  This would have (approx) 3 cm long strips.  It might be fabricated in a p bulk process.  The development and fabrication of a quantity of the short detectors would be undertaken.

The large quantity of detectors required (~100) ruled out in-house production at BNL. We obtained quotes to produce short strip detectors from both Hammamatsu and Sintef. As Sintef’s quote was higher than expected, we chose to produce detectors via Hammamatsu. This choice has the added benefit in that the detector will be very similar to the present SCT detector, only shorter (about ½ the length). In order that the detectors are fully compatible with the ABCD chip, we will fabricate p on n-type detectors. The order has been placed and the detectors are expected in about six months.  These detectors are in integral part of the 1 meter ATLAS stave test at the center of the 2007 workplan.

- Stave mechanics (LBNL and BNL): The inner layer stave would be thin and (approx) 1 meter long.  This is about 50% longer than the CDF stave so is probably not a major deviation.  For the outer layers am (approx) 2 meter stave is close to optimum.  The design of this object is certainly more complex technically.  We propose to mount some engineering effort in this direction.  We would initiate this by consulting with the Fermilab engineers who developed the CDF stave.  This would be followed by appropriate fixture development and fabrications.

A considerable design and simulation effort has occurred in collaboration with Bill Miller at ITI, an outside consultant to the project. This effort is described further in an accompanying report.  The effort has focused on the mechanics and cooling of a 1 meter long stave.  A design has been found which shows minimal gravitational sag (<60 microns) and negligible thermal deformation (<10 microns).  Fiber lay-ups and materials have been identified (4/1 fibers)  and selected as well as a cooling tube and core configuration.  The design is moving into engineering drawings and assembly fixture design.

Some effort has gone to consider also the 2 meter stave.  The basic conclusion is that similar sag can be achieved with an intermediate support at 1 meter.

Preliminary work on developing stave design and measurement capability has begun at BNL. Initial thermal and mechanical finite element analysis has begun. As work on the CDF style stave is well advanced at LBL, BNL is looking into some alternative, though similar designs. Additionally, BNL will study the implications of a 2-d inner stave should later simulation demonstrate that 2-d information from the inner staves is necessary.

Budget (2006)

In the accompanying spread-sheet a budget for all the activities listed above is calculated.

The estimates for LBNL and BNL are both $115K.  The Hampton tasks are not specified but it is expected that Hampton will engage with either of the National Labs on some aspect of the testing and characterization of the devise,  The Hampton cost is $20K.

A fraction of the money allocated remains un-committed.  This is because RAL built the serial-power hybrid at no cost to us, the DC-DC effort did not reach the hybrid phase, and stave fixturing costs were less than anticipated.  The excess funds can be used to support the FY2007 activity and front load the stave mechanical  fixturing in the near term (summer 2006).  This is all reflected in the new budget request (attached)

Figure 1: Overall barrel tracker layout shows intermediate and outer stave regions with a default of three stave layers in each region.

Figure 2: Concepts for long outer region stave (top) and intermediate region stave (lower).  Hybrids are not show but are on silicon for long stave (as in test stave under study now) and adjacent to the silicon for the intermediate stave with gaps between crystals.

Figure 3: Scheme with new serial or DC-DC powering hybrid shown.

Report on Mechanical Activities

The description and plan for mechanical activities towards a 1 meter stave are in an accompanying report entitled:

ATLAS Upgrade

Stave Mechanical and Cooling Design Study

WBS 4.1.4.3

William O. Miller

Innovative Technologies International (iTi)

M. G. D. Gilchriese and C. Haber

Lawrence Berkeley National Laboratory

June 19, 2006

The budget for this activity is included below and in the report.

Plan for FY2007

The plan for FY2007 is to complete the FY2006 studies and build and test an ATLAS specific 1 meter stave.

- Completion of FY2006 tasks

  - Complete testing of serial powered “CDF style” stave.  Most of this will occur in summer 2006

  - Complete DC-DC converter chip and board, test on a “CDF style” stave

  - Engineering studies on alternate powering reliability.

  - Complete mechanical studies leading the 1 meter stave design.

  - Complete software development around NI-6151 module in preparation for multi-module tests.  Test this new system.

  - Test and QA on detector order when it arrives from Hammamatsu.

- Design and build electrical components for the 1 meter stave

  - A six chip version of the ABCD hybrid, probably with integrated serial powering circuitry will be designed and built.  A preliminary floor plan has already been made.

  - A wider thin film fanout.

  - Test fixtures, holders, and interface cards.

  - A 1 meter version of the bus cable.

- Design and build mechanical assembly and test fixtures for the 1 meter stave. (This is included in Bill Miller’s plan and cost estimate.)

- Design and build electrical assembly and test fixtures for the 1 meter stave.

  - A fixture to test hybrids and detectors together

  - A fixture to laminate the bus cable on the stave core

  - A fixture to locate the hybrids on the stave

  - A fixture to locate the detectors on the stave

  - A fixture to hold the stave during wirebonding of hybrids and detectors

  - A fixture to hold the stave during metrology and survey

  - A test box including cooling and electrical feedthroughs.

  - A storage and transport box.

- Fabricate stave (mechanically) and survey (This is included in Bill Miller’s plan)

- Fabricate and test stave (electrically). Sufficient components will be on-hand to populate 3 staves.

End of FY2006 and FY2007 Schedule

Summer 2006:

- Assemble serial powering components and test on “CDF style” staves

- Continue DAQ software debug

- Continue mechanical design study

- Design 1 meter hybrid, fanout, and bus cable

- Design 1 meter stave mechanical assembly fixtures (Miller)

- Procure materials for 1 meter stave

Fall 2006

- Prepare and present papers at IEEE and Hiroshima meetings

- Fabricate 1 meter hybrid, fanout, bus cable, test fixtures

- Fabricate 1 meter stave mechanics and test.

- Design and fabricate electrical assembly fixtures for 1 meter stave

- Test DAQ for multimodules

Winter 2006-2007

- Test and QA on 3 cm detectors

- Assemble and test 1 meter stave hybrids and components

- Assembly and test 1 meter staves electrically

- Design work on 2 meter staves

Spring 2007

- Continue assembly and test of 1 meter staves

- Design work on 2 meter staves

Budget for FY2007

The totals are 170,246 (LBNL), 135,000 (BNL), 20,000 (Hampton), and 114,500 (Miller +LBNL mechanical effort) = $439,746

| FY2007 development cost for ATLAS ID stave prototype 15-June-2006 Carl Haber |  |
| --- | --- |
| Phase 3 |  |  |  |  |  |  |  |
| 4.1.4.1.1 |  |  |  |  |  |  |  |
| LBNL Section |  |  |  |  |  |  |
|  | item | num | materials | total | hours | labor-cost | notes |
| 1 | 6 chip AC Hybrid |  |  |  |  |  |  |
| 1.1 | substrate |  |  |  |  |  |  |
| 1.1.1 | BeO blanks | 75 | $25.00 | $1,875 |  |  | 1 |
| 1.2 | thick film |  |  |  |  |  |  |
| 1.2.1 | CAD |  |  |  | 150 | $13,650 | 2 |
| 1.2.2 | NRE | 1 | $6,000.00 | $6,000 |  |  |  |
| 1.2.3 | printing | 120 | $600.00 | $72,000 |  |  | 3 |
| 1.3 | fanouts |  |  |  |  |  |  |
| 1.3.1 | CAD |  |  |  | 40 | $3,640 | 2 |
| 1.3.2 | mask | 1 | $1,500.00 | $1,500 |  |  |  |
| 1.3.3 | fabrication | 150 | $125.00 | $18,750 |  |  |  |
| 1.3.4 | dicing | 150 | $5.00 | $750 |  |  |  |
| 1.4 | components |  |  |  |  |  |  |
| 1.4.1 | discretes | 1 | $400.00 | $400 |  |  |  |
| 1.5 | assembly |  |  |  |  |  |  |
| 1.5.1 | surface mount | 150 | $75.00 | $11,250 |  |  |  |
| 1.5.2 | bond chips | 150 | $75.00 | $11,250 |  |  |  |
| 1.5.3 | misc assy,QC |  |  |  | 25 | $1,450 |  |
| 1.6 | test |  |  |  |  |  |  |
| 1.6.1 | test PC adapter |  |  |  |  |  |  |
| 1.6.1.1 | CAD |  |  |  | 25 | $2,275 | 2 |
| 1.6.1.2 | fabrication | 1 | $3,000.00 | $3,000 |  |  |  |
| 1.6.2 | misc fixtures |  |  |  | 25 | $1,900 |  |
| 1.6.3 | misc components | 1 | $1,500.00 | $1,500 |  |  |  |
| 1.7 | holders | 100 | $50.00 | $5,000 |  |  |  |
| 2 | 1 Meter Bus Cable |  |  |  |  |  |  |
| 2.1 | CAD |  |  |  | 100 | $9,100 |  |
| 2.2 | NRE | 1 | $500.00 | $500 |  |  |  |
| 2.3 | parts | 20 | $400.00 | $8,000 |  |  |  |
| 3 | Interface card |  |  |  |  |  |  |
| 3.1 | CAD |  |  |  | 25 | $2,275 | 2 |
| 3.2 | fabrication | 1 | $1,500.00 | $1,500 |  |  |  |
| 4 | Stave elect assbly |  |  |  |  |  |  |
| 4.1 | parts | 1 | $7,000.00 | $7,000 |  |  |  |
| 4.2 | hybrid+det test fixt |  |  |  | 25 | $1,900 |  |
| 4.3 | cable lamination |  |  |  | 25 | $1,900 |  |
| 4.4 | stave mount fixt |  |  |  | 80 | $6,080 |  |
| 4.5 | stave bond fixt |  |  |  | 80 | $6,080 |  |
| 4.6 | test box |  |  |  | 40 | $3,040 |  |
| 4.7 | storage box |  |  |  | 25 | $1,900 |  |
| 4.8 | electrical assembly |  |  |  | 160 | $9,280 |  |
| 6 | Test box | 2 | $700.00 | $1,400 |  |  |  |
| 7 | Student labor test |  |  |  |  | $35,000 |  |
|  | total protoyping |  |  | $151,675 |  | $99,470 |  |
|  | overhead |  | 1.0600 | $160,776 |  |  |  |
|  | SUM |  |  | $260,246 |  |  |  |
|  | est 2006 uncomm |  |  | $90,000 |  |  |  |
|  | LBNL REQUEST |  |  | $170,246 |  |  |  |
| notes: | 1. Substrates can contain more than one hybrid when printed |  |  |
|  | 2. CAD includes work which can be applied to final design |  |  |
|  | 3. Fabrication cost driven by quantity, ~factor 2 savings in production |  |
| rates | CAD rate 1 |  | $91.00 |  |  |  |  |
|  | shops rate |  | $76.00 |  |  |  |  |
|  | junior tech |  | $58.00 |  |  |  |  |
|  | senior tech |  | $82.00 |  |  |  |  |
| 4.1.4.1.2 |  |  |  |  |  |  |  |
| BNL Section |  |  |  |  |  |  |  |
|  | item | num | materials | total | hours | labor-cost | notes |
| 1 | Hamamatsu Short Strips |  |  |  |  |  |
| 1.1 | Order Remainder | 1 | $85,000.00 | $85,000.0 |  |  |  |
| 1.2 | QA Testing | 1 | $5,000.00 | $5,000.0 |  |  |  |
| 2 | NewDaq Software Development |  |  |  |  |
| 2.1 | 1/6 Engineering |  |  |  | 320 | $20,000 |  |
| 3 | Stave Metreology | 1 |  |  |  |  |  |
| 3.1 | Optical system | 1 | $5,000.00 | $5,000.0 |  |  |  |
| 4 | 2nd Stave Assembly |  |  |  |  |  |
| 4,1 | engineer | 1 |  |  | 80 | $5,000 |  |
| 4.2 | tech | 1 |  |  | 160 | $10,000 |  |
| 4.3 | fixtures | 1 | $5,000.00 | $5,000.0 |  |  |  |
| Subtotal |  |  | $100,000.00 | $100,000.0 | 560 | $35,000.00 |  |
| TOTAL | BNL Request |  |  | $135,000 |  |  |  |
| 4.1.4.1.3 |  |  |  |  |  |  |  |
| Hampton Section |  |  |  |  |  |  |
| 1 | cooling box |  |  | $5,000 |  |  |  |
| 2 | daq modules |  |  | $5,000 |  |  |  |
| 3 | testing and fab effort |  |  |  | $10,000 |  |
|  | subtotal |  |  | $10,000 |  | $10,000 |  |
|  | total |  |  | $20,000 |  |  |  |
| 4.1.4.3 |  |  |  |  |  |  |  |
| Cooling Channels (Bill Miller Effort) |  |  |  |  |  |
| 4.1.4.3.1 | Stave materials |  |  |  |  |  |  |
| 1.1 | Pre preg | 1 | $17,500.00 | $17,500 |  |  |  |
| 1.2 | Honeycomb | 1 | $4,000.00 | $4,000 |  |  |  |
| 4.1.4.3.2 | Stave design/eng |  |  |  |  |  |  |
| 2.1 | Engineering |  |  |  | 300 | $22,500 |  |
| 2.2 | Design effort |  |  |  | 100 | $3,500 |  |
| 4.1.4.3.3 | Fixtures |  |  |  |  |  |  |
| 3.1 | Fixture fabrication | 1 | $25,000.00 | $25,000 |  |  |  |
| 4.1.4.3.4 | Assembly and test |  |  |  |  |  |  |
| 4.1 | Materials testing | 1 | $5,000.00 | $5,000 |  |  |  |
| 4.2 | Assembly labor |  |  |  | 390 | $32,001 | 4 |
| 4.3 | stability test fixture | 1 | $5,000.00 | $5,000 |  |  |  |
| 4.4 | subtotals |  | $56,500.00 | $56,500 |  | $58,001 |  |
| TOTAL |  |  |  | $114,500.50 |  |  |  |
| rates | engineering |  | $75.00 |  |  |  |  |
|  | design |  | $35.00 |  |  |  |  |
| notes | 4. LBNL tech labor |  |  |  |  |  |  |

# Text boxes

75 

termination

12+12 