## Sheet1
Comparison of ETC current vs ETC presented at Lehman review
Current date: April 3, 2000
| ETC | ETC
WBS | Lehman | Current | Delta | Comments
1.1 | 8395 | 8770 | 375
1.1.1 | 1504 | 1586 | 82 | Includes advance purchase of optical
CMM from OGP moved from FY01
1.1.2 | 4824 | 4999 | 175 | Corrected labor rates for Santa Cruz used
1.1.2.1 | 2684 | 3612 | 928 | Includes acceleration payments to Temic(81K)
Emergency test system engineering add(47K)
Added procurement of 15% of total ICs
1.1.2.2 | 973 | 482 | -491 | All hybrid fabrication(without ICs attached)
procurement removed
1.1.2.3 | 1167 | 904 | -263 | All thermal baseboard procurement removed
1.1.3 | 2067 | 2185 | 118 | Parts cost changes based on nearly
final schematic and revised piece costs
for some parts.