U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 1) BCP Number: |  | 2) BCP Title: Revised FY01 OSU Funding |  |
| --- | --- | --- | --- |
| 3) Budget Number: WBS 1.1 |  | 4) MSA Title: U.S. ATLAS |  |
| 5) Date Submitted (Project Office): |  |  |  |
| 6) Change Designation: Priority [ ] Routine [ X ] | 7) BCP Level Level 0 [ ] Level 2 [X] Level 1 [ ] Level 3 [ ] | 8) Directed Change? Yes [ ] No [X ] |  |
| 10) Point of Contact: M. Gilchriese 11) Phone: 510-486-6790 12) FAX : 510-486-5101 12a) E-mail: gilg@sts.lbl.gov 13) Address: Lawrence Berkeley National Laboratory, MS50B-6208, 1 Cyclotron Rd., Berkeley CA 94720 |  |  |  |
| 14) Change Description: Modifications to FY01 BA for Ohio State. The changes are: costing(final payment) for FE-D2 DMILL submission in FY01 rather than FY00; addition of test board costs for optical IC prototypes; increase in design costs for optical hybrid(technical student); and increases in costs of optical hybrids prototypes, including additional prototype round in FR4 not included in ETC01. Additional prototype round is needed because of changes to interfaces to optical hybrids, not under OSU control. In addition, OSU will provide collaborators with test boards, need not fully understood when ETC01 estimate was made. |  |  |  |
| 15) Change Justification: Actual costs from OSU were not available at the time ETC01 estimate was made. Shift of payment of remaining bill for FE-D2 submission to FY01 was missed in ETC01 estimate. Other changes result from need to increase effort on optical ICs and optical prototypes to meet review scheduled for June 2001. |  |  |  |
| 16) Impact of Non-Approval: Optical IC and optical hybrid prototype schedule will be delayed. |  |  |  |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 17) BCP Number: | 18) BCP Title: Revised FY01 OSU Funding |  |  |
| --- | --- | --- | --- |
| 19) Impact on Cost Baseline: | Baseline (AY$ in Thousands) | Proposed (AY$ in Thousands) | AY$ Change |
| 1.1.1.3.2.1.1 FE-D2 1.1.1.3.2.4.2 Equip/Test Boards(OSU) 1.1.1.4.1.1.3 Design/Eng Opt Hybrids 1.1.1.4.2.2 Devel/proto opt Hybrids | 0 No WBS 0 40.8 | 18.6 7.3 2.4 52.7 | 18.6 7.3 2.4 11.9 |
| 20) Impact on Funding Profile: FY01 - 40.2K additional BA |  |  |  |
| 21) Explanation of Impact on Cost and Funding Baselines: Increases cost baseline by 40.2K |  |  |  |
| 22) Impact on Schedule Baseline: Allows schedule baseline to be met. |  |  |  |
| 23) Explanation of Impact on Schedule Baseline: See above. |  |  |  |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 24) BCP Number: | 25) BCP Title: Revised FY01 OSU Funding |  |  |  |
| --- | --- | --- | --- | --- |
| 26) Impact on Scope Baseline: |  |  |  |  |
| Item |  | Baseline | Proposed | Change |
| None |  |  |  |  |
| 27) Explanation of Impact on Scope Baseline: N/A |  |  |  |  |
| 28) Other Impacts: (Health, Safety, Environment, etc.) None |  |  |  |  |
| 29) Interim or Corrective Actions: None |  |  |  |  |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 30) BCP Number: | 31) BCP Title: Revised FY01 OSU Funding |  |  |
| --- | --- | --- | --- |

PROJECT DISPOSITION - LEVEL 3

| 32) REVIEW RECOMENDATIONS: |  |
| --- | --- |
| U.S. ATLAS Project Manager W. Willis | Disposition [ ] Approve [ ] Reject |
|  | DATE: |
| BNL Associate Laboratory Director T. Kirk | Disposition [ ] Approve [ ] Reject |
|  | DATE: |

# LHC PROJECT MANAGER DISPOSITION – LEVEL 2

| LHC Project Manager J. Yeck | Disposition [ ] Approve [ ] Reject |
| --- | --- |
|  | DATE: |
| NSF Project Manager | Disposition [ ] Approve [ ] Reject DATE: |

## AGENCY DISPOSITION - LEVEL 1

| 33) Joint Oversight Group | RECOMMENDATION |
| --- | --- |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| ATLAS/CERN | RECOMMENDATION |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| DISPOSITION |  |
| Chairperson Date [ ] Endorsed [ ] Approved [ ] Rejected |  |
| 34) Explanation (If Action is Approved with Conditions, or Not Concurred Upon) |  |