U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 1) BCP Number: XX | 2) BCP Title: Pixel Front-End Electronics/Die Sort |
| --- | --- |
| 3) Budget Number: WBS 1.1.1 | 4) MSA Title: U.S. ATLAS |
| 5) Date Submitted (Project Office): MM/DD/YY |
| 6) Change Designation: Priority [ X ] Routine [ ] | 7) BCP Level Level 0 [ ] Level 2 [ ] Level 1 [ ] Level 3 [X] | 8) Directed Change? Yes [ ] No [X ] |  |
| 10) Point of Contact: Abe Seiden 11) Phone: (831) 459-2923 12) FAX : (831) 459-5777 12a) E-mail: abs@scipp.ucsc.edu 13) Address: SCIPP/Natural Sciences II/University of California Santa Cruz/1156 High Street, Santa Cruz, CA 95064 |
| 14) Change Description: Release of management contingency for the procurement of front-end electronics and die sorting and probing of front-end electronics. |
| 15) Change Justification: Baseline funding for procurement of front-end electronics and for die sorting and probing of front-end die is insufficient for 2-hit pixel system. |
| 16) Impact of Non-Approval: An insufficient number of front-end electronics integrated circuits would be procured and the pixel detector could not be completed. Die sorting and probing of these integrated circuits would not be completed. |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 17) BCP Number: XX | 18) BCP Title: Pixel Front-End Electronics/Die Sort |
| --- | --- |
| 19) Impact on Cost Baseline: | Baseline (AY$ in Thousands) | Proposed (AY$ in Thousands) | AY$ Change |
| Fabrication(FE Electronics) 1.1.1.5.3.3 IC Die Sort Note that $ values are FY03 and not $AY | 51K 34K | 158K 155K | 107K 121K |
| 20) Impact on Funding Profile: The required funding profile is Baseline FY03 FY04 Fabrication(FE Electronics) 51 1.1.1.5.3.3 IC Die Sort 34 Management contingency FY03 FY04 Fabrication(FE Electronics) 107 1.1.1.5.3.3 IC Die Sort 76 45 Total FY03 FY04 Fabrication(FE Electronics) 158K 1.1.1.5.3.3 IC Die Sort 110 45 |
| 21) Explanation of Impact on Cost and Funding Baselines: The cost baseline will increase by the amount of the change. |
| 22) Impact on Schedule Baseline: The revised baseline schedule becomes Start Date Stop Date Fabrication(FE Electronics) 9/25/03 9/8/04 1.1.1.5.3.3 IC Die Sort 8/25/03 8/20/04 |
| 23) Explanation of Impact on Schedule Baseline: Fabrication does not include FE-I2(preproduction). However, IC die sort does include die sorting and reprobing of both preproduction and production FE integrated circuits. Fabrication funds must be committed before production by IBM begins. |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 24) BCP Number: xx | 25) BCP Title: Pixel Front-End Electronics/Die Sort |
| --- | --- |
| 26) Impact on Scope Baseline: |
| Item | Baseline | Proposed | Change |
| Fabrication(FE Electronics) 1.1.1.5.3.3 IC Die Sort | 894 ICs in detector 1519 ICs in detector | 2770 ICs in detector 6924 ICs in detector | 1876 ICs 5405 ICs |
| 27) Explanation of Impact on Scope Baseline: As proposed, the US would fund 20% of the total number of FE ICs needed for the 2-hit systems and would sort and reprobe 50% of the FE ICs needed for a 2-hit system. |
| 28) Other Impacts: (Health, Safety, Environment, etc.) None. |
| 29) Interim or Corrective Actions: None. |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 30) BCP Number: XX | 31) BCP Title: Pixel Front-End Electronics/Die Sort |
| --- | --- |

PROJECT DISPOSITION - LEVEL 3

| 32) REVIEW RECOMENDATIONS: |
| --- |
| U.S. ATLAS Project Manager W. Willis | Disposition [ ] Approve [ ] Reject |
|  | DATE: |
| BNL Associate Laboratory Director T. Kirk | Disposition [ ] Approve [ ] Reject |
|  | DATE: |

# LHC PROJECT MANAGER DISPOSITION – LEVEL 2

| DOE/NSF U.S. LHC Project Manager J. Yeck | Disposition [ ] Approve [ ] Reject |
| --- | --- |
|  | DATE: |
| NSF Project Manager | Disposition [ ] Approve [ ] Reject DATE: |

## AGENCY DISPOSITION - LEVEL 1

| 33) Joint Oversight Group | RECOMMENDATION |
| --- | --- |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| ATLAS/CERN | RECOMMENDATION |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| DISPOSITION |
| Chairperson Date [ ] Endorsed [ ] Approved [ ] Rejected |
| 34) Explanation (If Action is Approved with Conditions, or Not Concurred Upon) |