ENDCAP C INTEGRATION PLAN AND STATUS

| DATE | TASK | STATUS |
| --- | --- | --- |
| Apr. 21 | Attach 1C capillaries(S07-10) and leak check | Done 4/21 |
| Apr. 22 | Put capillaries S11-14 into thermal cycle | Done 4/22 |
| Apr. 23 | Put capillaries S15-18 into thermal cycle | Done 4/23 |
| Apr. 24 | Remove S11-14, leak check, pressure cycle, leak check Tack nuts on 1C | S11-13 OK but S14 has nut backwards Done 4/24 |
| Apr. 25 | Attach S11-14 to 2C and leak check Remove S15-18, leak check, pressure cycle, leak check |  |
| Apr. 26 | Attach S15-18 to 3C and leak check Tack nuts on 2C |  |
| Apr. 27 | Tack nuts on 3C Complete photo documentation of 1C, 2C and 3C and final inspection |  |
| Apr. 28 | Trial assembly of plastic holder Install plastic pieces captured during integration |  |
| May 1 | Integrate 1C and document/photo |  |
| May 2 | Integrate 2C and document/photo |  |
| May 3 | Integrate 3C and document/photo |  |
| May 4 | Add temporary endplate and complete plastic holder |  |
| May 5 | Add side panels to frame Final photo/documentation |  |
| May 8-12 | Slack in schedule |  |
| May 15 | Fly to CERN |  |