Endcap C Daily Status

May 16, 2006: Endcap C arrives at CERN. Visual inspection OK. Pictures are in "EndcapCArrivalCERN" in the usual spot, including subfolders of pictures taken at CERN. This daily section will be "archived" tomorrow in Word document and future entries will describe Endcap A. Congratulations to all!

May 15, 2006: Endcap C flies away at 0745. Smooth operation. Few pictures in "BonVoyageEndcapC" at the usual link.

May 12, 2006: Final organization for flying on May 15.

May 11, 2006: Packing in shipping box completed. Pictures of this in "ShippingBoxandBuggy".

May 10, 2006: Integration of endcap C is complete and it is ready to put into shipping box tomorrow. Pictures are in folder "EndcapCFinalIntegration" at the link at top.

May 9, 2006: LBL photo services pictures. Tube constraints added. Trial fit of rest of plastic holder. Regular pictures in the "EndcapCFinalIntegration" folder at the usual link top of page. Foam for inside shipping box arrives. Trial fit of box+extra foam in car.

May 8, 2006: Continuity testing completed. OK. Work on tube clamps and plate. Work on shipping box continues.

May 5, 2006: Leak check of 3 disks in frame complete and OK. However, cork used in leak testing fell and ended up on module on sector 9048 in disk 1C. Pictures in folder "LeakCheckEndcapC" in link at top of page, including cork. Cork removed(easy). Continuity testing done, no apparent damage. Continuity testing of all modules in progress(see pictures in "ContinuityTesting" folder). Protective side panels added. Started machining tube holder parts. Additional work on shipping box(ground off a bit on inside bottom to get more clearance and added labels) and modified baby carriage. Pictures of shipping box and buggy are in folder "ShippingBoxandBuggy".

May 4, 2006: Disk 3C was integrated into frame. There was an interference between the Disk 2 exhaust and the strain relief clamps on Disk 3C. Material on the clamps was removed. Remaining clearance between Disk 2 pipes and Disk 3 sector pipes is very small(0 to sub mm) but we decide to live with it. Pictures in folder at link at top.

May 3, 2006: Disk 2C was integrated into frame. Low resolution pictures at link at top.

May 2, 2006: Disk 1C was integrated into the endcap frame. Pictures are in a folder(Disk1CIntegration) at the link at the start of this page. Note there are some very high resolution shots from LBL photo services(and currently very big files).

May 1, 2006: Final capillary attached to 3C. Leak check OK. Glue(9396) added to exhaust strain reliefs on 1C, 2C, 3C. Bolt up and fit up of plastic holder parts underway. Work on shipping parts continues. Plan to start 1C integration tomorrow.

April 28, 2006: Initial fit-up of plastic holder pieces and aluminum temporary endplate completed. Final capilary for 3C leak check OK after pressure cycle. Thermal cycle over weekend.

April 27, 2006: Plastic machining/gluing continues. More work on shipping box, foam and shock logging. Started modifying baby buggy for moving box in airport. Photo documentation of 1C, 2C and 3C by LBL photo services.

April 26, 2006: Three capillaries added to 3C. Pass leak check. Plastic machining continues. Capillary glued yesterday passes leak check. Pressure cycle Friday, thermal cycle over weekend, test and install Monday. Paperwork, shipping procedures advancing.

April 25, 2006: Capillaries added to 2C. Pass leak check. Had to adjust one exhaust location. OK also. Nuts tacked on 2C. Three other capillaries pressured cycled and pass leak check. Ready to put on 3C tomorrow. Progress on plastic holder parts towards assembly planned for Friday. Another capillary glued to replace one with backward nut but wont be ready until May 1.

April 24, 2006: Added Endcap C plan and status link above. Nuts on 1C tacked. Three capillaries for 2C pass leak checks after pressure cycle. 4th had a nut on backwards! QA failure.

April 21, 2006: Capillaries attached to 1C and leak check OK. Capillaries for 2C and 3C will start thermal cycle Saturday and Sunday, respectively.

April 20, 2006: All disks have clamps replaced. Capillaries for 1C pass final test(after thermal cycle). Plan to attach them tomorrow. Capillaries for 2C and 3C are curing. Decided to make temporary endplate for C endcap, which means attaching clips to real endplate is off path now. Target date to begin integration of disks is May 1. Two visits yesterday to SFO, including trial of carrying box on plane in seat. Looks like hand carry can work. Target date for flight is May 15.

April 19, 2006; All 3 C-side disks have clamps replaced. Working on first A-side this afternoon. 1C capillaries in thermal cycle, will be done tomorrow afternoon. Plan to leak check and if OK attach Friday. Capillaries for 2C glued today. Will cure until Saturday and start thermal cycle then(reversal of test sequence). Stay clear regions identified but have decided to make temporary end plate and leave real one for attachment after system test on endcap C. Maurice and Gil visited SFO and talked to Continental and TSA. Encouraging enough that will go back tonight and hopefully trial fit box on 757 to make sure it works.

April 18, 2006: Room temperature cure looks good. 4 production capillaries OK after pressure cycle, thermal cycle starts today. Thick Type 0 clamps replaced with skinny ones on two rings. SLA clips for Type 0 on endplate look good, need to clarify stay-clear regions.

April 17, 2006: Capillary testing is summarized at link above. So far it looks like all OK with room temperature cure but will start testing 4 production capillaries tomorrow after 3 day cure. Pressure cycle tomorrow, then temperature cycle for 2 days. Production of SLA clamps for Type 0 underway and will begin replacement tomorrow. If capillaries are OK, then roughly expect to begin integration of completed disks(with capillaries, new clamps, tacked nuts, etc) on May 1.

April 14, 2006: We need more capillary samples. Decision to proceed with four tuned capillaries, glued as per procedure and let them cure over weekend and at least Monday AM. If OK, then 1st 4 production capillaries. This would give us 8 samples more to test. Together with previous, 11 samples made by Mario with room temperature cure. Two would be tested April 17 AM, pressured cycled and tested. One after thermal cycle(already pressure cycled) is OK.  Will also glue up samples using Cu plug soldered to capillary. Type 0 thin clamps look OK so production can start by April 17. Plastic machining proceeding but delayed by having to make capillaries. See link above for capillary status summary.

April 13, 2006: One more iteration of the Type 0 clamps is needed and is underway for tomorrow. Type 0 clip samples OK, given to make model for SLA parts. Status of capillaries is summarized in the table linked above.

April 12, 2006: 6 of 10 fittings on the 5 capillaries can be removed with just fingers. Very poor adhesion. We cured these at 150F for one hour after an overnight room temperature cure(to speed up). Is this the problem? Not clear. We did not do this in the qualification. Test sample passed all tests(including 50 cycles at 20 bar). It cured at room temperature. Started temperature cycling this sample. Cooked one fitting glued by Jon some weeks ago to 150F. It also fine after 50 20 bar cycles. Decide to make up 4 more samples, cure overnight. Two will be cooked at 150F tomorrow and 2 leak checked without this. Type 0 clamps redesigned and two variants submitted. Sample Type 0 clips that have to be glued on endplate produced.

April 11, 2006: Capillaries with fittings leak, or many fittings. Type 0 clamps not quite correct fit, need small modification.

April 10, 2006: Possible dirt found in 1A joint that leaked. Cleaned. 1A tubed checked. OK. Put back on. Leak tight. All U-tube and exhaust now on and leak checked OK. Test capillary glued fitting leaked checked (improved technique, new person doing the gluing). OK. Five capillaries glued. Type 0 cable clamps look good but need to countersink holes for lowest profile. Plastic holder fab continues.

April 7, 2006: Summary of status. U-tubes on all disks, OK. Exahust tubes on Disk 2 and 3 C and A, OK. Disk 1 exhaust positions were found last week to be wrong, removed. Disk 1C replaced and OK. Three of 4 on 1A OK, leak in 4th(found late today). In exhaust tube or at joint. To be investigated. Have developed method to tack nuts against vibration. Final skinny clamps(we hope) to hold Type 0 are in fab over the weekend. Design of plastic holder for transportation and holding in system test is complete. Materials in hand. Fabrication held up by illness of personnel. Seven capillaries tuned. Fitting gluing started on batch of 5 capillaries for Disk 1C. Transport box arrived. Visit to SF airport planned to discuss with airline and security. Roughly one month away from shipping to CERN is guess.

March 27, 2006: U-tubes attached to 3A. Leak check on U-tubes OK but leak found near other fitting on sector 9009. Investigating. Parts for plastic holder ordered. No progress on pieces for gluing Type 0 or fixing nuts on fittings against vibration loosening. Capillary tuning procedure still proceeding, trying first production sample tomorrow.

March 24, 2006: U-tubes attached to 2A. Leak check OK. U-tubes on 1A retorqued. No movement. Design of plastic holder continues. Concept for gluing Type 0 to strain reliefs(last item before insertion) developed. Development of capillary tuning continues(converging).

March 23, 2006: Disks 1C, 2C and 3C are inspected and have U-tubes and exhaust tubes attached and leak checked successfully. Disks 1A, 2A and 3A have been inspected. HV bonds on a module on 3A have been repaired and module tested OK. U-tubes have been attached and leak checked on 1A. Design of plastic shipment/system test holder parts underway.

ENDCAP C INTEGRATION PLAN AND STATUS

| PLAN | TASK | STATUS |
| --- | --- | --- |
| Apr. 21 | Attach 1C capillaries(S07-10) and leak check | Done 4/21 |
| Apr. 22 | Put capillaries S11-14 into thermal cycle | Done 4/22 |
| Apr. 23 | Put capillaries S15-18 into thermal cycle | Done 4/23 |
| Apr. 24 | Remove S11-14, leak check, pressure cycle, leak check Tack nuts on 1C | S11-13 OK but S14 has nut backwards Done 4/24 |
| Apr. 25 | Attach S11-14 to 2C and leak check Remove S15-18, leak check, pressure cycle, leak check | S11-13, S15 on 2C. OK. Done 4/25 Done 4/25 |
| Apr. 26 | Attach S15-18 to 3C and leak check Tack nuts on 2C | 3 attached and leak check OK 4/26 Final capillary on 3C OK 5/1 Done 4/25 |
| Apr. 27 | Tack nuts on 3C Complete photo documentation of 1C, 2C and 3C and final inspection | Complete 5/1 Photos done 4/27 |
| Apr. 28 | Trial assembly of plastic holder Install plastic pieces captured during integration | Done 4/28 Done 5/1 |
| May 1 | Integrate 1C and document/photo | Done 5/2 |
| May 2 | Integrate 2C and document/photo | Done 5/3 |
| May 3 | Integrate 3C and document/photo | Done 5/4 |
| May 4 | Add temporary endplate and fit up tube clamps Add side panels to frame Leak check all circuits | Done 5/5 Done 5/5 |
| May 5 | Continuity test Final photo/documentation | Done 5/8 Done 5/9 photo services |
| May 8 | Add tube clamps |  |
| May 9 | Continue adding tube clamps | Done 5/9 |
| May 10 | Route Type 0 and capillaries for shipping | Done 5/10 |
| May 11 | Close plastic. Photograph Pack in shipping box. Photograph | Done 5/11 |
| May 12 | Slack in schedule....or party as the case may be |  |
| May 15 | Fly to CERN | Done 5/15. |