ENDCAP C INTEGRATION PLAN AND STATUS

| PLAN | TASK | STATUS |
| --- | --- | --- |
| Apr. 21 | Attach 1C capillaries(S07-10) and leak check | Done 4/21 |
| Apr. 22 | Put capillaries S11-14 into thermal cycle | Done 4/22 |
| Apr. 23 | Put capillaries S15-18 into thermal cycle | Done 4/23 |
| Apr. 24 | Remove S11-14, leak check, pressure cycle, leak check Tack nuts on 1C | S11-13 OK but S14 has nut backwards Done 4/24 |
| Apr. 25 | Attach S11-14 to 2C and leak check Remove S15-18, leak check, pressure cycle, leak check | S11-13, S15 on 2C. OK. Done 4/25 Done 4/25 |
| Apr. 26 | Attach S15-18 to 3C and leak check Tack nuts on 2C | 3 attached and leak check OK 4/26 Final capillary on 3C OK 5/1 Done 4/25 |
| Apr. 27 | Tack nuts on 3C Complete photo documentation of 1C, 2C and 3C and final inspection | Complete 5/1 Photos done 4/27 |
| Apr. 28 | Trial assembly of plastic holder Install plastic pieces captured during integration | Done 4/28 Done 5/1 |
| May 1 | Integrate 1C and document/photo | Done 5/2 |
| May 2 | Integrate 2C and document/photo | Done 5/3 |
| May 3 | Integrate 3C and document/photo | Done 5/4 |
| May 4 | Add temporary endplate and fit up tube clamps Add side panels to frame Leak check all circuits | Done 5/5 Done 5/5 |
| May 5 | Continuity test Final photo/documentation | Done 5/8 Done 5/9 photo services |
| May 8 | Add tube clamps |  |
| May 9 | Continue adding tube clamps | Done 5/9 |
| May 10 | Route Type 0 and capillaries for shipping | Done 5/10 |
| May 11 | Close plastic. Photograph Pack in shipping box. Photograph | Done 5/11 |
| May 12 | Slack in schedule....or party as the case may be |  |
| May 15 | Fly to CERN | Done 5/15. |