U.S. ATLAS MOU NO. ?/00

Amendment

to

Memorandum of Understanding

between

University of New Mexico

and

The U.S. ATLAS Project Office

for Fiscal Year FY 2000

August 25, 1999

1.	Introduction

This Amendment is made to provide details of the work agreed to between the parties making the Memorandum of Understanding covering the specific  period of performance from October 1, 1999 through September 30, 2000.  It is subject to all the points of agreement and conditions in the current version of the parent Memorandum and the current version of the U.S. ATLAS Project Management Plan (U.S. ATLAS 97-7).

2.	Personnel

2.1.	List of Scientific Personnel

Participating scientists with anticipated fraction of their research time committed to ATLAS during this period of performance are:

| Name | ATLAS Fraction | Other Research Commitments/Comments |
| --- | --- | --- |
| Sally Seidel | 0.5 | CDF |
| Igor Gorelov | 0.5 | CDF |

2.2.	Institutional Board Representative

Sally Seidel is the present representative of the University of New Mexico on the U.S. ATLAS Collaboration Board.

2.3.	List of Technical Personnel

Participating technical personnel with the anticipated fraction of their time committed to ATLAS during this period of performance and their source(s) of support are:

Engineers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |  | ATLAS Project |
| M. Hoeferkamp | 0.75 | Infrastructure/UNM |

Designers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |  | ATLAS Project |
| None |  | UNIVERSITY OF NEW MEXICO |

Technicians

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| Geno Santistevan | 0.15 | UNIVERSITY OF NEW MEXICO |
| Trek Palmer | 0.30 | UNIVERSITY OF NEW MEXICO |
| None |  | ATLAS Project |

Software Professionals

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |  |  |

Others

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |  | ATLAS project |
| None |  | UNIVERSITY OF NEW MEXICO |

2.4.	Other Key Personnel

The Environment, Safety and Health officer for the University of New Mexico currently responsible for compliance with applicable ES&H policies associated with ATLAS participation by this institution is Marc A. Gomez of the University of New Mexico.  The Quality Assurance officer for the University of New Mexico currently responsible for QA compliance of tasks performed by this institution is Sally Seidel of the University of New Mexico.

3. 	Design, Prototype, Production and Installation Responsibilities

3.1.	Design, Prototype and Production Responsibilities for this Period of Performance

3.1.1	Deliverables: From U.S. ATLAS Project Funds:

The UNIVERSITY OF NEW MEXICO will receive a total of $24.0K for work on the Silicon Subsystem(WBS 1.1.1) FY00 ATLAS Project funds for the work and deliverables summarized in the tables below.

| WBS (L5) | Pixel System | 24.0 |
| --- | --- | --- |
| 1.1.1.2 | Pixel Sensors | 24.0 |
| 1.1.1.2.1 | Design/Engineering | 10.0 |
|  | Design validation of 2nd prototype sensors and preproduction sensors |  |
| 1.1.1.2.2 | Development/Prototypes | 14.0 |
|  | Labor, materials and supplies for pixel sensor testing |  |

Infrastructure funds will be provided by DOE to support Electrical Engineer Martin Hoeferkamp as indicated in the table below.

| WBS (L5) | Pixel System |  |
| --- | --- | --- |
| 1.1.1.2 | Pixel Sensors |  |
| 1.1.1.2.1 | Design of sensor testing and testing | 60.0 |

3.2.	Coordination and  Reporting

The U.S. ATLAS L2 Manager for the silicon subsystem is M. Gilchriese. The institution contact person for silicon subsystem activities at University of New Mexico is S. Seidel. The task managers for silicon subsystem activities carried out at University of New Mexico are as follows:

WBS 1.1.1.2 Pixel Sensors(S. Seidel)

3.3.	Collaboration with Other Groups and Institutions(no amendments are included in this section)

Design, construction and installation related to the silicon subsystem will be carried out in close communication and collaboration with other groups working on this and related subsystems.

4.	Contribution of Effort, Services and Equipment

4.1.	Effort

Subject to adequate funding by DOE or NSF, University of New Mexico will provide support for the scientific and technical personnel as indicated in section 2 during this period of performance.

5. 	Costs and Funding

An amount of $24.0K  from ATLAS Project funds will be provided for the period October 1, 1999 - September 30, 2000 to cover work described under 3.1.1.

6.	Administration (no amendments are included in this section)

7.	General Considerations (no amendments are included in this section)

8.	Schedules and Milestones

University of New Mexico will make every effort to carry out their institutional responsibilities consistent with the overall ATLAS schedule.  In this amendment are listed the program milestones for this period of performance.

8.1.	Design, Fabrication and Installation Milestones

The program milestones for this period of performance relevant to University of New Mexico are listed here:

| WBS | Item | Baseline | Current | Milestone |
| --- | --- | --- | --- | --- |
| 1.1.1 | Pixel System | 29-May-00 | 1-Sep-00 | Baseline review |
| 1.1.1.2 | Pixel Sensors |  |  |  |
| 1.1.1.2.1 | Design/Engineering |  |  |  |
|  |  | 20-Jan-00 | 20-Jan-00 | Final Design Review |
|  |  | 19-Jul-00 | 19-Jul-00 | Complete preproduction design |
| 1.1.1.2.2 | Development/protos |  |  |  |
|  |  | 20-Jan-00 | 20-Jan-00 | Complete testing 2nd prototypes |
| 1.1.1.2.3 | Production |  |  |  |
|  |  | 20-Jan-00 | 20-Jan-00 | Select production detector type |
|  |  | 20-Jan-00 | 20-Jan-00 | Select detector vendors |
|  |  | 24-Feb-00 | 24-Feb-00 | Start preproduction procurement |
|  |  | 22-Jun-00 | 22-Jun-00 | Complete preproduction procurement |

9.	Makers and Concurrence

The following persons concur in the terms of this Amendment.  These terms will be updated as appropriate in later Amendments to this Memorandum.

Makers of this Memorandum:

William J. Willis	date	William W. Britton	date

U.S. ATLAS Project Manager		University of New Mexico

M. Gilchriese	date

Silicon Subsystem L2 Manager

Concurrence:

Thomas B.W. Kirk	date

Associate Director, BNL