# U.S. ATLAS MOU NO. 9/01

Amendment

to

Memorandum of Understanding

between

Lawrence Berkeley National Laboratory

and

The U.S. ATLAS Project Office

For WBS 1.1 Silicon Subsystem

for Fiscal Year 2001

February 6, 2001

1.	Introduction

This Amendment is made to provide details of the work agreed to between the parties making the Memorandum of Understanding covering the specific  period of performance from October 1, 2000 through September 30, 2001.  It is subject to all the points of agreement and conditions in the current version of the parent Memorandum and the current version of the U.S. ATLAS Project Management Plan (U.S. ATLAS 99-20).

2.	Personnel

2.1.	List of Scientific Personnel

Participating scientists with anticipated fraction of their research time committed to ATLAS during this period of performance are:

| Name | ATLAS Fraction | Other Research Commitments/Comments |
| --- | --- | --- |
| M. Barnett | 0.2 | Particle Data Group, Theory |
| A. Ciocio | 1.0 |  |
| K. Einsweiler | 1.0 |  |
| V. Fadeyev | 1.0 |  |
| M. Garcia-Sciveres | 0.75 | CDF |
| M. Gilchriese | 1.0 |  |
| C. Haber | 0.75 | CDF |
| I. Hinchliffe | 0.5 | Theory |
| S. Loken | 0.1 | Administration |
| J. Richardson | 1.0 |  |
| A. Saavedra | 0.4 | New postdoc, arrives mid-year |
| M. Shapiro | 0.25 | CDF |
| J. Siegrist | 0.1 | Div. Head |
| H. Spieler | 0.1 | Instrumentation development |
| G. Trilling | 1.0 |  |
| L. Vacavant | 0.75 | CDF |
| F. Zetti | 0.25 | Visiting physicist |

2.2.	Institutional Board Representative

M. Gilchriese is the present representative of Lawrence Berkeley National Laboratory on the U.S. ATLAS Collaboration Board.

2.3.	List of Technical Personnel

Participating technical personnel with the anticipated fraction of their time committed to ATLAS during this period of performance and their source(s) of support are given below:

Engineers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| E. Anderssen | 1.0 | LBNL/ATLAS |
| P. Denes | 0.25 | ATLAS |
| F. Goozen | 0.9 | LBNL |
| E. Mandelli | 0.9 | LBNL/ATLAS |
| R. Marchessini | 0.25 | LBNL/ATLAS(left Jan. 1) |
| G. Meddeler | 0.9 | LBNL/ATLAS |
| V. Risk | 1.0 | ATLAS |
| J. Joseph | 0.1 | ATLAS |
| N. Hartmann | 0.9 | ATLAS |
| C. Vu | 0.75 | ATLAS |

Designers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| B. Holmes | 0.25 | ATLAS |
| J. Taylor | 1.0 | LBNL |
| D. Uken | 0.25 | ATLAS |
| Other designer | 0.5 | ATLAS |

Technicians

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| F. McCormack | 1.0 | LBNL |
| T. Weber | 1.0 | LBNL |
| J. Wirth | 1.0 | LBNL |
| G. Zizka | 0.25 | LBNL/ATLAS |
| T. Johnson | 0.5 | LBNL/ATLAS |
| R. Witharm | 1.0 | LBNL/ATLAS |
| C. Tran | 0.5 | ATLAS |

Others

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| Shop personnel | 1.0 | ATLAS |
| Student labor | 1.0 | LBNL/ATLAS |

2.4.	Other Key Personnel

The Environment, Safety and Health officer for Lawrence Berkeley National Laboratory currently responsible for compliance with applicable ES&H policies associated with ATLAS participation by this institution is Kathy Hardy of Lawrence Berkeley National Laboratory.  The Quality Assurance officer for Lawrence Berkeley National Laboratory currently responsible for QA compliance of tasks performed by this institution is M. Gilchriese of Lawrence Berkeley National Laboratory.

3. 	Design, Prototype, Production and Installation Responsibilities

3.1.	Design, Prototype and Production Responsibilities for this Period of Performance

Lawrence Berkeley National Laboratory is responsible for effort defined during the U.S. ATLAS Project Estimate-to-Complete concluded in March 2000, and documented in the U.S. ATLAS Cost Books in the following WBS areas:

| WBS | Task Description |
| --- | --- |
| 1.1.1.1.1 | Mechanics Design |
| 1.1.1.1.2 | Prototypes |
| 1.1.1.1.3 | Production |
| 1.1.1.3.1 | Electronics Design |
| 1.1.1.3.2 | Prototypes |
| 1.1.1.4.1 | Design |
| 1.1.1.4.2 | Prototypes |
| 1.1.1.5.1 | Modules Design |
| 1.1.1.5.2 | Prototypes |
| 1.1.1.6 | Beam/System Test Support |
| 1.1.2.1.1 | IC Electronics Design |
| 1.1.2.1.2 | Development & Prototypes |
| 1.1.2.1.3 | Production |
| 1.1.2.2.2 | Hybrids/Cables/Fanouts Fabrication |
| 1.1.2.2.3 | Hybrids/Cables/Fanouts Production |
| 1.1.2.3.1 | Design of Assembly & Test Tooling |
| 1.1.2.3.2 | Development & Prototypes |
| 1.1.2.3.3 | Production |

3.2.	Coordination and  Reporting

The U.S. ATLAS L2 Manager for the silicon subsystem is M. Gilchriese. The institution contact person for silicon subsystem activities at Lawrence Berkeley National Laboratory is M. Gilchriese. The task managers for silicon subsystem activities carried out at Lawrence Berkeley National Laboratory are as follows:

WBS 1.1.1 Pixel System (M. Gilchriese)

WBS 1.1.1.1 Mechanics (M. Gilchriese)

WBS 1.1.1.3 Electronics (K. Einsweiler)

WBS 1.1.1.5 Modules (M. Garcia-Sciveres)

WBS 1.1.2 Silicon Strip System (C. Haber)

WBS 1.1.2.1 Silicon Strip IC Electronics (A. Ciocio)

WBS 1.1.2.2 Silicon Strip Hybrids (C. Haber)

WBS 1.1.2.3 Silicon Strip Modules (C. Haber)

- Collaboration with Other Groups and Institutions

No amendments are included in this section.

Design, construction and installation related to the silicon subsystem will be carried out in close communication and collaboration with other groups working on this and related subsystems.

4.	Contribution of Effort, Services and Equipment

4.1.	Effort

Subject to adequate funding by DOE , Lawrence Berkeley National Laboratory will provide support for the scientific and technical personnel as indicated in section 2 during this period of performance.

5. 	Costs and Funding

Funds in the amount of $1,574.8k will be provided for the period October 1, 2000 to September 30, 2001.  This funding level was determined by the following analysis:

5.1	Scope of Work

The U.S. ATLAS Project completed a re-estimate of it’s cost and schedule in January 2001, and a baselining of the Pixel Subsystem.  This MOU supercedes or take precedent over all prior agreements between Lawrence Berkeley National Laboratory and the U.S. ATLAS Project Office.

The cost of work assigned or proposed by Lawrence Berkeley National Laboratory for the Silicon Subsystem, including: work that was completed, in-progress or planned through Fiscal Year 2001 is shown at Level 5 of the US Atlas WBS structure in Table 1. This table is consistent with the actual cost reported ending in Fiscal Year 2000 and the Silicon Subsystem’s work plan for Fiscal Year 2001.

## Table 1

Cumulative Cost Plan

| WBS | Task Description | Cumulative (AY $k) Cost Plan Inception through FY01 |
| --- | --- | --- |
| 1.1.1.1.1 | Mechanics Design | 909.8 |
| 1.1.1.1.2 | Prototypes | 632.6 |
| 1.1.1.1.3 | Production | 204.3 |
| 1.1.1.3.1 | Electronics Design | 572.7 |
| 1.1.1.3.2 | Prototypes | 442.8 |
| 1.1.1.4.1 | Design | 0.0 |
| 1.1.1.4.2 | Prototypes | 16.1 |
| 1.1.1.5.1 | Modules Design | 109.6 |
| 1.1.1.5.2 | Prototypes | 316.2 |
| 1.1.1.6 | Beam/System Test Support | 28.5 |
| 1.1.2.1.1 | IC Electronics Design | 641.4 |
| 1.1.2.1.2 | Development & Prototypes | 144.8 |
| 1.1.2.1.3 | Production | 15.0 |
| 1.1.2.2.2 | Hybrids/Cables/Fanouts Fabrication | 107.9 |
| 1.1.2.2.3 | Hybrids/Cables/Fanouts Production | 153.9 |
| 1.1.2.3.1 | Design of Assembly & Test Tooling | 110.5 |
| 1.1.2.3.2 | Development & Prototypes | 28.5 |
| 1.1.2.3.3 | Production | 307.2 |
|  | Cumulative Cost Plan (FY 96-01) | 4741.8 |

5.2	Review of Funding Allocations

Lawrence Berkeley National Laboratory has been allocated the following funds (Table 2) to perform work on behalf of the U. S. ATLAS Project for the Silicon subsystem.

## Table 2

Total Budget Allocation

|  | Budget Allocations $k |
| --- | --- |
| Budget Allocation (BA) | FY 96 | FY 97 | FY 98 | FY 99 | FY 00 | Total BA |
| DOE | 182.0 | 314.0 | 633.0 | 715.0 | 1,323.0 | 3,167.0 |
| NSF |  |  |  | - | - | - |
| Total Budget Allocation |  |  |  |  |  | 3,167.0 |
| Includes funding from inception through 8/15/00 |  |  |  |  |  |

5.3	Current Funding Allocation

This MOU establishes the net additional allocation of funding that will be provided to Lawrence Berkeley National Laboratory for work planned through Fiscal Year 2001.  The Current Funding Allocation is the difference between the Total Budget Allocation of all prior funding actions (Table 2) and the Cumulative Cost Plan for work planned through Fiscal Year 2001 (Table 1). See Table 3 for summary details.

Table 3

Current Funding Allocation

| Financial Summary | $k |
| --- | --- |
| Cost Plan Requirement (inception - FY 00) | 4,741.8 |
| Current Budget Allocation | 3,167.0 |
| New Budget Allocation | 1,574.8 |
| Total Additional DOE Funding Request | 1,574.8 |
| Total Additional NSF Funding Request | - |
| Current Funding Allocation | 1,574.8 |

6.	Administration (no amendments are included in this section)

7.	General Considerations (no amendments are included in this section)

8.	Schedules and Milestones

Lawrence Berkeley National Laboratory will make every effort to carry out their institutional responsibilities consistent with the overall ATLAS schedule.  In this amendment are listed the program milestones for this period of performance.

8.1.	Design, Fabrication and Installation Milestones

The program milestones for this period of performance relevant to Lawrence Berkeley National Laboratory and supported by the amended FY01 funding are listed here and correspond to the revised (ETC) baseline schedule:

| WBS | Milestone | Baseline | Current |
| --- | --- | --- | --- |
| 1.1.1 | US ATLAS Pixel Project |  |  |
| 1.1.1.1.1 | MechanicsDesign |  |  |
|  | Disk Sector PRR | 6/20/01 | 6/20/01 |
|  | Global Support CDR | 6/20/01 | 6/20/01 |
|  | Support tube CDR | 6/20/01 | 6/20/01 |
|  | Cables/services CDR | 6/20/01 | 6/20/01 |

| WBS | Milestone | Baseline | Current |
| --- | --- | --- | --- |
| 1.1.1.1.2 | Development/Prototypes |  |  |
|  | Complete sector development | 6/20/01 | 6/20/01 |
| 1.1.1.2 | Sensors |  |  |
| 1.1.1.2.1 | Design |  |  |
|  | Compl. Spec for production order release | 3/12/01 | 3/12/01 |
|  | ATLAS PM approval of production procurement | 7/23/01 | 7/23/01 |
|  | Release initial MC for sensors/testing | 7/23/01 | 7/23/01 |
| 1.1.1.2.3 | Production |  |  |
|  | Start preproduction fab | 10/2/00 | 10/2/00 |
|  | First preproduction wafers delivered | 2/16/01 | 2/16/01 |
| 1.1.1.3 | Electronics |  |  |
| 1.1.1.3.1 | Design |  |  |
|  | DMILL Review | 12/15/00 | 12/15/00 |
|  | DMILL decision (FE-D3 or not) | 2/15/01 | 2/15/01 |
|  | FE-I1 spec complete | 5/16/01 | 5/16/01 |
|  | FE-I1 FDR | 6/13/01 | 6/13/01 |
| 1.1.1.3.2 | Development/Prototypes |  |  |
|  | Submit TSMC digital test chip | 1/8/01 | 1/8/01 |
|  | Digital test chip delivered | 3/16/01 | 3/16/01 |
|  | Submit TSMC analog test chip | 3/5/01 | 3/5/01 |
|  | Analog test chip delivered | 5/11/01 | 5/11/01 |
|  | FE-D3 submitted | 5/2/01 | 5/2/01 |
|  | FE-D3 wafers arrive | 8/22/01 | 8/22/01 |
| Sil L2/6 | 1st IBM prototype submitted(FE-I1) | 7/26/01 | 7/26/01 |
| 1.1.1.4 | Flex Hybrids/Optical Hybrids |  |  |
| 1.1.1.4.1 | Design |  |  |
|  | Flex Hybrid FDR | 12/15/00 | 12/15/00 |
|  | Optical package decision | 6/15/01 | 6/15/01 |
| 1.1.2 | Silicon Strip System |  |  |
| 1.1.2.1 | IC Electronics |  |  |
| 1.1.2.1.1 | Design |  |  |
|  | Production Readiness Review (PRR) | 6/15/01 | 6/15/01 |
| 1.1.2.1.2 | Development & Prototypes |  |  |
|  | Test Systems Complete | 8/3/01 | 8/3/01 |
| 1.1.2.1.3 | Production |  |  |
|  | Complete preproduction fab | 2/28/01 | 2/28/01 |
|  | Complete preproduction design verification | 5/23/01 | 5/23/01 |
| Sil L2/1 | Release/Start Full Electronics Production | 7/6/01 | 7/6/01 |

| WBS | Milestone | Baseline | Current |
| --- | --- | --- | --- |
| 1.1.2.2 | Hybrids/Cables/Fanouts |  |  |
| 1.1.2.2.1 | Design |  |  |
|  | Hybrid/Module Final Design Review | 4/16/01 | 4/16/01 |
|  | Start Procurement for Production Hybrid Assembly | 3/5/01 | 3/5/01 |
|  | Release Hybrid Production Dwg/Specs | 4/2/01 | 4/2/01 |
|  | Release Hybrid Bids | 4/30/01 | 4/30/01 |
|  | Hybrid Bid Evaluation Complete | 6/11/01 | 6/11/01 |
|  | Hybrid/Module Production Readiness Review | 9/3/01 | 9/3/01 |
|  | Complete Award Hybrid Contracts | 9/14/01 | 9/14/01 |
| 1.1.2.2.3 | Production |  |  |
|  | Compl Preproduction Assy | 8/13/01 | 8/13/01 |
|  | Compl Testing of Preprod Hybrid | 9/3/01 | 9/3/01 |
|  | 1st Preproduction Hybrids Avail for Mod Assy | 6/4/01 | 6/4/01 |
| 1.1.2.3 | Module Assembly and Test |  |  |
| 1.1.2.3.1 | Design of Assembly & Test Tooling |  |  |
|  | Compl Design of Proto Mod Assy/Test | 3/5/01 | 3/5/01 |
|  | Compl Design of Preprod Mod Assy/Test | 9/3/01 | 9/3/01 |
|  | Module FDR | 4/16/01 | 4/16/01 |
|  | Module PRR | 9/3/01 | 9/3/01 |
| 1.1.2.3.2 | Development & Prototypes |  |  |
|  | Compl Assy of Proto Modules | 3/5/01 | 3/5/01 |
|  | Compl Test/Measure Proto Modules | 4/16/01 | 4/16/01 |
| 1.1.2.3.3 | Production |  |  |
|  | Complete Preproduction Module Assembly | 7/30/01 | 7/30/01 |
|  | Complete Preproduction Module Testing | 9/3/01 | 9/3/01 |

9.	Makers and Concurrence

The following persons concur in the terms of this Amendment.  These terms will be updated as appropriate in later Amendments to this Memorandum.

Makers of this Memorandum:

William J. Willis	date	Jim Siegrist	date

U.S. ATLAS Project Manager		Director, Physics Division

Lawrence Berkeley National Laboratory

M. Gilchriese	date

Silicon Subsystem L2 Manager

Concurrence:

Thomas B.W. Kirk	date

Associate Director, BNL