## Sheet1
|  | Silicon: List of Concerns |  |  | Based on Mar 01 Status
|  |  | Baseline | Baseline
WBS | ID | Description | Start | Completion | % Compl | SV | Remarks
1.1.1
1.1.1.2.1 | 93 | Sensors 'Complete Spec for Production Order' | 2001-03-12 | 2001-03-12 | 0 | 0 | Forecast Date is 6/15/01
1.1.2
1.1.2.2.1 | 99 | Start Procurement for Production Hybrid | 2001-03-05 | 2001-03-05 | 0 | 0 | Forecast Date is 5/25/01
1.1.2.3.1 | 134 | Design of Prototype Assembly & Test | 1998-09-08 | 2001-03-05 | 50 | 0 | Forecast Compl is 4/25/01
1.1.2.3.1 | 138 | Design of Production Assembly & Test | 2001-03-19 | 2002-02-08 | 0 | 0
1.1.2.3.2 | 146 | Assembly of Prototypes Modules | 1999-11-04 | 2001-03-05 | 89 | 0 | Forecast Compl is 5/20/01
1.1.3
1.1.3.3.4 | 14 | ROD Controler Design | 2000-01-03 | 2000-04-05 | 98 | 0
1.1.3.3.6 | 18 | Board Level Simulation FY01 | 2000-10-02 | 2001-03-15 | 80 | -12298
1.1.3.3.7 | 22 | Pixel Specific Formater VHDL FY01 | 2000-10-02 | 2001-03-01 | 50 | -15373
1.1.3.4.3 | 32 | Production Diagnostic Test Stand Compl | 2000-09-29 | 2000-09-29 | 0 | 0
1.1.3.4.3 | 33 | SCT/Pixel Test Stand S/W FY01 | 10/2/00 | 5/21/01 | 50 | -24083
1.1.3.7.1 | 56 | Updating of ROD to Production Model | 11/30/00 | 4/13/01 | 35 | -24838
1.1.3.8.4 | 91 | Purchase ROD Crates Fy01 | 3/6/01 | 9/28/01 | 0 | -616
-77208