U.S. ATLAS PROJECT OFFICE

Physics Department

UPTON, NEW YORK 11973

July 25, 2001

Mr. James Yeck

Department of Energy

Fermi Group

POB 2000

Batavia, IL 60510

Dr. Thomas Kirk

Associate Laboratory Director

Brookhaven National Laboratory

Upton, NY  11973

SUBJECT:  U.S. ATLAS Project Monthly Status Report for May 2001

Dear Sirs:

Attached please find Monthly Status Report No. 39 for the U.S. ATLAS Project.

Sincerely yours,

William J. Willis

U.S. ATLAS Project Manager

Distribution:

Abolins, M.

Alam, S.

Baker, K.

Barnett, M.

Bensinger, J.

Blair, R.

Butehorn, C.

Carolan, P. - DOE

Cleland, W.

Crawford, G.

Cullen, J. – PAP

De, K.

Dodd, J.

Ernst, R.

Errede, S.

Feldman, G.

Gilchriese, M.

Goldberg, M. - NSF

Gordon, H.

Firestone, A. - NSF

Harrison, M. – PAP

Hinchliffe, I.

Huth, J.

Kagan, H.

Kane, S.

Kirby, D.

Kirk, T.

Lankford, A.

Larsen, R. - PAP

Lissauer, D.

Lubatti, H.

Mantsch, P. - PAP

Murtagh, M.

Neal, H.

Norton, S.

Ogren, H.

Oh, S.

Parsons, J.

Pilcher, J.

Polychronakos, V.

Premisler, L.

Price, L.

Rijssenbeek, M.

Ritchie, J., DOE

Rutherfoord, J.

Seiden, A.

Seidel, S.

Siegrist, J.

Sikinger, P.

Sinkular, M., NSF

Skubic, P.

Slattery, P.

Sliwa, K.

Sondericker, J.

Stroynowski, R.

Taylor, F.

Toohig, T., DOE

Tuts, M. – PAP

Whitaker, S.

Wolbers, S. - PAP

Williams, H.

Willis, W.

Wu, S.L.

Yeck, J.

PROJECT STATUS REPORT No. 39

REPORTING PERIOD

May 2001

TABLE OF CONTENTS

Page

- Project Objective	1

- Technical Approach Changes	2

- Project Manager’s Summary	2

- Technical Progress –subsystem managers’ summaries	3

- Open Items between DOE/NSF and U.S. ATLAS	7

- Summary Assessment and Forecast	7

1.  Financial Status	7

2.  Schedule Status	7

3.  Baseline Change Proposals	7

Table 6-1 - Summary Cost Estimate	8

Figure 6-1 - Project System Network	9

- Funding	10

Table 7.1 - Summary of Funds Authorized & Total Costs and Commitments to Date	10

Table 7.2 - FY 2001 Funds – U.S. ATLAS Summary by Institution and Subsystem	11

- Performance Analysis	12

- Figure 9-1 - Budget Authority, Costs and Obligations 	15

- Table 10-1 - Cost Schedule Status Report by WBS	16

- Figure 11-1 - Milestone Schedule Status Report	17

Figure 11-2 - Line of Balance Chart	18

- Table 12-1 - Milestone Log	19

- NSF COST SCHEDULE STATUS REPORT	24

Table 13 – Cost Schedule Status Report	26

14.	DETAILED TECHNICAL PROGRESS REPORTS	27

WBS 1.1	Silicon 	27

WBS 1.2	TRT	47

WBS 1.3	LAr	59

WBS 1.4	Tile	75

WBS 1.5	Muon	81

WBS 1.6	Trigger/DAQ	101

# 1.  PROJECT OBJECTIVE

The U.S. ATLAS Project consists of the activities to design, supply, install and commission the U.S. portion of the ATLAS detector.  The detector will become part of the Large Hadron Collider (LHC) at CERN, the European Laboratory for Particle Physics.  The ATLAS detector is being designed to understand the dynamics of electroweak symmetry breaking.  The U.S. ATLAS collaboration is funded jointly by the U.S. Department of Energy and the National Science Foundation.

The fundamental unanswered problem of elementary particle physics relates to the understanding of the mechanism that generates the masses of the W and Z gauge bosons and of quarks and leptons.  To attack this problem, one requires an experiment that can produce a large rate of particle collisions of very high energy.  The LHC will collide protons against protons every 25 ns with a center-of-mass energy of 14 TeV and a design luminosity of 1034 cm-2 s-1.  It will probably require a few years after turn-on to reach the full design luminosity.

The detector will have to be capable of reconstructing the interesting final states.  It must be designed to fully utilize the high luminosity so that detailed studies of rare phenomena can be carried out.  While the primary goal of the experiment is to determine the mechanism of electroweak symmetry breaking via the detection of Higgs bosons, supersymmetric particles or structure in the WW scattering amplitude, the new energy regime will also offer the opportunity to probe for quark substructure or discover new exotic particles.  The detector must be sufficiently versatile to detect and identify the final state products of these processes.  In particular, it must be capable of reconstructing the momenta and directions of quarks (hadronic jets, tagged by their flavors where possible), electrons, muons, taus, and photons, and be sensitive to energy carried off by weakly interacting particles such as neutrinos that cannot be directly detected.  The ATLAS detector will have all of these capabilities.

The ATLAS detector is expected to operate for twenty or more years at the CERN LHC, observing collisions of protons, and recording more than 107 events per year.  The critical objectives to achieve these goals are:

- Excellent photon and electron identification capability, as well as energy and directional resolution.

- Efficient charged particle track reconstruction and good momentum resolution.

- Excellent muon identification capability and momentum resolution.

- Well-understood trigger system to go from 1 GHz raw interaction rate to ~100 Hz readout rate without loss of interesting signals.

- Hermetic calorimetry coverage to allow accurate measurement of direction and magnitude of energy flow, and excellent reconstruction of missing transverse momentum.

- Efficient tagging of b-decays and b-jets.

The U.S. ATLAS cost objective is $163.75M while supplying initially the work scope described in Appendix 3 of the Project Management Plan (PMP) and, if possible, all the goals described in Appendix 2 of the PMP.

The ATLAS project was initiated in FY 1996, and is scheduled for a 10-year design and fabrication period beginning in the first quarter of FY 1996, and finishing in FY 2005.  This period will be followed by operation at the LHC.

# 2.  TECHNICAL APPROACH CHANGES

No change.

# 3.  PROJECT MANAGER’S SUMMARY ASSESSMENT – W. Willis

Attention should be paid to two important points in this Report, both found in the report for the Liquid Argon Calorimeter, WBS 1.3.

This detector comprises a very large number of fast, high dynamic-range read out channels.  The front-end electronics for this system are buried deep inside the detector, leading to complex arrangements for access, cooling and inside a region subject to high radiation fields.  The U.S. has assumed the primary responsibility for designing and producing this system, as the result of a process in ATLAS that concluded that the U.S. team was best qualified for this difficult task.  In order to accumulate sufficient resources to carry out the production and testing of the system, a number of funding entities were required to cooperate in sharing the expenses.  It was important, in the view of U.S. Management, to retain technical and managerial control over this task while assembling the required funds.  This required a long effort on the part of the physicist representatives with the essential mediation of the Electronics Coordinator for Liquid Argon, Bill Cleland, and the former and present ATLAS Financial Coordinators, Peter Schmid and Marcus Nordberg.  This effort led to a final agreement in May.  Leadership on the part of the CERN group, in providing the last increment of funding that allowed the Agreement to be completed, is gratefully acknowledged.  The Agreement is just in time to allow the production to proceed, under conditions that should permit a smooth operation.

There is bad news connected with the same area of LAr Calorimeter readout.  There are many electronic systems in the four LHC experiments that are exposed to radiation, and need a voltage regulator which will survive in the radiation field.  It has long been known that the standard industrial devices will not survive in the radiation environment.  For this reason, and to avoid the cost of duplicate efforts in the experiments, CERN took the initiative to establish a common effort with a major European vendor to develop devices that would be available to all the experiments.  The LA Calorimeter in ATLAS is, we believe, the largest user.  The initiative of CERN to avoid duplication is surely commendable, but it has introduced a correlated problem across the board.  The CERN Directorate has taken an interest in this problem, and the Research Director has been in contact the leadership of the vendor, who promise that the required part will be delivered as soon as possible.  Nevertheless, there will be a substantial delay due to the late availability of the regulators.  Testing is proceeding with radiation-soft devices, and the new schedule will be fixed when the regulator delivery is known, but a few months delay is likely.

# 4.  technical progress - subsystem mangers’ summaries

1.1 Subsystem Manager's Summary 	Murdock Gilchriese (Lawrence Berkeley Lab.)

1.1.1 Pixels

Overall the work in most areas of the pixel system is proceeding as planned. First results on a 0.25-micron analog test chip are encouraging and this process appears to be both very rad-hard and predictable (measurements agree with simulations). However, some risks for delay (1-2 months) are starting to appear in some elements of the mechanics, the front-end IC and flex hybrids. It is likely there will be at least a one month delay in the submission of the first major engineering run that will include the four custom ICs needed for the pixel system, and this remains the critical path item.

1.1.2 Silicon Strip System

Preparations for the SCT ASIC PRR in July continued in May. The wafer probing system is now operational at Santa Cruz and CERN (but limited by lack of access to a dedicated probe station) and nearly operational at RAL. Analysis of test data still must be done at CERN, but there is progress in providing access to the rather complicated analysis code that determines the yield.

The SCT barrel module FDR was completed in May. Preproduction orders for hybrids (Japan) and baseboards (UK/CERN) will be now be placed. Detector fabrication is already in progress.

Considerable progress was made to resolve software problems with the module assembly system at LBNL. A few days trip to RAL was required to understand these problems and to be updated on tooling design.

1.1.3 ReadOut Drivers

The prototype ROD has now been debugged enough to schedule an integration test at Cambridge with the Back-of-Crate Card and the Timing Interface Module. This will occur at the end of June into early July. This is a major milestone for the RODs.

1.2 Subsystem Manager's Summary 	Harold Ogren (Indiana University)

1.2.1 Mechanics

Component systems continued in production during May. We completed the certification of assembly processes. All aspects of production were restarted by the middle of May. Most of the assembly processes at Duke and Indiana are now compatible if not identical, and the entire production flow is standardized to a set of unified procedures.

Four modules are completed at Indiana, six modules completed at Duke, and eight modules in production. Gain tests on three type 2 modules have been carried out at Duke, and one type 1 module from Indiana will soon start gain tests at Duke. Module 2.1 is at University of Pennsylvania for systems tests and module 1.01 at Dubna undergoing a reactor test.

1.2.5 Electronics

The final engineering run of ASDBLR and DTMROC wafers were due back in June, however, at the end of May we were informed by TEMIC that the ASDBLR/DTMROC processing run submitted on 15 January had had significant processing problems - leading to the certain loss of at least 25% of each wafer (one quadrant). We have arranged for some of the chips to be packaged to see if any of the chips are recoverable. TEMIC is starting more wafers through the line, but have not yet given us a ship date for the backup processing.

We have made good progress with Signetics on defining a custom FBGA package for the ASDBLR (DTMROC to follow). An FBGA package would be small enough to fit on the barrel stamp boards, thus obviating the need for wire bonding (Chip On Board) to the board and, in addition would be a lower mass, lower inductance, lower capacitance solution for the End Cap. The goal here is to have a design and tooling ready for delivery of the DMILL wafers - now more plausible given the TEMIC problems.

Additional stamp boards have been bonded at Lund and are now being tested at Penn. Lund is also working on a non- chip on board design based upon getting silicon in smaller packages.

1.3 Subsystem Manager's Summary 	Richard Stroynowski (Southern Methodist University)

Good progress on cryostat and feedthroughs: The cryostat is on its way to CERN: It is transported via ship to Rotterdam, on barge along Rhine to Strassbourg and then on truck to Geneva. Its arrival at CERN is expected at the end of June and the start of acceptance tests is planned for July.

Feedthrough production continues at a good pace. Mechanical components of HV feedthroughs are completed and there are 18 completed and ready to ship signal FT. Pin carrier production rate continues to be higher than needed.

Preparations for the FT installation have started. In order to protect HV cables, a decision was made to install HV ports first, followed by signal FT installation and finally to install HV cables last.

The award of the contract for cryogenics components was delayed because the bids came higher than expected. Negotiations continue.

The protracted discussion on the re-alignment of the responsibilities for the FEB production and purchase of its components has been finally concluded. In the new scheme, US groups will be fully responsible for the production and assembly of the FEB boards excluding several of the radiation tolerant chips, SCAs, voltage regulators and 50% of ADCs. A loan covering missing funds for the SCA will be extended by CERN. There is no change in the overall US financial obligations, and there is a much simpler matrix of responsibilities.

The technical progress on the Front-End electronics remains an area of concern. On the positive side - the preamps and layer sum boards production is proceeding well and the prototypes of 5 out of 7 radiation tolerant digital chips have been delivered and successfully tested. The tests of the 1/4 FEB are expected to be on schedule. However, additional delays have been incurred by the failure of the radiation tolerant voltage regulators developed under CERN guidance. A search for alternate solutions has started, but a delay in completion of the overall design of the board is expected. Another unresolved problem is the identification of radiation tolerant power supplies. Here, the main problem lies in keeping the cost of acceptable technical solutions to be within allocated budget.

There is steady progress in the motherboards production with 5 sets sent already to France. The contract for baseplane production has been awarded.

The production of the FCAL-C module (both mechanical and cold electronics) proceeds ahead of recent expectations.

1.4 Subsystem Manager's Summary 	Lawrence Price (Argonne National Lab.)

Submodule production was completed at the University of Chicago, with a total of 194 submodules constructed.  Other submodule and module production continues on schedule.  A design for the extended barrel support saddle has been completed and sent to ATLAS Technical Coordination for evaluation.  Iteration of the structural analysis is continuing.  Checks have so far verified the result that stresses and deflections of the saddles are within acceptable limits.  Instrumentation work is proceeding well.  It is not quite as routine as the mechanical production because of the variability of scintillator light output and fiber transmission, plus the possibility of fiber misalignment.  PMT testing also continues well, but some delays have been encountered in receiving PMT batches and the frid of reference tubes.  3-in-1 card production is complete and burn-in and testing is approaching the 50% point.  Volume deliveries of the motherboards will begin in June.  ITC production is on schedule.

1.5 Subsystem Manager's Summary 	Frank Taylor (MIT)

Work continued on the ATLAS endcap muon system during May with a Production Advancement Review (PAR), a review of the big wheel design at CERN, chamber and alignment parts production and mechanical and electrical engineering of critical items.

The PAR was held at Harvard University May 4-5. Presentations were given on all aspects of the ATLAS Endcap system - with an emphasis on the MDT chamber construction, services and electronics. The results of the review are given in ATC-RM-ER-0013. The reviewers noted good progress on the production of bare MDT chambers at the three U.S. MDT production sites and gave strong encouragement to accelerate the production and installation of chamber services (gas manifolds, Faraday cages, electronics, etc.). A number of findings were recorded and seven general action items noted - most to be answered by September 2001.

The Big Wheel Final Design Review (Part 1) was held at CERN May 14, 2001. Bensinger, Coco, Daly, Mulhall and Polychronakos attended. The summary comments of Coco are:

"The overall impression of the material presented at the ATLAS Big Wheel Final Design Review 1 (FDR1) is very positive. The time and focus on details of the big wheel design were in evidence. It was reported that a comparison between the FEA analysis results completed by the VNIITF design team and CERN engineering agreed to ~10% which gives a level of confidence on the results reported.

The design team from VNIITF accomplished much in the four months since the redesign of the Big Wheel structure was initiated at CERN. In no small way this positive result can be attributed to the fact that the team was physically located at CERN during this period. This provided them with the necessary support of CERN engineering and the ability to discuss and quickly solve design problems as they were discovered.

It is strongly recommended that this same working relationship, (with) the (design) team based at CERN, continue during the next phase of the engineering effort which will lead to the Final Design Review 2 (FDR2) tentatively scheduled for September 01."

MDT base chamber production continued on schedule at each production site. Of special note is the completion of the entire EML2 base chamber series (all 16 modules) at Seattle. This is a significant milestone and was achieved ahead of schedule. Both BMC and Michigan sites completed their Modules 15 on schedule. Preparations were started for the next chamber series at each site. For example, tube production was started for EIS1 - the next chamber series for the BMC. Retooling of the tube production setups at Michigan and Seattle was started. Wellenstein and his engineering staff (Brandeis) worked closely with Marin (Boston), Hurst and Haggerty (Harvard) to prepare the tooling for the EIS1 BMC series 2 tooling. And the chamber teams at Michigan (Zhou, et al.) and Seattle (Mocket, et al.) worked closely with Wellenstein et al. on their chamber tooling.

MDT parts procurement and mechanical engineering focused on the next chamber series production cycle. Fries (Harvard) continued to track the procurement of critical path items and was able to always supply the U.S. sites with enough tubes, endplugs and associated parts to keep the U.S. tube/chamber production on schedule. Wang and Daly (Seattle) finished all the assembly drawings for the spacer frames of the next 3 chamber series. Coco, Marzocchi (MIT) and Kelrikh (Harvard) worked on the gas, Faraday cage designs and chamber assembly drawings.

A critical MDT electronics milestone was achieved in May. The EIL1 module 0 was fully instrumented with electronics and studied with cosmic rays yielding 81-micron resolution (2 to 14 mm tube radius), 97% efficiency with a threshold set at 20 electrons. The work was performed by a collaboration of Harvard (Guimaraes, Oliver, Brandenburg, et al.), Boston (Ahlen, Ide, Sherman, Hazen) and Michigan (Chapman and team) and coordinated by Ahlen using the BMC cosmic setup. In addition, Chapman et al. continued to develop the MDT Chamber Service Module (CSM) into a less expensive and more efficient design.

Good progress was made on Detector Control System (DCS) at Seattle. Rothberg continued to develop the controls readout that uses PVASS - utilizing DIM connectivity protocol.

The CSC factory at BNL is ramping up for series production. Module 0 is complete. The QA rigs for cathode flatness and for wire tension are operational.

CSC electronics work concentrated on modifying the IC50 preamp/shaper design for improved yield and enhanced operation characteristics at BNL (O'Connor). The Sparsifier Processing Unit coding advanced at UC-Irvine (Stoker, Langford, et al.).

Effort continued on the alignment system at Brandeis (Bensinger, Hashemi et al.). Preparations for the next round of chamber production, the big wheel review, H8, responding to TC questions and developing the layout of the polar lines with the new big wheel location (moved back by 399 mm) were made. In addition work continued on the design of the multipoint system (BCAM), alignment bars, proximity monitors and inplane MDT monitors.

1.6 Subsystem Manager's Summary	Robert Blair (Argonne National Lab.)

This month's TDAQ activity included refining the Users Requirement Documents for various components of the TDAQ system in preparation for review at the July TDAQ workshop at CERN. The evaluation of Athena as a Level 2 framework has proceeded and initial performance measurements have been redone with improved results. Work on ROD/ROS and TTC readout has progressed.

# 5.  Open Items between DOE/NSF and U.S. ATLAS

- Financial: There is $3,377,000 of available funding residing in management reserve and $9,590,000 of undistributed budget pending approval and implementation of MOU documents.  Table7-2 contains the summary of FY01 funds distribution.  There was $4,255,000 requested in additional funding allocations during May.

- Schedule:  None.

- Technical:  None.

6.  Summary Assessment and Forecast

1.  Financial Status

A total of $96,288,000 (58.8%) was authorized, held in reserve or identified as undistributed budget of the $163.75M Total Project Cost Objective.  The details of the overall project cost objective are presented in Table 6-1 reproduced overleaf from the U.S. ATLAS Project Plan as approved on 3/18/98 and revised to include cost changes approved through BCP #46.

The details of the reported costs and reported obligations are presented in the Table 7-1 in Section 7 of this report. In addition Table7-2 shows the cost breakdown by institution and funding source.

The relationship between budget authority/cost/obligations (including an estimate of other accrued costs and obligations) is presented in Figure 9-1 in Section 9 of this report.

The level 2 CSSR statistics are presented in section 10.  Performance analysis is included for major subsystems in section 8 of this report.

2.  Schedule Status

See details in Figure 11-1.

The overall schedule status report is found in section 11.

The milestone log from the PMP, including revised forecast dates, is reproduced as section 12.

3.  Baseline Change Proposals

Forty-seven BCPs were received through May 2001.  Forty-four BCP’s were approved, two were withdrawn and one is pending approval.

Table 6-1 reflects all cost BCPs through 46.

Table 6-1:  Summary Cost Estimate

Figure 6-1 - Project System Network

Funding

Table 7.1 - Summary of Funds Authorized & Total Costs and Commitments to Date

Table 7.2 – FY01 Funds – U.S. ATLAS Summary by Institution and Subsystem

# 8.  Performance Analysis

Status through the month of May 2001 reflects the new baseline schedules for all subsystems. The re-baseline date was established on October 1, 2000 and the Estimate to Complete 01 (ETC 01) was defined as all tasks and resources required to complete the project. All prior efforts were equated to the actual costs expended. The schedules are resource loaded to the baseline funding of $163,750K with Contingency, Management Contingency, and Items Outside of the Approved Baseline shown on separate lines and excludes all NSF R&D funds.

The CSSR in section 10 shows $62,041.3k of the work has been performed, which represents approximately 49.2% of the work authorized to date. There is an unfavorable schedule variance of ($792.0k) or 1.3% behind the plan.  There is an unfavorable cost variance of ($123.8k) or 0.2% over spent for the work accomplished. There are outstanding commitments of $7,422.9k at this time that do not show up in the performance. This analysis will provide a breakdown of these variances into the individual subsystems and identify the specific tasks that cause these variances.

## WBS 1.1 Silicon

## Summary

The CSSR shows that $8,333.0k of the work has been completed which represents 46.9% of the total effort for the Silicon subsystem. There is an unfavorable schedule variance of ($271.2k) or 3.2% behind the plan and an unfavorable cost variance of ($61.1k) or 0.7% over spent for the work accomplished.  There are outstanding commitments of $90.4k at this time that do not show up in the performance.

## Schedule Variance

The unfavorable schedule variance is concentrated in the following WBS level 3 elements:

WBS 1.1.2 Silicon Strip System SV = ($45.5k)

- Hybrids/Cables/Fanouts are behind plan ($15.3k)

- Module Assembly and Test is behind plan ($30.2k)

WBS 1.1.3 RODs SV = ($225.7k)

- Design ROD Cards is behind plan ($16.9k)

- ROD Test Stand is behind plan ($63.5k)

- ROD Prototypes is behind plan ($51.2k)

- ROD Prototype Evaluation is behind plan ($12.6k)

- ROD Production Model is behind plan ($79.4k)

- ROD Fabrication is behind plan ($2.0k)

## Cost Variance

There is a unfavorable cost variance of ($61.1k) which is distributed as follows: Pixel ($238.6k), the Silicon Strip System $254.3k and the ROD Design and Fabrication ($76.7k).

# WBS 1.2 TRT

## Summary

The CSSR shows that $4,815.5k of the work has been completed which represents 52.4% of the total effort for the TRT subsystem. There is an unfavorable schedule variance of ($216.1k) or 4.3% behind the plan and a favorable cost variance of $12.3k or 0.3% under spent for the work accomplished. There are outstanding commitments of $1,077.1k at this time that do not show up in the performance.

## Schedule Variance

The unfavorable schedule variance is concentrated in the following WBS level 3 elements

WBS 1.2.1 Barrel Mechanics SV = ($211.1k)

- Detector Elements are behind plan ($23.5k)

- Component Assembly is behind plan ($81.9k)

- Module Assembly #2 (Duke) is behind plan ($44.1k)

- Module Assembly #1 (IU) is behind plan ($61.6k)

## WBS 1.3 LAr

## Summary

The CSSR shows that $19,595.4k of the work has been completed which represents 46.5% of the total effort for the LAr subsystem. There is an unfavorable schedule variance of ($110.8k) or 0.6% behind the plan and a favorable cost variance of $409.0k or 2.1% under spent for the work accomplished. There are outstanding commitments of $4,426.1k at this time that do not show up in the performance.

## Schedule Variance

The unfavorable schedule variance is concentrated in the following WBS level 3 elements:

1.3.7 Front End Board SV = ($1.3k)

1.3.10 Forward Calorimeter SV = ($93.2k)

- FCAL1 Module Production is behind plan ($36.4k)

- FCAL Electronics Design and Prototype are behind plan ($15.9k) and ($30.8k) respectively

- FCAL Production is behind plan ($10.0k)

## Cost Variance

# The favorable cost variance of $409.0k is a combination of positive and negative variances concentrated in the following WBS Level 3 elements.

- 131 Barrel Cryostat CV = $364.0k

- 132 Feedthroughs CV = $15.7k

- 133 Cryogenics CV = ($40.4k)

- 134 Readout Electrodes/MB CV = ($32.7k)

- 136 System Crate Integration CV = $1.6k

- 137 Front End Board CV = ($35.4k)

- 139 ROD System CV = $105.2k

- 1310 FCAL CV = $22.9k

## WBS 1.4 Tile

## Summary

The CSSR shows that $6,904.9k of the work has been completed which represents 75.5% of the total effort for the Tile subsystem. There is an unfavorable schedule variance of ($106.7k) or 1.5% behind the plan and a favorable cost variance of $7.1k or 0.1% under spent for the work accomplished. There are outstanding commitments of $131.3k at this time that do not show up in the performance.

## Cost Variance

# There is a favorable cost variance of $7.1k which is distributed as follows:

- 141 EB Mechanics ($44.0k)

- 142 EB Optics ($39.0k)

- 143 Readout $126.3k

- 144 ITC ($36.1k)

## WBS 1.5 Muon

## Summary

The CSSR shows that $11,589.6k of the work has been completed which represents 43.9% of the total effort for the Muon subsystem. There is an unfavorable schedule variance of ($50.4k) or 0.4% behind the plan and an unfavorable cost variance of ($432.0k) or 3.7% over spent for the work accomplished.  There are outstanding commitments of $1,698.0k at this time that do not show up in the performance.

## Schedule Variance

The unfavorable schedule variance is concentrated in the following WBS level 3 elements:

1.5.8 MDT Supports SV = ($31.3k)

- Chamber Mount Struts Design is behind plan ($13.5k)

- Integration with Support Structure Design is behind plan ($17.8k)

## Cost Variance

The unfavorable cost variance of ($432.0k) is a combination of positive and negative variances concentrated in the following WBS Level 3 elements.

- 154 CSC Chambers CV = ($221.3k)

- 157 MDT Chambers CV = ($90.7k)

- 158 MDT Supports CV =  ($23.1k)

- 159 MDT Electronics CV = $41.9k

- 1511 CSC Electronics CV = ($43.6k)

- 1512 Global Align System CV = ($95.2k)

## WBS 1.6 Trigger/DAQ

## Summary

The CSSR shows that $1,484.5k of the work has been completed which represents 47.6% of the total effort for the Trigger/DAQ subsystem. There is an unfavorable schedule variance of ($36.8k) or 2.4% behind the plan and an unfavorable cost variance of ($59.0k) or 4.0% over spent for the work accomplished.  There is an unfavorable cost variance of ($116.0k) for the Level 2 Supervisor but this is offset by a favorable cost variance of 71.4k for the Level 2 Calorimeter Trigger.  There are no outstanding commitments at this time.

# 9.  Budget Authority Costs and Obligations

# 10.  WBS – Cost Schedule Status Report

# Figure 11-1 - Milestone Schedule Status Report

# 12.  MILESTONE LOG

The milestones have been updated with the new ETC 01 baseline dates.

U.S. ATLAS Major Project Milestones (Level 1)

| Description | Baseline Schedule | Forecast (F) Date | Actual (A) Date |
| --- | --- | --- | --- |
| Project Start | 01-Oct-95 | 01-Oct-95 (F) | 01-Oct-95 (A) |
| Project Completion | 30-Sep-05 | 30-Sep-05 (F) |  |

U.S. ATLAS Major Project Milestones (Level 2)

| Subsystem | Schedule Designator | Description | Baseline Schedule | Forecast (F) / Actual (A) Date |
| --- | --- | --- | --- | --- |
| Silicon (1.1) | SIL L2/1 | Start Full Silicon Strip Electronics Production | 06-Jul-01 | 15-Jul-01 (F) |
|  | SIL L2/2 | Start Full Strip Module Production | 07-Jan-02 | 07-Jan-02 (F) |
|  | SIL L2/3 | ROD Design Complete | 01-Oct-01 | 01-Oct-01 (F) |
|  | SIL L2/4 | Complete Shipment of Silicon Strip Module Production | 13-Oct-03 | 13-Oct-03 (F) |
|  | SIL L2/5 | ROD Production/Testing Complete | 24-Jun-03 | 24-Jun-03 (F) |
|  | SIL L2/6 | Pixels 1st IBM Prototype Submitted | 26-Jul-01 | 26-Jul-01 (F) |
|  | SIL L2/7 | Pixels Start IBM Production | 13-Mar-03 | 13-Mar-03 (F) |
|  | SIL L2/8 | Pixels Start IBM Outer Bare Module Prod | 22-Oct-03 | 22-Oct-03 (F) |
|  | SIL L2/9 | Pixels Disk System at CERN | 13-Oct-04 | 13-Oct-04 (F) |
| TRT (1.2) |  |  |  |  |
| Mechanical | TRT L2/1 | Final Design Complete | 31-Dec-98 | 07-Dec-98 (A) |
|  | TRT L2/2 | Module Production Complete (CUM 102) | 31-Mar-03 | 31-Mar-03 (F) |
|  | TRT L2/3 | Barrel Construction Complete | 16-Sep-03 | 16-Sep-03 (F) |
| Electrical | TRT L2/4 | Select Final Elec Design | 15-Jun-01 | 30-Aug-00 (A) |
|  | TRT L2/5 | Start Production of ASICS | 18-Jan-02 | 18-Jan-02 (F) |
|  | TRT L2/6 | Installation Complete | 04-Jan-05 | 04-Jan-05 (F) |
| LAr Cal | LAr L2/1 | Cryostat Contract Award | 24-Jul-98 | 05-Aug-98 (A) |
| (1.3) | LAr L2/2 | Barrel Feedthroughs Final Design Review | 30-Sep-98 | 02-Oct-98 (A) |
|  | LAr L2/3 | Start Electronics Production (Preamps) | 30-Jun-00 | 30-Jun-00 (A) |
|  | LAr L2/4 | FCAL Mechanical Design Complete | 14-Dec-98 | 15-Dec-99 (A) |
|  | LAr L2/5 | FEB SCA Prod. Chip Submission/Contract Award | 19-Jul-01 | 01-Oct-01 (F) |
|  | LAr L2/6 | Level 1 Trigger Final Design Complete | 04-Oct-01 | 04-Oct-01 (F) |
|  | LAr L2/7 | ROD Final Design Complete | 12-Dec-02 | 12-Dec-02 (F) |
|  | LAr L2/8 | Motherboard System Production Complete | 30-Jun-02 | 30-Jun-02 (F) |
|  | LAr L2/9 | Cryostat Arrives at CERN | 15-May-01 | 02-Jul-01 (F) |
|  | LAr L2/10 | Barrel Feedthroughs Production Complete | 15-Feb-02 | 15-Feb-02 (F) |
|  | LAr L2/11 | FCAL-C Delivered to EC | 17-Oct-02 | 17-Oct-02 (F) |
|  | LAr L2/12 | FCAL-A Delivered to EC | 08-Dec-03 | 08-Dec-03 (F) |

U.S. ATLAS Major Project Milestones (Level 2) (Continued)

| Subsystem | Schedule Designator | Description | Baseline Schedule | Forecast (F) / Actual (A) Date |
| --- | --- | --- | --- | --- |
| Tile Cal | Tile L2/1 | Start Submodule Procurement | 01-Sep-97 | 01-Sep-97 (A) |
| (1.4) | Tile L2/2 | Technology Choice for F/E Electronics | 15-Nov-97 | 15-Nov-97 (A) |
|  | Tile L2/3 | Start Module Construction | 01-May-99 | 20-Sep-99 (A) |
|  | Tile L2/4 | Start Production of Motherboards | 01-Apr-01 | 30-Mar-01 (A) |
|  | Tile L2/5 | All Electronic Components Delivered to CERN | 01-Oct-02 | 01-Oct-02 (F) |
|  | Tile L2/6 | Module Construction Complete | 30-Sept-02 | 30-Sep-02 (F) |
|  | Tile L2/7 | All Modules Delivered to CERN | 02-Dec-02 | 02-Dec-02 (F) |
| Muon (1.5) | Muon L2/1 | Start MDT Chambers Lines 1 and 3 | 17-Jul-00 | 15-Sep-00 (A) |
|  | Muon L2/2 | Start CSC Chamber Production | 01-Sep-01 | 01-Sep-01 (F) |
|  | Muon L2/3 | MDT Electronics ASD PRR | 19-Oct-01 | 01-Oct-01 (F) |
|  | Muon L2/4 | Final Design of Global Alignment Devices Complete | 01-Apr-02 | 01-Apr-02 (F) |
|  | Muon L2/5 | CSC IC Production Complete | 15-May-02 | 15-May-02 (F) |
|  | Muon L2/6 | Kinematic Mount Design Complete | 30-Jan-01 | 30-Jan-01 (A) |
|  | Muon L2/7 | MDT Chambers (U.S.) Production Complete | 27-Aug-04 | 14-Sep-04 (F) |
|  | Muon L2/8 | Kinematic Mount Production Complete | 24-May-04 | 24-May-04 (F) |
|  | Muon L2/9 | CSC ROD Production Complete | 05-Nov-03 | 05-Nov-03 (F) |
|  | Muon L2/10 | MDT Elec.’s Mezzanine Production Complete | 06-Mar-03 | 06-Mar-03 (F) |
|  | Muon L2/11 | CSC Assembly/Testing at CERN Complete | 17-Dec-04 | 17-Dec-04 (F) |
|  | Muon L2/12 | Global Alignment System Final Delivery | 30-Sep-04 | 30-Sep-04 (F) |
| Trigger/ DAQ (1.6) | TDAQ L2/1 | Select Final LVL2 Architecture | 31-Dec-99 | 31-Mar-00 (A) |
|  | TDAQ L2/2 | LVL2 Trigger Design Complete | 31-Dec-02 | 31-Dec-02 (F) |
|  | TDAQ L2/3 | LVL2 Trigger Prototype Complete | 30-Sep-02 | 30-Sep-02 (F) |
|  | TDAQ L2/4 | Start Production | 08-Jan-03 | 08-Jan-03 (F) |
|  | TDAQ L2/5 | Start Installation & Commissioning | 05-Mar-03 | 05-Mar-03 (F) |
|  | TDAQ L2/6 | Production Complete | 30-Jul-05 | 30-Jul-05 (F) |
|  | TDAQ L2/7 | LVL2 Installation & Commissioning Complete | 30-Sep-05 | 30-Sep-05 (F) |

U.S. ATLAS Major Project Milestones (Level 4)

| WBS | Schedule Designator | U.S. ATLAS Responsibility Completion Description | ETC01 Baseline Scope Planned Completion Date | Forecast (F)/ Actual (A) Baseline Scope Completion Date | ATLAS Required Date | Baseline Scope Planned Float (Months) |
| --- | --- | --- | --- | --- | --- | --- |
| Silicon |  |  |  |  |  |  |
| 1.1.2 | Sil L4/1 | Complete Shipping of Silicon Strip Prod Modules | 10/03 | 10/03 | 4/03 | -6 |
| 1.1.3 | Sil L4/2 | RODs 45% Production Complete | 9/02 | 9/02 | 6/03 | 9 |
| 1.1.1 | Sil L4/3 | Pixels ‘Disk System at CERN’ | 10/04 | 10/04 | 12/04 | 2 |
| TRT |  |  |  |  |  |  |
| 1.2.1 | TRT L4/1 | Barrel Modules Ship to CERN Complete | 8/02 | 8/02 | 3/03 | 7 |
| 1.2.5 | TRT L4/2 | ASDBLRs Ship to LUND Complete | 10/02 | 10/02 | 11/02 | 1 |
|  | TRT L4/3 | ASDBLRs Ship to CERN Complete | 11/02 | 11/02 | 12/02 | 1 |
|  | TRT L4/4 | PCB-Endcaps Ship to CERN Complete | 4/03 | 4/03 | 10/03 | 6 |
| LAr |  |  |  |  |  |  |
| 1.3.1 | LAr L4/1 | Cryostat Final Acceptance Test Complete | 8/01 | 8/01 | 11/01 | 3 |
| 1.3.2 | LAr L4/2 | Signal FT Installation Complete | 11/02 | 11/02 | 10/02 | -1 |
|  | LAr L4/3 | HV FT End-Cap C Install Complete | 2/02 | 2/02 | 11/01 | -3 |
|  | LAr L4/4 | HV FT Barrel Install Complete | 11/01 | 11/01 | 5/02 | 6 |
|  | LAr L4/5 | HV FT End-Cap A Install Complete | 12/02 | 12/02 | 9/02 | -3 |
| 1.3.3 | LAr L4/6 | LAr Cryogenics Vendor Install Complete | 9/03 | 9/03 | 12/03 | 3 |
| 1.3.4.1 | LAr L4/7 | Last Del of Readout Electrodes | 12/02 | 12/02 | 10/02 | -2 |
| 1.3.4.2 | LAr L4/8 | MBs Ship to Annecy,Saclay (France) | 6/02 | 6/02 | 9/02 | 3 |
| 1.3.5.1 | LAr L4/9 | Preamp Deliveries to FEB Complete | 5/03 | 5/03 | 3/04 | 10 |
| 1.3.5.2 | LAr L4/10 | Prec Calor Calib Production Complete | N/A | N/A | N/A | N/A |

U.S. ATLAS Major Project Milestones (Level 4) (Continued)

| WBS | Schedule Designator | U.S. ATLAS Responsibility Completion Description | ETC01 Baseline Scope Planned Completion Date | Forecast (F)/ Actual (A) Baseline Scope Completion Date | ATLAS Required Date | Baseline Scope Planned Float (Months) |
| --- | --- | --- | --- | --- | --- | --- |
| Lar (Continued) |  |  |  |  |  |
| 1.3.6.1 | LAr L4/12 | Pedestal Ship to CERN Complete | 12/01 | 12/01 | 7/02 | 7 |
|  | LAr L4/13 | Barrel Ship to CERN Complete | 12/01 | 12/01 | 3/03 | 15 |
| 1.3.6.2 | LAr L4/14 | Cables Shipping Complete | 10/02 | 10/02 | 3/03 | 5 |
|  | LAr L4/15 | Baseplane Last Delivery to CERN Complete | 10/02 | 10/02 | 3/03 | 5 |
| 1.3.6.3 | LAr L4/16 | EC Crates Last Delivery to CERN Complete | 10/02 | 10/02 | 3/03 | 5 |
|  | LAr L4/17 | Barrel Crates Last Delivery to CERN Complete | 10/02 | 10/02 | 3/03 | 5 |
| 1.3.6.4 | LAr L4/18 | Controls Ship to CERN Complete | 9/03 | 9/03 | 5/04 | 8 |
|  | LAr L4/19 | Power Supplies Last Delivery Complete | 9/04 | 9/04 | 5/04 | -4 |
| 1.3.6.5 | LAr L4/21 | Thermal Contacts (Proto) Last Delivery Complete | 9/02 | 9/02 | 9/02 | 0 |
| 1.3.7.1 | LAr L4/22 | FEB Last Delivery Complete | 8/04 | 8/04 | 1/05 | 5 |
| 1.3.7.2 | LAr L4/23 | SCAs Last Delivery to FEB Complete | N/A | N/A | N/A | N/A |
| 1.3.7.4 | LAr L4/24 | Last Driver Delivery to FEB Complete | 4/04 | 4/04 | 5/04 | 1 |
| 1.3.8.1 | LAr L4/26 | Layer Sums Last Delivery to FEB Complete | 12/02 | 12/02 | 3/04 | 15 |
| 1.3.8.2 | LAr L4/27 | I/F to Level 1 Ship to CERN Complete | 8/04 | 8/04 | 12/04 | 4 |
| 1.3.9 | LAr L4/28 | ROD System Final Prototype Complete | 8/02 | 8/02 | 8/02 | 0 |
| 1.3.10 | LAr L4/29 | Deliver Finished FCAL-C to EC | 10/02 | 10/02 | 10/02 | 0 |
|  | LAr L4/30 | Deliver Finished FCAL-A to EC | 12/03 | 12/03 | 11/03 | -1 |
|  | LAr L4/31 | FCAL Elec.'s Summ Bds Ready for Installation | 12/01 | 12/01 | 2/02 | 2 |
|  | LAr L4/32 | FCAL Elec.'s Cold Cables Testing Complete | 11/01 | 11/01 | 2/02 | 3 |

U.S. ATLAS Major Project Milestones (Level 4) (Continued)

| WBS | Schedule Designator | U.S. ATLAS Responsibility Completion Description | ETC01 Baseline Scope Planned Completion Date | Forecast (F)/ Actual (A) Baseline Scope Completion Date | ATLAS Required Date | Baseline Scope Planned Float (Months) |
| --- | --- | --- | --- | --- | --- | --- |
| Tile |  |  |  |  |  |  |
| 1.4.1 | Tile L4/1 | Submodules Production Complete | 7/01 | 7/01 | 8/01 | 1 |
|  | Tile L4/2 | EB Module Ship to CERN Complete | 12/01 | 12/01 | 7/02 | 7 |
| 1.4.2 | Tile L4/3 | Optics Instrumentation at ANL & MSU Complete | 9/02 | 9/02 | 11/02 | 2 |
| 1.4.3 | Tile L4/4 | PMT Ship to ATLAS Complete | 1/02 | 1/02 | 7/02 | 6 |
| 1.4.3 | Tile L4/5 | Readout Ship to ATLAS Complete | 6/02 | 6/02 | 9/02 | 3 |
| 1.4.4 | Tile L4/6 | Gap Submodules Ship to ANL & BCN Complete | 7/01 | 7/01 | 8/01 | 1 |
| Muon |  |  |  |  |  |  |
| 1.5.7 (1) | Muon L4/1 | MDT Chamber Prod Complete (BMC Qty. 80) | 6/04 | 6/04 | 2/04 | -4 |
|  |  | MDT Chamber Prod Complete (Mich Qty. 80) | 8/04 | 8/04 | 2/04 | -6 |
|  |  | MDT Chamber Prod Complete (Seattle Qty. 80) | 8/04 | 8/04 | 2/04 | -6 |
| 1.5.8 (2) | Muon L4/2 | MDT Mounts Prod Complete/Delivered to Chambers | 10/03 | 10/03 | 2/04 | 4 |
| 1.5.9 (3) | Muon L4/3 | MDT Elec.'s Mezzanine Bd Production Complete | 3/03 | 3/03 | 2/03 | -1 |
|  | Muon L4/4 | MDT Elec.'s Hedgehog Production Complete | 12/01 | 12/01 | 4/01 | -8 |
| 1.5.4 | Muon L4/5 | CSC Chambers Production Complete | 1/03 | 1/03 | 4/04 | 15 |
| 1.5.11 (5) | Muon L4/6 | ASMs Production Complete | 4/04 | 4/04 | 4/04 | 0 |
|  | Muon L4/7 | Sparsifiers Ship to CERN | 3/04 | 3/04 | 10/04 | 7 |
|  | Muon L4/8 | RODs Ship to CERN | 3/04 | 3/04 | 10/04 | 7 |
|  | Muon L4/9 | Support Electronics Ship to CERN | 3/04 | 3/04 | 10/04 | 7 |
| 1.5.12 (6) | Muon L4/10 | Align Bars Ship to CERN | 3/04 | 3/04 | 12/04 | 9 |
|  | Muon L4/11 | Proximity Monitors Ship to CERN | 12/03 | 12/03 | 12/04 | 12 |
|  | Muon L4/12 | Multi-Point System Ship to CERN | 3/03 | 3/03 | 3/05 | 24 |
|  | Muon L4/13 | DAQ Ship to CERN | 9/04 | 9/04 | 12/04 | 3 |

# 13.  NSF cost schedule status Report

Fourteen US ATLAS institutions will receive funding under the NSF Cooperative Agreement (No. PHY 9722537) in FY01. Technical progress reports are given in the respective subsystem paragraphs of Section 4. The NSF Cost Schedule Status Report (CSSR) in this section covers these 14 institutions, in addition to the Education, Institutional Dues and Common Project items which will be funded by the NSF, and also the Items Outside Approved Baseline and Contingency.

Status through the month of May 2001 reflects the new baseline schedules for all subsystems.  The schedules are resource-loaded to the baseline funding of $163,750K with Contingency, Management Contingency and Items Outside of the Approved Baseline shown on separate lines, excluding all NSF R&D funds.  The anticipated NSF contribution to the baseline funding is $60,800K

We note that more than half of the universities in the NSF CSSR are, or have been, funded by both NSF and DOE, while we manage the project without distinguishing the agency source of funding. For this reason, the NSF+DOE Budgeted AY$s column in Table 13-1 includes all Project funds allocated to each institution, while the last two columns to the far right show the contribution of each agency.

The re-baseline date was established as October 1 2000 and the FY 01 Estimate to Complete (ETC-01) was defined as all tasks and resources required too complete the project.   These tasks were scheduled and the necessary resources were loaded into the schedules.  All prior efforts were equated to the actual cost expended.  There was a negative schedule variance along with a positive cost variance in the old baseline and this resulted in a reduction in both the work scheduled and the work performed in the new baseline.

The CSSR shows that $22,184.2K of the work has been completed which represents approximately 39.0% of the work authorized to date.  There is an unfavorable schedule variance of $279.1 or 1.2% behind the plan and a favorable cost variance of $134.0K or 0.6% under spent for the work accomplished.  There are outstanding commitments of $897.8k at this time that do not show up in the performance.

Schedule Variance

Hampton – SV = ($81.9k)

WBS 1.2.1.1.3 Barrel Module Component Assembly is behind plan $81.9k

University of Chicago – SV = ($94.3k)

WBS 1.4.3.3.3 Front End Mother Board Production is behind plan $89.7k

Cost Variance

Although the overall cost variance for NSF Institutions is a favorable $134.0k it is comprised of both positive and negative variances as follows:

- Brandeis – CV = ($132.3k)

- Overspent on tooling ($39.8k)

- Charging against Global System Production tasks ($92.7k)

- Nevis – CV = ($46.8K)

- Over spent on the FEB

- MSU CV = ($81.7K)

- Over spent on Trigger/DAQ Level 2 SRB

- SUNY Stony Brook CV = ($51.7K)

- Over spent on the HV Feedthrough Production

- University of Rochester CV = $508.4K

- Under spent by $349.8k on Vendor Manufacturing but shows an outstanding commitment of $317.8k

- Under spent by $161.4k on Manufacturing Monitoring

- University of Texas Arlington CV = ($109.6K)

- Over spent by $47.8k on the Intermediate Tile Calorimeter Production

- Reported $60k of prior year cost

- University of Chicago CV = $90.8

- Under spent by $117.7k on Readout

- Overspent by $33k Extended Barrel Module

- University of Washington CV = ($35.5K)

### Table 13

# 14.  detailed Technical progress

1.1 SILICON

Milestones with changed forecast dates:

| 1.1.1.3.1 Design |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| FE-I1 spec complete | 16-May-01 | 16-May-01 | 16-Jul-01 | Delayed (See #1) |
| Note #1 Specification has been started, and was supposed to be ready for June review. Testing of Analog Test chip has taken priority |

| 1.1.1.3.2 Development/Prototypes |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| FE-D3 submitted | 2-May-01 | 2-May-01 | 2-Dec-01 | Delayed (See #1) |
| Note #1 We have delayed all further work on FE-D3 pending submission of FE-I1 and study of its performance. At the present time, no further DMILL submissions are foreseen unless significant problems are observed with 0.25( designs |

| 1.1.2.1.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Complete preproduction fab | 28-Feb-01 | 30-May-01 | 30-Jun-01 | Delayed (See #1) |
| Complete preproduction design verification | 23-May-01 | 23-May-01 | 30-Jun-01 | Delayed (See #2) |
| Note #1 The last of the 5 pre-production lots was delivered with one out of spec fab parameter. We gave Atmel a conditional waiver in that we said we would first test the wafers and then determine to accept them only if the out of spec parameter did not effect yield or performance. Atmel has also delivered some extra wafers to augment the last lots which did yield poorly. We have not tested all the wafers and therefore have not accepted the last lot. The remaining wafers should be tested by end of June so that we can complete acceptance. Note #2 We are still studying one post-rad problem. Progress has been made in understanding the problem but it is not complete. This must be done before the PRR on 4-Jul. |

| 1.1.2.2.1 Design |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Start Procurement for Production Hybrid Assembly | 5-Mar-01 | 25-May-01 | 15-Jun-01 | Delayed (See #1) |
| Note #1 The FDR was completed but some minor modifications have been circulated since. |

| 1.1.2.2.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| 1st Preproduction Hybrids Avail for Mod Assy | 4-Jun-01 | 1-Sep-01 | 15-Sep-01 | Delayed (See #1) |
| Compl Preproduction Assy | 13-Aug-01 | 13-Oct-01 | 21-Oct-01 | Delayed (See #2) |
| Compl Testing of Preprod Hybrid | 3-Sep-01 | 3-Sep-01 | 21-Oct-01 | Delayed (See #3) |
| Note #1 This will follow the hybrid design review and is set by Japanese procurement schedule. The FDR is complete but some minor mods have been circulated. Note #2-3 Set by date of item1 above. |

| 1.1.2.3.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Complete Preproduction Module Testing | 3-Sep-01 | 3-Sep-01 | 30-Oct-01 | Delayed (See #1) |
| Note #1 See note 1. |

| 1.1.3.4.3 SCT/Pixel Test Stand Software |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Production Diagnostic Test Stand Completed | 29-Sep-00 | 29-Jul-01 | 29-Aug-01 | Delayed (See #1) |
| Note #1 The test stand software is complete. It will not be verified as production test stand until the first card has been debugged and tested. This was expected in 2000 but the date now selected for completion is August 29, 2001. This is caused by the slow progress in testing the ROD. Recently much testing of software has been performed. With the working ROD infrastructure, the testing of the software can proceed at its own pace. The software is 80% complete. Completion will be done when the first ROD is full completed. The completion of the software is waiting on the production models of the ROD. Sufficient time after debugging of the ROD is projected into August. This will be in time for the production of the ROD. |

| 1.1.3.7.3 Evaluation of Production Model |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Release Production Dwg/Specs | 16-May-01 | 16-Jun-01 | 25-Jul-01 | Delayed (See #1) |
| Pixel ROD Design complete | 14-Jun-01 | 14-Jul-01 | 1-Aug-01 | Delayed (See #2) |
| Note #1 The current progress show that the drawing will not be ready till June. This was caused by the extended time required to debug the proto ROD. Production is not expected to slip. Note #2 The code for the pixel specific part is written and simulated. The one-month delay is expected to have little impact. The delay of 2 months is expected to have little impact. |

1.1.1 Pixels 	Murdock Gilchriese (Lawrence Berkeley Lab.)

1.1.1.1 Mechanics

Preparations for a Conceptual Design Review of all of the pixel mechanics and a PRR for the local supports is proceeding on schedule. In general, we are on or ahead of schedule with two possible exceptions. One, delivery of carbon-carbon plates to our specifications may be delayed as the result of vendor fabrication problems. We will know if there will be a delay by mid-June. Two, the design requirements for the pixel support tube (PST) are partly driven by overall ATLAS and beam pipe installation requirements. These have only recently been frozen, so there may be some delay in completing the PST design. It will take until July to understand if there will be a delay or not.

1.1.1.2 Sensors

The test results on the CIS preproduction sensors continue to look good. The second vendor, Tesla, claims to now understand their yield problems and additional preproduction wafers should arrive soon for testing.

1.1.1.3 Electronics

A third generation DMILL prototype of the opto-ICs was submitted in May.

First test results of the analog test chip (ATC) for the front-end IC are promising. Some minor errors were found in this chip and understood. A more significant problem, excessive threshold dispersion, appears to also have an explanation. The first irradiation of the ATC to about 60 MRad showed essentially no change in performance - very encouraging. The layout and verification of the complete FE chip is progressing, but it's very likely there will be at least a one-month delay in submission. Layout revisions will likely be necessary to fix the threshold problem, and final layout and verification is proceeding somewhat more slowly than planned.

Fabrication of the first parts for the new test system were completed in May. Additional parts are still in design and layout.

1.1.1.4 Hybrids

The submission of the 3rd generation flex hybrid will be delayed for two reasons. First, two designs were found to be required, one compatible with existing AMS MCC chips (v.3) and one with the 0.25 micron MCC to be included in the IBM engineering run. Second, CERN, which was to be the first vendor for these, has recently informed us they no longer can support this work until the fall of 2001 because of lack of personnel. The plan is to submit v.3 first to Compunetics, one of the vendors for the v.2 flex.

Work on the optical hybrids is proceeding as scheduled. A selection between the OSU and Taiwan optical packages will be made in the second week of June.

Albany is reporting for the first time this month. They are now working on QC (HV testing and other) of the flex hybrids using fixtures made at LBNL and at Albany.

1.1.1.5 Modules

The "dummy module" program continues with advancements made in wire bonding and mounting these dummies on disk sectors.

The 8" dummy wafers made in the US have been rejected because of poor nitride passivation. We are attempting to determine how to get the vendor to improve the passivation step, but this is a major delay in qualifying bump bonding vendors to handle 8" wafers.

1.1.1.1 Mechanics

1.1.1.1.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Cables/services CDR | 20-Jun-01 | -- | 11-Jul-01 | Delayed (See #1) |
| Disk Sector PRR | 20-Jun-01 | -- | 12-Jul-01 | Delayed (See #2) |
| Global Support CDR | 20-Jun-01 | -- | 11-Jul-01 | Delayed (See #3) |
| Support tube CDR | 20-Jun-01 | -- | 11-Jul-01 | Delayed (See #4) |
| Global Support FDR | 16-Oct-01 | -- | 16-Oct-01 | On Schedule |

Note #1-4  Unable to arrange reviewers with TC on original date.

Pixel Support Tube	Eric Anderssen (Lawrence Berkeley Lab.)

Interface to SCT Barrel was presented for approval to the ID engineers, and the detail design of the supports for the Pixel Support Tube (PST) were developed and discussed. Designs for support blocks and flexures were proposed and analysis results presented. Flexures are proposed in place of sliding contact joints for reliability and predictable forces. Design of the PST barrel flange details (bolt patterns, web-reinforcement, thickness) was completed based on preliminary manufacturing plan (needed for composite parts).

Interface Drawing to SCT was presented with new support condition implemented. FEA analysis with this support condition has been the baseline for all PST development since end of April, and requests to SCT to analyze the ramifications of this support condition were incorporated into FEA analysis of the SCT Barrel structure, results of which were made available at end of May.

PST support and interface to the SCT remain subject to approval, but tentative agreement was reached to continue in these directions for the CDR in July.

Disk Sectors	Murdock Gilchriese (Lawrence Berkeley Lab.)

The detailed design of tooling for fabrication of the disk sectors is continuing. The preparation of documents for the Local Support PRR also continues.

Disk Support Rings

The design of the tooling needed to fabricate the disk support rings has started. The current design now includes a close connection with the disk sector construction. The proposal is to create a master gauge

tool that fixes the location of the three support points for the disk sector. Mistress gauges would be used to both fabricate the disk sectors so that the support points are always located in the same position. A similar mistress gauge would be used to transfer the location of the three support points, in groups, to the graphite tooling used to fabricate the disk support ring. The intent is to allow any sector to be placed on any disk support ring, in any location.

Global Support Frame

Work on the FE analysis of the global support is continuing. This is going slowly, and is limited by obtaining updated information on the correct weights of components, services, etc.

Sally Seidel (University Of New Mexico)

Several iterations of the connector selection and layout on PP2 were performed. At the LBNL mechanics meeting, several options A1 and A2 for the optimization of Type II cables were proposed, and an option B was presented which moved PP2 outside the first layer of the muon chamber and increased the dimensions to 450 mm x 450 mm x 150 mm. Iterations of the PP2 connector layout were performed for option B; these included placing four cables per connector (total of 11 connectors) and two cables per connector (total of 25 connectors). The one connector per cable (total of 50 connectors) design is presently in progress at New Mexico.

1.1.1.1.2 Development/Prototypes

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete sector development | 20-Jun-01 | -- | 20-Jun-01 | On Schedule |
| Complete disk development | 16-Oct-01 | -- | 16-Oct-01 | On Schedule |
| Complete global support development/prototypes | 16-Oct-01 | -- | 16-Oct-01 | On Schedule |

INSTALLATION MOCKUP	Neal Hartman (Lawrence Berkeley Lab.)

Work on the mockup is being suspended until a study of sliding materials for the detector and service panels can be completed. The study will evaluate different plastics (yet to be identified) in actual contact with a carbon fiber/cyanate ester laminate. Once this study is completed, a slider design will be fabricated and tested in the mockup.

COOLING SERVICES

The cold testing He leak checker setup has been tested at low temperature, and it has been found that -22 Celsius can easily be reached. Warm up time is up to an hour, however, so forced warming may need to be used in order to cycle samples through at a higher rate. Several samples have been tested so far at low temperature.

One of four variseals has been successfully leak checked through the entire regimen (including cold and irradiation). One sample failed initially (on first fitup) and should have been re-clamped in order to retest,

but this was never done. The two other samples failed during pressurized leak checking, and never made it to cold testing. One of the failures passed, however, after being pressure cycled once. Four more variseal samples are being made in order to add to this data set.

The taper seal fittings (similar to Luer-Lok) did not fare well during pressure testing, with one of three surviving the test. This poor behavior may be due to surface finish, so new seals are being fabricated.

The indium seal fittings also did not fare well. One fitting of three failed during pressure testing, while one could never be made to seal (for the initial vac check). The third fitting fared well. These failures are thought to be due to the fact that the seals were not initially designed for indium, but were adapted from other fittings. In order to fairly test an indium joint, a new set of fittings are being made.

Four "dumbbell" laser welded samples were received and visually look good. The fabricator tested them to low 7 scale, and retesting upon receipt confirmed this result to better than mid 10 scale. The laser welded samples have yet to be tested with variseals in them.

It was decided to suspend all brazing work for the time being. The brazed dumbbell samples have fared well (all of them passing initial leak and proof tests) but laser welding is much more desirable (due mostly to the small heat affected zone) and appears to be feasible based on initial samples and quotes, so all effort will be devoted to this solution.

Disk Sectors and Staves	Murdock Gilchriese (Lawrence Berkeley Lab.)

The fabrication of the three prototype disk sectors to the current dimensions is complete. One of these uses the baseline thermal compound (used in the previous ten prototypes) to couple the aluminum tube in the sector to the faceplates. The other two prototypes use a rigid epoxy. Testing of the prototypes will begin in June.

Testing of a stave prototype continued. The stave underwent 50 thermal cycles from room temperature to -35F. The thermal performance was not affected. LN2 vapor was used to quickly cool the stave to -40C(thermal shock). The thermal performance was not affected. A similar test was done first on an older sector prototype with no changes in thermal performance. A stave and sector were both cooled when powered by LN2 vapor. This may be an effective way of doing cold QC tests on individual staves and sectors when real modules are mounted.

Disk Support Rings and Global Support Frame

The Disk Support Rings are supported by mounts in the Global Support Frame. These mounts are located in holes drilled in the Global Support Frame after its fabrication. Bushings are glued into the Support Frame using precision tooling. This tooling is also used to locate the Support Ring. We are trying this procedure with the second prototype Support Ring and the prototype of the Support Frame. A set of holes was drilled and the bushings glued into the frame at the end of May. Testing will occur in June.

1.1.1.1.3 Production 	Murdock Gilchriese (Lawrence Berkeley Lab.)

Disk Sector and Support Ring

Chemical vapor deposition of the carbon-carbon plates for disk sectors and the disk support ring was completed. There were some problems found by the vendor. The plates were cut into two pieces - a circular cutout and the remainder. This was required by the subcontractor providing the furnace time for the CVD to allow temperature measurements to be made. The plates before CVD were all less than 0.018" thick. The circular cutout after CVD was 0.021-0.025" thick. The outer section was about 0.021" thick. These are larger than expected, as is the variation. The next step in the process is heat treatment. The vendor is concerned that he will not meet our specifications and may have to cut the plates, sand the pieces, re-CVD and re-heat treat. The heat treatment will be completed by mid-June. We will inspect the material at this time to determine if some of it meets spec or if additional steps will be necessary. The vendor is producing much more material than we need, so it's possible enough will be produced to our specifications.

1.1.1.2 Sensors

1.1.1.2.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Compl. Spec for production order release | 12-Mar-01 | -- | 16-Jun-01 | See Note #1 |
| ATLAS PM approval of production procurement | 23-Jul-01 | -- | 23-Jul-01 | On Schedule |
| Release initial MC for sensors/testing | 23-Jul-01 | -- | 23-Jul-01 | On Schedule |

Note #1  Tests of pre-production wafers are continuing. As the sensor schedule is ahead of the schedules of other components and consequently not on the critical path, this is not expected to impact the global schedule.

1.1.1.2.2 Development/Prototypes 	Sally Seidel (University Of New Mexico)

Acceptance tests of the pre-production wafers are continuing. At New Mexico, the CV measurements on the six single chip structures have now been completed. QA tests 7, 8, and 9 have been completed for all 13 wafers. These are, respectively, the IV on the oxide test structure, the CV on the oxide test structure, and the IVgate on the GCD. The wafers continue to look good. Cross calibration measurements have been performed on wafer 4455-08 including QA procedures 3, 4, 5, and 6. Work is underway at all the probing institutes to adapt the Dortmund double-sided probing chucks to use in their own facilities.

1.1.1.3 Electronics

1.1.1.3.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FE-I1 spec complete | 16-May-01 | 16-May-01 | 16-Jul-01 | Delayed (See #1) |
| FE-I1 FDR | 13-Jun-01 | -- | 13-Jun-01 | On Schedule |

Note #1  Specification has been started, and was supposed to be ready for June review. Testing of Analog Test chip has taken priority

Murdock Gilchriese (Lawrence Berkeley Lab.)

This report was prepared by K. K. Gan. We have completed the layout for the 3rd DMILL prototype of the optical dice, DORIC-D3 and VDC-D3. There are two improvements in the DORIC: the RC time constant in the feedback circuit for canceling the pre-amp offset has been increased to 20 us so that the die can handle larger offset. In addition, the feedback is now connected directly into the input of the pre-amp via a 1 MOhm resistor.

The input coupling capacitor has been increased from 4 pF to 20 pF. This design is much simpler than the IBM design submitted in February and can handle pre-amp offset of up to 50 mV, even at corner transistor parameters. The design was submitted near the end of May and we expect to receive the dice in October.

Kevin Einsweiler (Lawrence Berkeley Lab.)

We are still awaiting the return of bump-bonded FE-D2S assemblies from IZM and AMS for further characterization. They are now expected to return during the month of June. In our Feb meeting with ATMEL, they promised to process a new lot, using our FE-D2 masks, in which they would divide the lot between wafers in which the top epitaxial layer was deposited by their present US vendor, and wafers in which this layer was deposited by a second German vendor. Preliminary evidence from other designs indicated a significant yield improvement, and they suggested exploring this for pixels. We will receive 10 wafers in LBL, and probe them during the coming month.

We continue to place all of our design resources on the deep-submicron design effort. We have received our TSMC Analog Test chip, submitted in March. We have rapidly commissioned our new test system for this chip. This system uses a PCMCIA I/O register to control the digital lines on the chip, and a LabWindows program to support basic operations such as DAC characterization, threshold scans, TOT scans, and timewalk scans. Within about one week, we had the system and the chips working.

It appears that there are only three relatively minor problems with the chip. The first is that the output pads were all inverting. The second is that the readback function for the pixel control bits does not work. Further simulation indicates that this is related to the risetime of the load signals used during readback, and that if they were slowed slightly, this function would work. The third problem was a power bus sizing error for the DAC supplies (these DACs each consume a standing current of 255uA), which causes some systematic shifts in the currents delivered to the pixels.

We have carried out a detailed analog characterization of the chip. The current reference works well, and the DACs are very linear (0.3LSB differential linearity). The front-end performance can be monitored in several ways. There is a multiplexed fast buffer which can display the preamp waveform, or the two sides of the second stage waveform, for a special test pixel. It has a test input for calibration purposes. Second, there is a direct discriminator output from one pixel. Finally, there is our usual FastOR readout, in which a programmable set of pixels OR their discriminator outputs together for analysis. This latter signal is used to drive all of our threshold, TOT, and timewalk scans.

The front-end waveforms look almost identical to those in simulation. The noise is roughly what was expected. The noise of an unloaded pixel is about 160-180e. There are programmable capacitive loads in the test chip to allow adding load in 100fF increments. Our nominal design load is 400fF, at which point the noise is about 300e. Our initial noise measurements are relatively sensitive to environmental effects, which were not always fully controlled during these measurements. Injection of leakage current does not alter the preamp waveform shape or baseline (unlike previous designs, where most TOT information was lost after leakage injection). The noise increase for a 50nA leakage (this is the design value, we expect only 30nA at end of lifetime) is roughly what is expected, giving about 400e total noise.

We immediately noticed that the threshold dispersion is extremely large for this front-end. There are only 20 pixels in each test chip, so in order to gain statistics, we have averaged the results from threshold scans on 5 different chips. This gives a very large dispersion of over 2000e, about 5 times larger than our design goal. Some of this comes from dispersion between chips, but most seems to arise directly on one chip. We have examined the design in some detail to understand this effect, but we have only had the chips for a bit more than 2 weeks, so this analysis is very preliminary. It appears that the threshold dispersion of the design is quite sensitive to the matching of a number of transistors in weak inversion. By taking measured VT matching numbers as a function of transistor size from RD-49 work at CERN, we can estimate the effects. A first analysis suggests that perhaps as much as 1500e of the threshold dispersion could be explained by this mechanism. Further studies are needed, but we intend to modify the front-end layout and significantly increase the size of those transistors which are most critical for matching (some of which are quite small). This should allow us to reduce the matching errors by about a factor of 2. Stay tuned for further updates…

We were fortunate enough to get two short dedicated runs scheduled at the 88" Cyclotron for irradiations. The first of this was in late May, and we irradiated a single TSMC test chip to 61 MRad. The chip was operated continuously during the irradiation, and the current reference, DAC performance, and front-end noise and threshold were monitored. There were no major changes observed in the chip performance, despite the fact that towards the end of the irradiation, we were providing a dose of about 15MRad/hour. The current reference was observed to increase by about 10%, but due to the way in which the reference is used by the DACs, the change in DAC scale was only a few percent. There were no systematic changes in the front-end noise performance. There were some modest threshold shifts, but the threshold dispersion remained essentially unchanged. Further lab characterization was performed on the irradiated chip, and we observed that the trim DAC performance was unchanged, as well as the timewalk performance. This is the first time that we have observed our acceptable pre-rad performance persist under the expected lifetime doses for ATLAS pixels!

There is a special current mirror inside the preamp that allows us to directly measure the feedback current in each pixel (as well as the leakage current). We have used this node to characterize the feedback current dispersion between pixels, and to extract the feedback capacitance by examining the dV/dt for the preamp return to baseline. The feedback current dispersion is only about 15% between pixels, which is quite acceptable. We have also checked the values for the injection capacitors, and they also agree roughly with our extracted values. We have characterized the new two new 5-bit trim DACs that are placed in each pixel, and find them to have reasonable performance.

Meanwhile, work is continuing on all aspects of the complete FE-I chip. We are preparing for a 2-day review at CERN in early June. This, plus our test chip evaluation effort, have slowed down the main activity somewhat. The integration of the chip is progressing well, but more slowly than expected. The analog integration has not progressed much in the last month, but it is almost complete. We have decided to integrate significant "smart" decoupling into the column pairs, in order to better manage the power distribution in the chip (we are very worried about the large transient currents that are generated in the 0.25u process when the large annular NMOS switch). These capacitors have a "test" mode in which they check for low resistance across the capacitor, and if it is found, automatically disconnect the capacitor from ground so that no current flows. Each capacitor is about 1.5pF, and fits in about 30x40u of area, conveniently inside a pixel. The digital integration has been going smoothly. The layout of the column pair and the EOC buffers and their related logic is now complete. Extensive simulations are starting using TimeMill (an accelerated timing and power simulator that works from SPICE netlists and BSIM models, which being several orders of magnitude faster than SPICE), and Verilog. We intend to use TimeMill at the column pair level as our timing simulation, cross-checked on smaller netlists using ELDO SPICE. We are using Verilog for the overall functional verification, and have developed some simple code to check for the operation of all of the registers, etc.

In summary, very significant progress has been made towards a submission of the complete pixel array to IBM this summer. However, we are beginning to believe that we will submit in August, missing our July milestone date by one month.

In order to exercise the next generation of chips from ATMEL and IBM to the fullest extent possible, and in particular to develop the capability to label chips as "known good die", and be sure that this classification will remain true after exposure to the full radiation doses of ATLAS, we are developing an improved test system.

We received the first PLL boards, and loaded two of them this month. One has been undergoing preliminary testing. We have not been able to devote much effort to this because of the higher priority given to the 0.25u work. However, basic checking of the module has taken place. The power and clock distribution are working, and the VME interface is working. Further checking, which involves the real VHDL in the module, is just starting.

We are now working on putting the final finishing touches on the PICT schematics. We will need to make some minor modifications to cope with what appears to be the final pinout for the FE chip. We plan to have a full schematic review at the end of June. This will use other experts in the engineering group at LBL, some of whom have worked on the similar SCT test system. We have begun board layout. The layout of this mixed-signal board will be somewhat challenging, and could easily take a month. With our present complement of 1 FTE of engineering working on this design, it is progressing, but significantly more slowly than initially expected. However, we anticipate that it will be fully operational in our labs by Sept, when it is required for testing the returning FE-I wafers.

1.1.1.3.2 Development/Prototypes

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FE-D3 submitted | 2-May-01 | 2-May-01 | 2-Dec-01 | Delayed (See #1) |
| Analog test chip delivered | 11-May-01 | -- | 11-May-01 | Completed |
| 1st IBM prototype submitted (FE-I1) | 26-Jul-01 | -- | 26-Jul-01 | Delayed (See #2) |
| FE-D3 wafers arrive | 22-Aug-01 | -- | 22-Aug-01 | Delayed (See #3) |
| 1st IBM prototype delivered | 24-Oct-01 | -- | 24-Oct-01 | Delayed (See #4) |

Note #1, 3  We have delayed all further work on FE-D3 pending submission of FE-I1 and study of its performance. At the present time, no further DMILL submissions are foreseen unless significant problems are observed with 0.25u designs

Note #2, 4  Testing of the Analog Test chip has revealed large threshold dispersion. This must be improved before full submission. Other accumulated delays suggest a one-month delay in the submission date.

1.1.1.4 Flex Hybrids/Optical Hybrids

1.1.1.4.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Optical package decision | 15-Jun-01 | -- | 15-Jun-01 | On Schedule |

Flex Hybrids – University of Oklahoma	Rusty Boyd (University of Oklahoma)

The design and layout for the version 3 flex hybrid is behind schedule. It became apparent when the layout was about 80% complete that the idea of an AMS and DSM MCC compatible layout would lead to neither a final MCC pad layout nor a final flex hybrid layout. Thus, it was decided to design separate AMS and DSM layouts in order to keep the flex hybrid PRR on schedule for June 2002. At the end of May, we were still considering various pad layouts for the DSM MCC. This has been a complicated issue, as we need to keep a layout that is essentially compatible with the AMS MCC in order to prevent the need to redesign and fabricate circuit boards, jigs, probe cards, etc. used for MCC testing and also meet the layout requirements of the flex hybrid.

The AMS compatible flex is now designated v3 and the DSM version is v4. The layout of these two versions only differ by the routing of the MCC and the extra components (about 13) required by the AMS MCC. Therefore, the routing for v3 is about 90% compatible with v4, which allows a quick migration of the design from the AMS version the DSM version. In addition, v4 should be very near to the final layout. It is anticipated that v3 should be completed by the end of June and v4 by mid-July, as two weeks will be spent traveling to Bonn, Genova and CERN in June.

1.1.1.4.2 Development/Prototypes 	Murdock Gilchriese (Lawrence Berkeley Lab.)

This report was prepared by K. K. Gan. The new opto-packs designed for the pixel detector have been fabricated. 31 single VCSEL opto-packs have been produced. The VCSEL was placed using a new technique. In the old method, the precision VCSEL placement was done using a jig. In this jig, there is a slot for the base plus a pocket for the VCSEL. There are three contributions to the VCSEL placement precision: the slight oversize of the slot and pocket and the relative location of the pocket with respect to the slot. These uncertainties yield opto-packs of limited quality: 12 out of the 18 packages fabricated satisfy the minimum coupled power requirement of 300 uW. In the new procedure, the location of the pin on the cap mold is precisely measured so that the VCSEL is placed precisely at the location where we expect the fiber. All 31 bases fabricated have coupled power significantly above the specification. In addition, the caps are interchangeable: a cap was tested on all the 31 bases and all yield power significantly above the specification. This demonstrates that the cap is reusable. Two 3-PIN opto-packs were fabricated and both have responsivity ~25% above the spec. A review panel will choose between the OSU design and Taiwan design in June. The new opto-board designed to use the pixel opto-packed has been submitted and we expect the delivery in early June.

This report was prepared by S. Alam and F. Wappler.

Conducted tests on three AFHs (not populated):

2.2-4, 2.2-5, and 2.2-10.

(1) Tests of Conductivity (Opens & Shorts of Bus, Power, and FE-to-MCC Traces)

Defects were only found on 2.2-4, where four traces were non-conducting (FE0 to MCC, FE2 to MCC, two data traces at FE2); five corresponding wirebond pads appeared grey/non-reflective (gold coating covered or removed).

(2) Tests for Pinholes and HV Breaks (with Probe-to-AlFoil Setup, and with LBNL HV Test Fixture)

An initial visual inspection was inconclusive. No defects were found with the Probe-to-AlFoil technique up to 1050V. With the HV Fixture, breakdowns occurred in all three AFHs;

2.2-5 at 450V, 2.2-4 and 2.2-10 at 550V.

Those breakdowns occurred during initial tests, while we were learning to operate the HV Fixture; in particular without being completely certain that the metallic ring around the survey hole was perfectly aligned with the hole in the rubber layer of the HV Fixture. Only subsequently we drilled a hole through one side of the HV Fixture to better observe the alignment, and we cut approx. 2mm of one rubber band side to ensure the rubber bands being completely separated by an aligned AFH. The breakdowns remained observable at 50V to 350V, subject to moderate pressure applied to the fixture.

Renewed visual inspection of the backside showed pinholes/burnmarks through the bottom layer underneath the MCC pad (about two, in each of the three tested AFHs), and an entire burned/blackened corner under the MCC pad of 2.2-4.

Subsequent Probe-to-AlFoil tests showed breakdowns when connecting to the corresponding pads (at 150V - 250V through the bottom metal layer under the MCC, and at 650V through the top metal layer under the MCC), and still no breakdown up to 1050V connecting to other metal traces via corresponding pads.

Meeting at Genova on 06-09-01, Rusty Boyd inspected those three AFHs under a microscope as well (apparently the performance of this particular bottom cover layer type was not entirely surprising).

Various pictures of the setup can be found at http://charm.phy.albany.edu/flex/flex_pics.html

Flex Hybrids - UOK	Rusty Boyd (University of Oklahoma)

The CERN PCB shop will be unable to fabricate v3 or v4 flex before the fall of 2001 because of a personnel shortage there, due to attrition. The original plan was to have the CERN PCB shop fabricate v3, but now they will be made by Compunetics. They estimate that they can fabricate the flex circuits in about three weeks after receipt of the drawings. The relaxed flex design rules have resulted in a 1/3 reduction in cost of fabrication by Compunetics.

Fifteen CERN v2.2 flex hybrids have been assembled at Mipot in Italy, including mounting and wire bonding of the MCC. Only five of these are defect free, with 6 having defective MCC's. Although the MCC's were believed to be good when shipped to Mipot, they were tested several years ago. The application of thin Kapton tape over the traces in the area of the test tab where no cover layer is present prevented disintegration of the traces there during component loading this time. At least two others have shorts due to Au bridges between traces. Although the flex circuits are tested, it is done before Au plating in order to repair defects in the Cu etching.

It has also been discovered that the cover layer on these flex circuits is 60 microns thick instead of the 25 microns specified. In addition, the cover layer has many defects, including holes that cause initial breakdown at 500 V or less (see the Albany section of this report for details). Visual inspection reveals several defects in each flex which appear to be bubbles in the Pyralux.

1.1.1.5 Modules

1.1.1.5.2 Development/Prototypes 	Maurice Garcia-Sciveres (Lawrence Berkeley Lab.)

LBL Module Assembly Status Report for May 30, 2001

Dummy-Dummy modules

No noticeable change in wirebond pull strength was seen after 24 hours in C3F8. Three modules have been loaded on a sector using "production" tooling and CGL. Measurements in progress before loading remaining 3 modules on other side. No thermal cycling yet. No dummy pigtails have been added yet.

Dummy Modules

Wirebonding on 3 dummy modules assembled with CERN V2 Flex is of "production quality". One of the modules was bonded with zero misbonds in full auto mode. Wirebond pull strength is consistent and high (average around 8 grams).

Hot Modules

A second Flex V2 hot module has been assembled and wirebonded using Compunetics flex and an Alenia module. Electrical tests have not yet been performed due to priority for testing 0.25um test chip.

HV holdoff tests of flex HV test fixture has been sent to Albany and further tests are in progress there.

Dummy wafers

The 6 wafers sent to Bonn were closely inspected by Ogumundur and by Norbert, and all of them have been rejected as having too many defects in the nitride passivation to proceed with bump deposition. It seems at this point that the only way to recover any of the 25 wafers is to remove the nitride passivation and re-coat. The vendor (Process Specialties) is investigating the feasibility of removal of the nitride without damage to the metal and oxide below. An injury has been sent to IZM for possible alternatives to using thick low stress nitride (no response yet). Deposition of thick low stress nitride on 8" wafers is not a widely available capability, and the path to improving the results without going to another passivation is not clear at this point. Using a different passivation would be the fastest way to recover the 8" dummy wafers.

Wafer Thinning

Removal of the glass "handle" wafer from the thinned test wafers was problematic even after attaching with photoresist a second handle wafer to the back of the thinned wafer. The problem is that the UV-release tape adheres too strongly to the resist-coated surface of the bumped wafer.

A second attempt is being made where the UV-release tape is pre-exposed on most of its area, thus making a much weaker bond to the wafer being thinned (but still strong enough for the grinding process).

1.1.2 Silicon Strip System 	Abe Seiden (University Of Calif. At Santa Cruz)

This past month the Barrel Modules had a final design review. The review was very successful and "the most significant recommendation the reviewers could give to the SCT team is to go into production as fast as possible."

During May Carl Haber spent a significant amount of time at RAL to go over the software which runs the module fabrication. This software has not been functioning in a sufficiently smooth fashion at the LBNL production site.

In the area of front-end chips, preparation continued for the July 4th PRR. The tester at UCSC is running well and several wafers have been tested both in the U.S. and at CERN allowing detailed comparisons. The software to be used in analyzing the test results is still not sufficiently transparent, although we are slowly beginning to be able to do analyses in the U.S. Issues to be worked on in the coming month include this software, settling on the final set of test vectors to be used, and a choice of the number of repetitions of measurements to allow sufficient statistics to pin down the gain, noise and offset without requiring excessive test time.

1.1.2.1 IC Electronics

1.1.2.1.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Production Readiness Review (PRR) | 15-Jun-01 | -- | 4-Jul-01 | Delayed (See #1) |

Note #1  The PRR has been delayed until 4-Jul to further understand one last post-rad problem we are having with some chips. SCT is moving forward with the PRR on this date. Preparations are underway.

Alexander A. Grillo (University Of Calif. At Santa Cruz)

LBNL & UCSC

The wafer tester operated smoothly all month. The hardware is operating without problems and the "online" programs seem to be stable for the time being although we know some enhancements must be made before full production starts. We have tested 5 reference wafers at UCSC, which were already tested on the new tester at CERN and the old original tester at CERN. The problem now is getting the analysis software working so that we can analyze the test results and check the correlation of the various testers. This has been frustrating this month. It has been an ongoing struggle to get adequate software support from our European collaborators. The original software developer is trying to help but it is clear this is not his primary job. The CERN person who has most recently been working on the software is also solely responsible for testing wafers at CERN and coordinating material movement and inventory there. We are working towards getting more control of the software here in California but this is going slowly.

RAL has made good progress with their tester. It appears to be functional and ready to test the reference wafers. They will be shipped from UCSC to RAL as soon as we have some first analysis of the UCSC test data indicating that re-test is not necessary.

Progress finding a solution to the lack of room for services continues to be a problem. The ATLAS EB made a final decision to increase the GAP by 40mm giving 32mm to the ID for extra services space and giving 8mm to TC for contingency. This was done in spite of the fact that the ID management, including the ID Project Engineer, did not agree with this decision and stated clearly that they could not guarantee that a solution was possible in the available space. The bottom line was that the ID was told to find their own solution within the new parameters. The SCT may be left with a choice between building something, which is mechanically unreliable or electrically unreliable.

1.1.2.1.2 Development/Prototypes

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Test Systems Complete | 3-Aug-01 | -- | 3-Aug-01 | On Schedule |

LBNL & UCSC 	Alexander A. Grillo (University Of Calif. At Santa Cruz)

In spite of the fact that we have not completed the analysis of the reference wafers on the new tester at UCSC, we have started to test new untested wafers from the April delivery. These are from the 4-way split of new epitaxy sub-contractor and a thinner oxide layer. Both are experiments that Atmel believes may improve the yield. If the wafers from the new epitaxy sub-contractor do show markedly improved yield, they will launch a program to qualify the new sub-contractor for production. That could happen as early as November or December of this year.

1.1.2.1.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete preproduction fab | 28-Feb-01 | 30-May-01 | 30-Jun-01 | Delayed (See #1) |
| Complete preproduction design verification | 23-May-01 | 23-May-01 | 30-Jun-01 | Delayed (See #2) |
| Release/Start Full Electronics Production | 6-Jul-01 | -- | 15-Jul-01 | Delayed (See #3) |

Note #1  The last of the 5 pre-production lots was delivered with one out of spec fab parameter. We gave Atmel a conditional waiver in that we said we would first test the wafers and then determine to accept them only if the out of spec parameter did not effect yield or performance. Atmel has also delivered some extra wafers to augment the last lots which did yield poorly. We have not tested all the wafers and therefore have not accepted the last lot. The remaining wafers should be tested by end of June so that we can complete acceptance.

Note #2  We are still studying one post-rad problem. Progress has been made in understanding the problem but it is not complete. This must be done before the PRR on 4-Jul.

Note #3  See note on delay of PRR to 4-Jul. If the PRR on 4-Jul is passed, we should start production by mid-July.

LBNL & UCSC	Alexander A. Grillo (University Of Calif. At Santa Cruz)

The decision was made at the SCT Steering Group meeting to go forward with the ABCD Production Readiness Review on 4-July. The goal will be to issue the first production release order for 520 wafers as soon as possible after that date. Atmel has started fabricating approximately 75 wafers even without our release but in anticipation of a successful PRR in July. Those wafers will be ready for delivery as soon as we can issue the order. The first large batch of 200 wafers will then be delivered in late November or early December. Preparations are now in full swing for the PRR.

1.1.2.2 Hybrids/Cables/Fanouts

1.1.2.2.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Procurement for Production Hybrid Assembly | 5-Mar-01 | 25-May-01 | 15-Jun-01 | Delayed (See #1) |
| Hybrid/Module Final Design Review | 16-Apr-01 | -- | 25-May-01 | Completed |
| Release Hybrid Bids | 30-Apr-01 | -- | 15-Jun-01 | Delayed (See #2) |
| Hybrid Bid Evaluation Complete | 11-Jun-01 | -- | 15-Jul-01 | Delayed (See #3) |
| ATLAS PM Approval of Maj Procs | 20-Aug-01 | -- | 20-Aug-01 | On Schedule |
| Hybrid/Module Production Readiness Review | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |
| Complete Award Hybrid Contracts | 14-Sep-01 | -- | 14-Sep-01 | On Schedule |

Note #1  The FDR was completed but some minor modifications have been circulated since.

Note #2-3  Not a US responsibility.

Carl Haber (Lawrence Berkeley Lab.)

This is no longer a US responsibility. An FDR was held this month and the hybrid design was accepted. The Japanese group sent afterwards a list of minor design modifications which are currently under review.

1.1.2.2.2 Development & Prototype Fabrication 	Carl Haber (Lawrence Berkeley Lab.)

The hybrid-folding fixture was inspected. An additional assembly step is pending and will be completed in June. A set of dummy hybrids is being fabricated for assembly test purposes.

The temperature cycling test setup is still underway.

1.1.2.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 1st Preproduction Hybrids Avail for Mod Assy | 4-Jun-01 | 1-Sep-01 | 15-Sep-01 | Delayed (See #1) |
| Compl Preproduction Assy | 13-Aug-01 | 13-Oct-01 | 21-Oct-01 | Delayed (See #2) |
| Compl Testing of Preprod Hybrid | 3-Sep-01 | 3-Sep-01 | 21-Oct-01 | Delayed (See #3) |

Note #1  This will follow the hybrid design review and is set by Japanese procurement schedule. The FDR is complete but some minor mods have been circulated.

Note #2-3  Set by date of item 1 above.

1.1.2.3 Module Assembly and Test

1.1.2.3.1 Design of Assembly & Test Tooling

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Module FDR | 16-Apr-01 | -- | 25-May-01 | Completed |
| Compl Design of Preprod Mod Assy/Test | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |
| Module PRR | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |

Carl Haber (Lawrence Berkeley Lab.)

A visit was made to RAL this month. A number of aspects of the assembly design were discussed. Additional drawings were obtained of the metrology plate and the RAL hybrid-folding fixture. The folding fixture seems too complex. We expect to either further develop ours or design a new simpler one for us in the US.

1.1.2.3.2 Development & Prototypes

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Compl Assy of Proto Modules | 5-Mar-01 | -- | 23-May-01 | Completed (See #1) |
| Compl Test/Measure Proto Modules | 16-Apr-01 | -- | 23-May-01 | Completed (See #2) |

Note #1  Shift due to shift of module fdr and difficulty commissioning UK fixtures and code. The FDR occurred and was passed. All modules now are considered pre-production. Due to difficulties and evolution of UK code and fixtures work continues partly on components from the prototyping phase but all is in support of pre-production effort now.

Note #2  Shift due to shift of module fdr and difficulty commissioning UK fixtures and code. Same comments as Note #1 applies.

Carl Haber (Lawrence Berkeley Lab.)

Hardware was installed for Z motion. Currently this is controlled by a separate box, but we will commission LabView code to run this in the near future. A new manual focus wait routine was added to the LV system.

A visit was made to RAL. Problems with image processing and acquisition were discussed and resolved during the visit. With some suggested mods we expect our system will work properly now. Various other aspects of the code and calibration process where covered as well.

Discussions were held at RAL concerning the commissioning of the new assembly stages. An additional set of mods is now required to align these stages properly.

An FDR of the baseboard design was held at CERN and the design was accepted. Concern still remains about flatness and the nature of the precision alignment holes. One recommendation was the SCT project engineer’s study these issues further.

Discussions were held at RAL concerning the metrology process using the Smart Scope. A set of tests to try on our system was identified.

Used probe station vendors were contacted and visited so that a station can be procured for use in the module detector probing. The RAL system was examined during the site visit there. An appropriate current measuring instrument was identified and will be ordered. A new computer was installed for these measurements.

Murdock Gilchriese (Lawrence Berkeley Lab.)

Work continued on dummy module parts. Tooling for making dummy hybrid assemblies was completed and one dummy hybrid made. Dummy detectors were processed in the UC Berkeley Microlab.

1.1.2.3.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Preproduction Module Assembly | 30-Jul-01 | -- | 30-Oct-01 | Delayed (See #1) |
| Complete Preproduction Module Testing | 3-Sep-01 | 3-Sep-01 | 30-Oct-01 | Delayed (See #2) |

Note #1-2  Requires pre-production hybrids which won't be available until the end of summer.

1.1.3 ROD Design & Fabrication 	Dick Jared (Lawrence Berkeley Lab.)

The data path through the ROD has been tested. The data flow is correct. This is a major step in the debugging of the ROD. System testing at Cambridge has been scheduled and tickets purchased. The test will start June 23, 2001. This testing will include the ROD, ROD Test Stand Software, TIM, BOC and RCC (the complete system). Minor corrections are being made to the ROD formatter, event fragment builder and router. These corrects are relatively simple and present no concerns. The controller all though functional has some problems that will require rewriting of the code that generates the event ID and dynamic mask. The current version supports data flow testing but is not optimal. The code rewriting is expected to be completed before the start of the Cambridge system test.

1.1.3.4 ROD Test Stand

1.1.3.4.3 SCT/Pixel Test Stand Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Production Diagnostic Test Stand Completed | 29-Sep-00 | 29-Jul-01 | 29-Aug-01 | Delayed (See #1) |

Note #1  The test stand software is complete. It will not be verified as production test stand until the first card has been debugged and tested. This was expected in 2000 but the date now selected for completion is August 29, 2001.  This is caused by the slow progress in testing the ROD. Recently much testing of software has been performed. With the working ROD infrastructure, the testing of the software can proceed at its own pace. The software is 80% complete. Completion will be done when the first ROD is full completed. The completion of the software is waiting on the production models of the ROD. Sufficient time after debugging of the ROD is projected into August. This will be in time for the production of the ROD.

1.1.3.6 ROD Prototype Evaluation

1.1.3.6.1 SCT Prototype Testing

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT Complete ROD Proto Testing | 7-Jun-01 | -- | 7-Jun-01 | On Schedule |

1.1.3.6.3 User Evaluation of ROD in Europe

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT ATLAS Final Design Review | 11-Jun-01 | -- | 11-Aug-01 | Delayed (See #1) |
| SCT ROD User Evaluation Complete | 1-Oct-01 | -- | 1-Oct-01 | On Schedule |

Note #1  The delay is partially due to progress and the ROD. Availability of the review personnel has caused the date to be projected for August.

1.1.3.7 ROD Production Model

1.1.3.7.1 Updating of ROD to production Model

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT ATLAS ROD PRR | 1-Oct-01 | -- | 1-Oct-01 | On Schedule |

1.1.3.7.3 Evaluation of Production Model

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Production Procurements | 13-Apr-01 | -- | 13-Jul-01 | Delayed (See #1) |
| Release Production Dwg/Specs | 16-May-01 | 16-Jun-01 | 25-Jul-01 | Delayed (See #2) |
| Pixel ROD Design complete | 14-Jun-01 | 14-Jul-01 | 1-Aug-01 | Delayed (See #3) |
| Release Production Bids | 4-Jul-01 | -- | 4-Jul-01 | On Schedule |
| Bid Evaluation Complete | 15-Aug-01 | -- | 15-Aug-01 | On Schedule |

Note #1  The procurement should wait for the final design review in July. The change in the parts market due to low demand should allow the parts to be available on time.

Note #2  The current progress show that the drawing will not be ready till June. This was caused by the extended time required to debug the proto ROD. Production is not expected to slip.

Note #3  The code for the pixel specific part is written and simulated. The one-month delay is expected to have little impact. The delay of 2 months is expected to have little impact.

1.1.3.8 ROD Fabrication

1.1.3.8.1 ROD 5% Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Project Managers Approval 5% Production | 1-Oct-01 | -- | 1-Oct-01 | On Schedule |

1.2 TRT

Milestones with changed forecast dates:

| 1.2.1.1.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Module Assy #1 IU Module Assy CUM #4 Complete | 28-Feb-01 | 28-May-01 | 28-Jul-01 | Delayed (See #1) |
| Shells (Module #3) CUM #9 Available | 28-Feb-01 | 28-May-01 | 28-Jun-01 | Delayed (See #2) |
| Module Assy #1 IU Module Assy CUM #5 Complete | 30-Mar-01 | 30-May-01 | 30-Jun-01 | Delayed (See #3) |
| HV Plates (Module #1) CUM #12 Available | 30-Mar-01 | 30-May-01 | 30-Jul-01 | Delayed (See #4) |
| HV Plates (Module #2) CUM #12 Available | 30-Mar-01 | 30-May-01 | 30-Jul-01 | Delayed (See #5) |
| HV Plates (Module #3) CUM #9 Available | 30-Mar-01 | 30-May-01 | 30-Sep-01 | Delayed (See #6) |
| Shells (Module #2) CUM #15 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #7) |
| Shells (Module #3) CUM #12 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #8) |
| Shells (Module #1) CUM #16 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #9) |
| CUM #32 Kit Available | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #10) |
| CUM #9 Test Complete | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #11) |
| HV Plates (Module #1) CUM #16 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #12) |
| HV Plates (Module #2) CUM #15 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #13) |
| Module Assy #1 IU Module Assy CUM #9 Complete | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #14) |
| Module Assy #2 Duke Module Assy CUM #9 Complete | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #15) |
| Module Assy #3 Duke & IU Module Assy CUM #4 Complete | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #16) |
| CUM #16,000 Available from Hampton | 31-May-01 | 31-May-01 | 1-Jun-01 | Delayed (See #17) |
| Note #1, 10-17 Held up due to production pause. Note #2 Vision has started an accelerated production. We expect to catch up soon, but this has not been a hold up. Note #3 Slow down do to production pause. Note #4 HV plates are not available for kits. Note #5-6 In production, but not here yet. Note #7-9 Shells are keeping up with production but are delayed WRT schedule. |

| 1.2.1.2.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Production Management Contingency Go-Ahead | 2-Jul-01 | 2-Jul-01 | 2-Oct-01 | Delayed (See #1) |
| Note #1 Next meeting will be in October. |

| 1.2.1.3 Installation |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Installation Management Contingency Go-Ahead | 2-Jul-01 | 2-Jul-01 | 2-Oct-01 | Delayed (See #1) |
| Note #1 Next meeting will be in October. |

1.2.1 Barrel Mechanics

1.2.1.1 Barrel Module 	Ken McFarlane (Hampton University)

See details in sub-categories.

Harold Ogren (Indiana University)

Design work continues on the space frame and the module assembly tooling. This is being done in collaboration with CERN and Protvino. We are also working on the Module services envelope and the cooling plates.

1.2.1.1.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| HV Plates (Module #3) CUM #3 Available | 31-Jan-01 | -- | 30-Jun-01 | Delayed (See #1) |
| CUM #18 Kit Available | 28-Feb-01 | -- | 1-Jun-01 | Delayed (See #2) |
| HV Plates (Module #1) CUM #8 Available | 28-Feb-01 | -- | 28-Jun-01 | Delayed (See #3) |
| HV Plates (Module #2) CUM #8 Available | 28-Feb-01 | -- | 28-Jun-01 | Delayed (See #4) |
| HV Plates (Module #3) CUM #5 Available | 28-Feb-01 | -- | 28-Jun-01 | Delayed (See #5) |
| Module Assy #1 IU Module Assy CUM #4 Complete | 28-Feb-01 | 28-May-01 | 28-Jul-01 | Delayed (See #6) |
| Shells (Module #3) CUM #9 Available | 28-Feb-01 | 28-May-01 | 28-Jun-01 | Delayed (See #7) |
| CUM #12,000 Available from Hampton | 30-Mar-01 | -- | 30-Jun-01 | Delayed (See #8) |
| CUM #18,743 Available from CERN | 30-Mar-01 | -- | 30-May-01 | Completed |
| HV Plates (Module #1) CUM #12 Available | 30-Mar-01 | 30-May-01 | 30-Jul-01 | Delayed (See #9) |
| HV Plates (Module #2) CUM #12 Available | 30-Mar-01 | 30-May-01 | 30-Jul-01 | Delayed (See #10) |
| HV Plates (Module #3) CUM #9 Available | 30-Mar-01 | 30-May-01 | 30-Sep-01 | Delayed (See #11) |
| Module Assy #1 IU Module Assy CUM #5 Complete | 30-Mar-01 | 30-May-01 | 30-Jun-01 | Delayed (See #12) |
| Module Assy #3 Duke & IU Module Assy CUM #2 Complete | 30-Mar-01 | -- | 30-Jun-01 | Delayed (See #13) |
| Shells (Module #1) CUM #12 Available | 30-Mar-01 | -- | 30-May-01 | Completed |
| CUM #14,097 Available from Hampton | 30-Apr-01 | -- | 30-Jul-01 | Delayed (See #14) |
| CUM #27 Kit Available | 30-Apr-01 | -- | 30-Sep-01 | Delayed (See #15) |
| CUM #5 Test Complete | 30-Apr-01 | -- | 30-Sep-01 | Delayed (See #16) |
| HV Plates (Module #1) CUM #14 Available | 30-Apr-01 | -- | 30-Jul-01 | Delayed (See #17) |
| HV Plates (Module #2) CUM #14 Available | 30-Apr-01 | -- | 30-Jul-01 | Delayed (See #18) |
| HV Plates (Module #3) CUM #11 Available | 30-Apr-01 | -- | 30-Sep-01 | Delayed (See #19) |
| Module Assy #1 IU Module Assy CUM #7 Complete | 30-Apr-01 | -- | 30-Jun-01 | Delayed (See #20) |
| Module Assy #3 Duke & IU Module Assy CUM #3 Complete | 30-Apr-01 | -- | 30-Sep-01 | Delayed (See #21) |
| CUM #16,000 Available from Hampton | 31-May-01 | 31-May-01 | 1-Jun-01 | Delayed (See #22) |
| CUM #2343 Available from CERN | 31-May-01 | -- | 31-May-01 | Completed |
| CUM #32 Kit Available | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #23) |
| CUM #9 Test Complete | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #24) |
| HV Plates (Module #1) CUM #16 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #25) |
| HV Plates (Module #2) CUM #15 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #26) |
| HV Plates (Module #3) CUM #12 Available | 31-May-01 | -- | 31-Jul-01 | Delayed (See #27) |
| Module Assy #1 IU Module Assy CUM #9 Complete | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #28) |
| Module Assy #2 Duke Module Assy CUM #9 Complete | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #29) |
| Module Assy #3 Duke & IU Module Assy CUM #4 Complete | 31-May-01 | 31-May-01 | 1-Sep-01 | Delayed (See #30) |
| Shells (Module #1) CUM #16 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #31) |
| Shells (Module #2) CUM #15 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #32) |
| Shells (Module #3) CUM #12 Available | 31-May-01 | 31-May-01 | 31-Jul-01 | Delayed (See #33) |
| Wire Joints -1 CUM #28 (600/m) Available | 31-May-01 | -- | 31-May-01 | Completed |
| Wire Joints -2 CUM #11 (200/m) Available | 31-May-01 | -- | 31-May-01 | Completed |
| Wire Joints -2 CUM #13 (200/m) Available | 28-Jun-01 | -- | 28-Jun-01 | On Schedule |
| CUM #37 Kit Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| HV Plates (Module #1) CUM #17 Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| HV Plates (Module #2) CUM #17 Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| HV Plates (Module #3) CUM #13 Available | 29-Jun-01 | -- | 29-Jul-01 | Delayed (See #34) |
| Module Assy #1 IU Module Assy CUM #11 Complete | 29-Jun-01 | -- | 29-Jun-01 | On Schedule (See #35) |
| Module Assy #2 Duke Module Assy CUM #11 Complete | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| Module Assy #3 Duke & IU Module Assy CUM #6 Complete | 29-Jun-01 | -- | 29-Sep-01 | Delayed (See #36) |
| Shells (Module #1) CUM #17 Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| Shells (Module #2) CUM #17 Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| Shells (Module #3) CUM #13 Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| Wire Joints -1 CUM #32 (600/m) Available | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |
| CUM #18,200 Available from Hampton | 30-Jun-01 | -- | 30-Jun-01 | On Schedule |
| CUM #25,643 Available from CERN | 30-Jun-01 | -- | 30-Jun-01 | On Schedule |
| Mangement Contingency Go-Ahead | 2-Jul-01 | -- | 2-Jul-01 | On Schedule |
| CUM #20,665 Available from Hampton | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| CUM #27,943 Available from CERN | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| CUM #42 Kit Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| HV Plates (Module #1) CUM #18 Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| HV Plates (Module #2) CUM #18 Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| HV Plates (Module #3) CUM #14 Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Module Assy #1 IU Module Assy CUM #13 Complete | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Module Assy #2 Duke Module Assy CUM #13 Complete | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Module Assy #3 Duke & IU Module Assy CUM #8 Complete | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Shells (Module #1) CUM #18 Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Shells (Module #2) CUM #18 Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Shells (Module #3) CUM #14 Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Wire Joints -1 CUM #36 (600/m) Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| Wire Joints -2 CUM #15 (200/m) Available | 31-Jul-01 | -- | 31-Jul-01 | On Schedule |
| CUM #1 Kit Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| CUM #23,000 Available from Hampton | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| CUM #30,243 Available from CERN | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| CUM #48 Kit Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| HV Plates (Module #1) CUM #20 Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| HV Plates (Module #2) CUM #19 Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| HV Plates (Module #3) CUM #15 Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Module Assy #1 IU Module Assy CUM #15 Complete | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Module Assy #2 Duke Module Assy CUM #15 Complete | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Module Assy #3 Duke & IU Module Assy CUM #10 Complete | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Shells (Module #1) CUM #20 Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Shells (Module #2) CUM #19 Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Shells (Module #3) CUM #15 Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Wire Joints -1 CUM #40 (600/m) Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| Wire Joints -2 CUM #17 (200/m) Available | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |
| CUM #25,400 Available from Hampton | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| CUM #32,543 Available from CERN | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| CUM #54 Kit Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| HV Plates (Module #1) CUM #21 Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| HV Plates (Module #2) CUM #21 Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| HV Plates (Module #3) CUM #16 Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |

| Module Assy #1 IU Module Assy CUM #17 Complete | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| --- | --- | --- | --- | --- |
| Module Assy #2 Duke Module Assy CUM #17 Complete | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Module Assy #3 Duke & IU Module Assy CUM #12 Complete | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Shells (Module #1) CUM #21 Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Shells (Module #2) CUM #21 Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Shells (Module #3) CUM #16 Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Wire Joints -1 CUM #44 (600/m) Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Wire Joints -2 CUM #19 (200/m) Available | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| CUM #25 Test Complete | 30-Sep-01 | -- | 31-May-02 | Delayed (See #37) |
| Production Modules A Testing Complete | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |
| Shells (Module #3) CUM #10 Available | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |
| CUM #27,800 Available from Hampton | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| CUM #31 Test Complete | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| CUM #34,843 Available from CERN | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| CUM #60 Kit Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| HV Plates (Module #1) CUM #22 Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| HV Plates (Module #2) CUM #22 Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| HV Plates (Module #3) CUM #17 Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Module Assy #1 IU Module Assy CUM #19 Complete | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Module Assy #2 Duke Module Assy CUM #19 Complete | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Module Assy #3 Duke & IU Module Assy CUM #14 Complete | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Modules Production A Complete | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Shells (Module #1) CUM #22 Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Shells (Module #2) CUM #22 Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Shells (Module #3) CUM #17 Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Wire Joints -1 CUM #48 (600/m) Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |
| Wire Joints -2 CUM #21 (200/m) Available | 31-Oct-01 | -- | 31-Oct-01 | On Schedule |

Note #1  HV plate type 3, has been delayed. We now have new plates being manufactured.

Note #2-5, 21, 34, 36  Waiting on HV plates.

Note #6  Held up due to production pause.

Note #7  Vision has started an accelerated production. We expect to catch up soon, but this has not been a hold up.

Note #8  Hampton is now back in production and should fill this quota in April.

Note #9  HV plates are not available for kits.

Note #10-11  In production, but not here yet.

Note #12  Slow down due to production pause.

Note #13  Awaiting HV plate for type 3.

Note #14  Delayed due to late shipment and production pause.

Note #15  Successful shipment from Dubna.

Note #16  Testing at Hampton still not operational.

Note #17-18  American Circuits working on backlog of approved plates.

Note #19  HV plate 3 are delayed due to machining problems.

Note #20  Delayed due to late HV plate and production pause.

Note #22-26, 28-30  Delayed due to pause.

Note #27  Delayed due to HV 3 plates.

Note #31-33  Shells are keeping up with production but are delayed wrt schedule.

Note #35  Delayed due to pause and parts

Note #37  This appears to be out of sequence.

Ken McFarlane (Hampton University)

1.2.1.1.3 Production

Staff

No change; we now have a total of 5 technicians (including the QA tech, who does not do assembly work).

1.2.1.1.3.1 Detector Elements

1.2.1.1.3.1.1 Straws

Straws were received from JINR-Dubna (4,900).

1.2.1.1.3.1.1.2 End sockets (end plugs)

1.2.1.1.3.1.1.4.1 Twister

1.2.1.1.3.1.1.4.2 Twister

1.2.1.1.3.1.1.8.2 Wire bushing (eyelet)

1.2.1.1.3.1.1.8.3 Crimp pin (taper pin)

1.2.1.1.3.1.1.8.5, 6 Gas connections

All purchase orders or contracts for the above components have been placed, and deliveries are on schedule.

1.2.1.1.3.4 Assembly

Straw subassemblies

2,546 straw subassemblies were completed, 1,253 shipped, leaving 2,638 in inventory.

Radiator packs

Two type-1, and one type-2, radiator pack kits were produced this month.

Dividers

Three divider kits were produced.

Wire supports

No outer wire supports were assembled this month. 1,094 were shipped, leaving none in inventory.

Capacitor Barrels

These are now produced as needed for tension-plate processing. Reports on these will be discontinued.

Tension plates

These are now processed as needed to create HV plate/TP kits. Reports on these will be discontinued.

HV plate testing and assembly with tension plates

Three HV plate/TP kits were produced (Two type-1, one type-2).

HV Plates	Seog Oh (Duke University)

We have received several new sets of Type III plates and they were measured at FNAL. The measurement showed that all non-mirrored plates met the specification while all mirrored plates were not. We have talked with the vendor and we do not understand the reason. We are investigating. Meanwhile the good HV plates for Type I and Type II were sent to American Circuit for the final assembly. We should have ~10 good sets of plates for each type within a couple of weeks.

Module Construction

Module 2.06

The module has gone through the final HV and leak test and meets both specs. This is ready for the x-ray scan.

Module 2.07

This module has also gone through the final HV and leak test. The leak rate is somewhat worse than the previous modules but still meets the specification. This is also ready for the x-ray scan.

Module 2.08

We have just started the module.

Module 2.09

We are waiting for the components.

Wire-joint production

The wire-joint production is moving well. Both stations are producing high quality wire-joints.

The number of joints produced is above LOB requirement.

Harold Ogren (Indiana University)

Divider material:

All of the laser cut sheets have been shipped to Hampton. This part of our production is complete, but we have spare stock to supply some extra dividers if needed.

Radiator fiber punching

Radiator material of all types is almost complete at Breiner Co. There are only a few more shipments of type 3 required. We have spare material at Breiner and at Bloomington to handle extra requests.

Module production:

Module 1.01 has been shipped to Dubna for radiation testing. It has arrived at the Laboratory. It was set up for the test by Pauline Gagnon and the staff at the laboratory. The radiation test has started. First indications are that current rates are acceptable (even with C02, the modules has some limited gain). The test will finish the middle of May with approximently 20 LHC years of radiation.

Module 1.02 has completed the signal testing. It has been taken to Duke for gain testing.

Module 1.03 has also finished signal testing. It also has two dead wires, and low dark current.

Module 1.04 has passed the leak test and is being prepared for stringing.

Module 1.05 is being strung.

Module 1.06 has passed the leak test and is being prepared for stringing.

Module 1.07 has passed the leak test and is being strung.

Modules 1.08 and 1.09 are being assembled.

Module 3.01 has been strung, and is being tested.

1.2.1.2 Gas/Cooling 	Ken McFarlane (Hampton University)

Dr. Ketevi Assamagan continued work on a 'User Requirements' document for the TRT gas system. This document will specify to the CERN Detector Gas group what the TRT requires for the TRT gas system.

1.2.1.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Production Management Contingency Go-Ahead | 2-Jul-01 | 2-Jul-01 | 2-Oct-01 | Delayed (See #1) |

Note #1  Next meeting will be in October.

1.2.1.3 Installation

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Installation Management Contingency Go-Ahead | 2-Jul-01 | 2-Jul-01 | 2-Oct-01 | Delayed (See #1) |

Note #1  Next meeting will be in October.

1.2.5 TRT Electronics

1.2.5.1 ASD/BLR

1.2.5.1.1 Design 	Richard Van Berg (University Of Pennsylvania)

No significant design activity for the ASDBLR in the past month.

1.2.5.1.2 Prototype

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| ASDBLR Design Frozen | 13-Jul-01 | -- | 13-Jul-01 | On Schedule (See #1) |
| Select Final Electronic Design | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |

Note #1  We hope we are on schedule here, the wafer processing problems at TEMIC may cause a delay in getting certifiably good chips from the run submitted in mid January and could cause this date to slip.

Richard Van Berg (University Of Pennsylvania)

At the end of May we were informed by TEMIC that the ASDBLR/DTMROC processing run submitted on 15 January had had significant processing problems - leading to the certain loss of at least 25% of each wafer (one quadrant). Two to four of the damaged wafers will be sent to CERN soon and can then be diced and packaged to see if any of the chips are recoverable. Any perfect die from these wafers will tell us if the design changes worked, but failures are not necessarily so interesting since it is plausible that they could have been caused by processing errors. TEMIC is starting more wafers through the line, but have not yet given us a ship date for the backup processing.

On the packaging front we are making good progress with Signetics on defining a custom FBGA package for the ASDBLR (DTMROC to follow). An FBGA package would be small enough to fit on the barrel stamp boards, thus obviating the need for wire bonding (Chip On Board) to the board and, in addition would be a lower mass, lower inductance, lower capacitance solution for the End Cap. The goal here is to have a design and tooling ready for delivery of the DMILL wafers - now more plausible given the TEMIC problems.

1.2.5.1.3 Production (Qty = 64,000 + 32,000 Chips)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Management Contingency Go-Ahead | 2-Jul-01 | -- | 2-Jul-01 | On Schedule |

Richard Van Berg (University Of Pennsylvania)

Not yet, but may be getting closer. Hard to know yet what the processing glitch will do to our actual schedule. We still hope to have a PRR for the ASDBLR at the end of 2001.

1.2.5.2 DTM/ROC

1.2.5.2.1 Design 	Richard Van Berg (University Of Pennsylvania)

All DTMROC design effort is being concentrated on the DSM (Deep SubMicron) option. Most of that work is being carried out at CERN, but some of the analog blocks are being designed by Penn - specifically, the test pulse, the ternary receiver, the "LVDS" driver and the LVDS receiver. All that work is complete and cells have been (or soon will be) submitted for test fab. The first round test fab with the ternary receiver and LVDS pair has been returned to be bonded and tested in the next few weeks. The CERN group has completed the verilog model, tested the synthesis chain, defined the memory blocks and, except for a lot of remaining simulation and the actual place and route process is in good shape. A submission in Sept. or Oct. is probable.

1.2.5.2.2 Prototype 	Richard Van Berg (University Of Pennsylvania)

As noted under the ASDBLR heading, the Jan 15 run of DMILL had a processing problem that ruined at least one quadrant of each wafer so we will not be able to make yield (or maybe even precision analog) measurements on the wafers that get delivered in June. However, even one "perfect" chip would indicate that the design modifications were successful. Real yield measurements will have to wait for the backup wafers. We do not yet have a schedule for those from TEMIC.

1.2.5.3 PCB - End Cap

1.2.5.3.1 Design 	Richard Van Berg (University Of Pennsylvania)

The End Cap board design is frozen at this time and could be final but needs to be verified through the testing process. There is also the possibility that modifications to the design will be necessary to increase the yield which, for the triple flex DTMROC board, are not yet very good. CERN is working with various pc vendors on this issue.

1.2.5.3.2 Prototype 	Richard Van Berg (University Of Pennsylvania)

Continuing tests at CERN using the new sector prototype show good performance. Noise figures are near or at the thermal threshold and simple correlation plots show no structure although the statistics taken so far are marginal. More testing needs to be done, especially with a larger system using the 8 plane wheel but the system can only get a little larger until we receive the new ASDBLRs and DTMROCs.

Some Barrel stamp flex boards made at CERN have had ASDBLRs bonded to them at Lund (the bonding done at CERN failed - maybe because of a cleaning step) and at least one board seems to be in full working condition - it has been tested on the Penn IMS and shown to be alive (precision threshold measurements have not yet been made) and it survived having glop put atop it. There are nine other such boards that were bonded at Lund and once we have a better handle on the performance of the first board we will be in a position to move up to a somewhat larger test system - see the section of integration and system testing.

1.2.5.4 Common Electronics

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| End of 01 Test Beam | 28-Sep-01 | -- | 4-Nov-01 | Delayed (See #1) |

Note #1  We have been granted additional time up through Nov. 4 01. This is a GOOD thing, so "delay" is too pejorative a term, but seems the only thing to pull down. Also, this milestone should be under Test Beam, nicht wahr? Also, of course, this should be under test beam, not common electronics.

Richard Van Berg (University Of Pennsylvania)

No activity here except for some low level design (and some lively discussions) on the proposed "bulk" HV system. We now have collaboration agreement on a common and inexpensive approach to HV, but the possible budget is now in Management Contingency - producing a nearly perfect cancellation.

1.2.5.6 System Integration & installation

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| System Design Certified | 1-Oct-01 | -- | 1-Oct-01 | On Schedule (See #1) |

Note #1  This depends upon getting large enough system tests in place before Oct. and that depends upon getting enough chips from the Jan. submission and that depends upon getting wafers back and there is a glitch there, so hard to be sure that we can make this schedule, but not yet unreasonable - just tight and getting tighter.

Richard Van Berg (University Of Pennsylvania)

Tests with the TB3 boards have been going forward. Noise figures are slightly above what one would expect from just chamber capacitance, but in this configuration we are very sensitive to the position and arrangement of the digital I/O cable going to the patch panel (there is no Faraday cage at the tension plate possible with a TB3 as it mounts perpendicular to the tension plate - in the stamp board configuration (which we hope to be able to test soon) the cooling plate acts as a Faraday cage isolation structure in between the board and the cable. Nevertheless, even with the TB3 we can make measurements using a Co57 source and look for cross talk patterns. At the present sensitivity, we can use the TR threshold vs. the tracking threshold to get a > 50::1 ratio between the large hit and any possible crosstalk pickup. We are beginning to be sensitive enough to see crosstalk on the order of the ~ 1% that we have seen before on the chip and board measurements (this may simply be a limitation of the methods). There is some hint that the chamber may actually contribute slightly to the crosstalk, but below the dominate chip/board level - these measurements may be easier using the stamp boards, but are reassuring already although we have not looked at all possible board positions.

1.3 ARGON

Milestones with changed forecast dates:

| 1.3.2.1.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| 20 Ft Complete | 31-Dec-00 | 30-May-01 | 30-Jun-01 | Delayed (See #1) |
| Note #1 The delay is due to the initial delay in pin carrier production. Present schedule matches that of ATLAS. |

| 1.3.2.1.4 Installation |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Installation | 17-Jan-01 | 18-Nov-02 | 30-Sep-02 | Delayed (See #1) |
| Start Installation Procedure | 13-Jul-01 | 13-Jul-01 | 15-Sep-01 | Delayed (See #2) |
| Last Shipment | 31-Oct-01 | 31-Oct-01 | 30-Aug-02 | Delayed (See #3) |
| Note #1 New completion date matches new ATLAS schedule. Note #2 Installation cannot start before the acceptance tests of the cryostat are complete. Note #3 The last shipment date matches the new ATLAS schedule. Feedthroughs production will be completed earlier. |

| 1.3.2.2.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| 2 Complete HV Feedthrough Ports | 1-Mar-01 | 1-Jun-01 | 1-Jul-01 | Delayed (See #1) |
| Note #1 The delivery of 2 ports will match the cryostat availability at CERN. |

| 1.3.2.2.4 Installation |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| End-Cap C Install Complete | 5-Sep-01 | 25-Sep-01 | 25-Nov-01 | Delayed (See #1) |
| Installation HVFT ports on Endcap C | 5-Sep-01 | 25-Sep-01 | 25-Nov-01 | Delayed (See #2) |
| Note #1-2 Delay will match the cryostat availability. |

| 1.3.3.1.2 LN2 Ref. System Procurement |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Proposal Assessment & Contract Start | 1-Feb-01 | 10-May-01 | 10-Jul-01 | Delayed (See #1) |
| LN2 Ref. System Procurement Complete | 2-Apr-01 | 15-May-01 | 15-Jul-01 | Delayed (See #2) |
| Note #1-2 Bids are higher than expected. Negotiations continue. |

| 1.3.3.1.3 LN2 Ref. System Fabrication |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Ln2 Ref. System Fabrication | 1-Jun-01 | 11-Oct-02 | 1-Sep-03 | Delayed (See #1) |
| LN2 Ref. System Fabrication Start | 1-Jun-01 | 1-Jun-01 | 1-Aug-01 | Delayed (See #2) |
| Note #1 The completion date of system installation matches new ATLAS installation schedule. Note #2 Delay is due to continuing price negotiations. Not on the critical path. |

| 1.3.6.2.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| RFP Issued | 14-Jun-01 | 14-Aug-01 | 14-Aug-00 | Completed |
| 20% Warm Cables Ship in Place | 29-Jun-01 | 29-Oct-01 | 29-Oct-00 | Completed |
| 20% Warm Cables Delivered | 29-Jun-01 | 20-Oct-01 | 20-Oct-00 | Completed |
| Bid Evaluation Completion | 12-Jul-01 | 1-Sep-01 | 1-Sep-00 | Completed |
| PM Approval of Purchase Order | 26-Jul-01 | 10-Sep-01 | 10-Sep-00 | Completed |
| Contract Award | 2-Aug-01 | 20-Sep-01 | 20-Sep-00 | Completed |
| 40% Warm Cables Delivered | 30-Aug-01 | 1-Dec-01 | 1-Dec-00 | Completed |
| 40% Warm Cables Ship in Place | 30-Aug-01 | 1-Dec-01 | 1-Jan-01 | Completed |
| 60% Warm Cables Delivered | 30-Oct-01 | 30-Oct-01 | 30-Mar-01 | Completed |
| 60% Warm Cables Ship in Place | 30-Oct-01 | 30-Oct-01 | 30-Mar-01 | Completed |

| 1.3.7.1.2 Pre-Proto/Mod 0/Atlas Prototype |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Freeze Connector Location | 1-May-01 | 1-May-01 | 1-Jul-01 | Delayed (See #1) |
| Rad Tol. FEB Design Review | 1-May-01 | 1-May-01 | 3-Sep-01 | Delayed (See #2) |
| Note #1 Delayed due to delay in finalizing TTC connector. Note #2 Delayed due to late delivery of rad-tol voltage regulators. |

| 1.3.8.1.3 Production (Qty = 3,441 Boards) |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Start Deliveries to FEB (ORSAY/Nevis) | 2-Jul-01 | 2-Jul-01 | 1-Jan-02 | See Note #1 |
| Note #1 Delivery will be started to Nevis or Orsay only when requested. |

| 1.3.10.1.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| FCAL1-C Matrix Plate Inspection-2 | 8-Jun-01 | 8-Jun-01 | 8-May-01 | Completed (See #1) |
| FCAL1-C Matrix on Carrier | 23-Jul-01 | 23-Jul-01 | 15-Jun-01 | On Schedule (See #2) |
| FCAL1-C Tube Swaging Complete | 1-Oct-01 | 1-Oct-01 | 31-Aug-01 | On Schedule (See #3) |
| Note #1 This will be completed well ahead of this schedule. But as I've pointed out many times, we negotiated an addendum to the plate machining contract which accelerated the schedule and these milestones do not reflect this change. Note #2 We seem to be able to clean plates faster than our conservative estimates of two months ago so we believe we will have the completed matrix on the carrier by this date (if not earlier). Note #3 I've aggressively moved up the forecast date to our present best estimate. |

1.3.1 Barrel Cryostat

1.3.1.4 Barrel Cryostat Manufacturing

1.3.1.4.3 Manufacturing Monitor

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Cryostat Transport Review | 1-Sep-00 | -- | 1-Sep-00 | Completed |

Barrel Cryostat Monthly Report	Jack Sondericker (Brookhaven National Lab.)

Throughout the month of April the Barrel Cryostat was being prepared for shipment to CERN.

Work packing up the cryostat and its fixtures for shipment to CERN was completed by the second week of the month. Special care was taken to protect the feed through flange surfaces. The Cryostat and fixtures were loaded on a barge at the Kawasaki dock on May 18th and brought to Kobe harbor. Here the Cryostat and fixtures were loaded aboard and carried below the deck of an ocean going container ship that will transport the equipment to Rotterdam. Then the cryostat will go by barge up the Rhine River to Strasbourg and the remaining distance overland by truck to CERN. By the end of May, the transport ship will be about 80% of the way across the Indian Ocean, heading for the Suez Canal.

1.3.1.5 Assembly & test in West Hall

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Cryostat Arrives at CERN | 15-May-01 | -- | 15-Jul-01 | Delayed (See #1) |
| Final Cryostat Acceptance (KHI-CERN) | 31-Aug-01 | -- | 31-Aug-01 | On Schedule |

Note #1  The delay is due to last minute leak tests and packing arrangements. The arrival date matches the availability of the Building 180.

1.3.2 Feedthrough

1.3.2.1 FT-Signal

1.3.2.1.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Cryostat Install Design Complete | 1-Sep-00 | -- | 15-May-01 | Completed |
| I/F Equipment Avail for Final Cryostat Complete | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |

1.3.2.1.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 20 Ft Complete | 31-Dec-00 | 30-May-01 | 30-Jun-01 | Delayed (See #1) |
| Last Pin Carrier Delivery | 1-Mar-01 | -- | 1-Sep-01 | Delayed (See #2) |
| 25% of Pin Carriers Delivered | 1-May-01 | -- | 1-May-01 | Completed |
| 50% of Pin Carriers Delivered | 2-Jul-01 | -- | 2-Jul-01 | On Schedule |
| 34 FT Complete | 15-Oct-01 | -- | 15-Oct-01 | On Schedule |

Note #1  The delay is due to the initial delay in pin carrier production. Present schedule matches that of ATLAS.

Note #2  After initial delay, the production matches the new ATLAS schedule

Bob Hackenburg (Brookhaven National Lab.)

We now have 18 Feedthroughs fully assembled and tested, and ready for shipment. We have scrapped our plans to send one (defective, FT003) feedthrough on a round trip to CERN and back, as a shipping study, and instead will be sending 4 ready-to-install FTs on a one-way trip to CERN, probably in about a week. We are acquiring a number of shock-monitors for this purpose. The defective FT has been dissected instead of shipped, (which we were planning on doing anyway after it returned, but we got impatient to verify the details of its trouble). We had believed the failure (which was a short between two signal lines, reproducible as the temperature dropped below -54C) to be an internally defective Vacuum Cable connector, since the TDR had pinpointed the location to the cold flange. However, upon opening up of the bellows and removing the cable, the cable turned out to be OK. The problem in fact turned out to be the spring clips, which bottom out in the pincarriers (i.e., a design flaw in the vacuum cable connector) and are forced in too close to the signal pins. We had already identified that problem after the first three FTs were made (and the first one failed), and have addressed it months ago by installing small, nylon washers over the screws on the vacuum cable connectors, so that they don't bottom out in the pincarrier. The bottom line is that we didn't learn anything we needed to learn, since the real problem had already been fixed (except in the first 3 FTs, two of which are perfectly good in spite of their lack of nylon washers), but at least we didn't get a nasty surprise.

The plan is to install the nylon washers on FT003, and close it back up, test it, etc., and it should be perfectly good. FT020, the latest failure, is actually a good failure because of its lesson. That is, FT020 developed a small leak (but bad enough: 10-6) around one of the pins in the pincarrier. The good news is that it was precisely the pin which had been badly bent over during cable installation, so it's preventable, sort of, and the lesson is that by badly bending any one pin during installation at CERN, we would have to discard the entire FT. Which means, as we already know, only more so now, that we absolutely need to minimize the number of times cables are connected to pincarriers. We are looking into the possibility of installing the warm cables at CERN, during FT installation, even if the baseplanes aren't ready, so that we can test the FTs without making additional connections.

We also have 2 more feedthroughs nearly done, bringing the total to 22, and when FT003 and FT020 are repaired (sometime next week, most likely), our total will be 24. We see no problem in being ready to install the first 32 by September, even allowing for vacations, etc.

Also, pincarriers continue to arrive (slightly) faster than we can use them, following about a two week lapse when about 24 were diverted to UVIC, accompanied by a government snafu which caused the manufacturer to stop production for about a week (now fixed!).

1.3.2.1.4 Installation

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Installation | 17-Jan-01 | 18-Nov-02 | 30-Sep-02 | Delayed (See #1) |
| 1st Shipment | 23-Apr-01 | -- | 10-Jul-01 | Delayed (See #2) |
| Start Installation Procedure | 13-Jul-01 | 13-Jul-01 | 15-Sep-01 | Delayed (See #3) |
| Last Shipment | 31-Oct-01 | 31-Oct-01 | 30-Aug-02 | Delayed (See #4) |

Note #1  New completion date matches new ATLAS schedule.

Note #2  First Feedthrough shipment will be in July. Cryostat and West area will not be ready before that time.

Note #3  Installation cannot start before the acceptance tests of the cryostat are complete.

Note #4  The last shipment date matches the new ATLAS schedule. Feedthroughs production will be completed earlier.

1.3.2.2 HV Feedthrough

1.3.2.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 2 Complete HV Feedthrough Ports | 1-Mar-01 | 1-Jun-01 | 1-Jul-01 | Delayed (See #1) |
| Barrel FTs (Mechanical) Delivered to CERN | 1-May-01 | -- | 15-Jul-01 | Delayed (See #2) |
| Barrel FTs (Electrical) delivered to CERN | 1-Jun-01 | -- | 15-Jul-01 | Delayed (See #3) |
| Production Complete | 14-Sep-01 | -- | 14-Sep-01 | On Schedule |

Note #1  The delivery of 2 ports will match the cryostat availability at CERN.

Note #2-3  The delivery will match the cryostat availability at CERN.

Michal Rijssenbeek (SUNY Stony Brook)

1.3.2.2.3.1 Warm Connectors

REDEL/LEMO warm HV connectors all in house. Crimping tests done, and tooling started.

1.3.2.2.3.2 Cold Connectors

Cold connectors all in house. Crimping tests successful, tooling available.

1.3.2.2.3.3 HV Wire

All wire has been received and used for manufacture of wire feedthroughs.

1.3.2.2.3.6 Sealed Wire FT (WFT)

Douglas Engineering has delivered all 28 WFTs (includes spares).

All WFTs have been tested in water at 5 kV. 2-3 wireloops per WFT found faulty, which is compensated by 2-3 excess loops available in the WFTs. Cleaning of the WFTs is well advanced.

Wire FT Plates have all been delivered, and are being cleaned. The first plate with four WFTs is in the cleanroom awaiting inserting in the HVFT.

1.3.2.2.3.4-5 Filter Modules and Filter Crate

All HV parts have been delivered. The remaining Filter daughter boards are expected in the next week. Front/back panels for the modules and backplane have been ordered. HV spark tests of the filter resistor have restarted, in order to check that resistors survive when HV PSs trip and crowbar the voltage at the power supply. In that situation the full energy of the calorimeter cells attached to a HV channel is dissipated over the filter resistor. For the current test, we connected a 64-channel filter prototype module in reverse, and charged (to 5 kV) and spark-discharged it via a 100 kOhm resistor (as foreseen in the EMB and EMEC). This is equivalent to 1.6 uF capacitance, and an energy of 25% of the energy expected from a 25 uF calorimeter capacitance at 2.5 kV.

1.3.2.2.3.7-9 Vacuum Components for the HV FT

All six HVFTs (flanges, bellows, pipe, ALU/SS transitions) have been received, machined, and have been welded and tested at BNL. The two barrel Feedthrough Ports have been completed and await shipping to CERN.

1.3.2.2.3.10 Assembly

After cleaning the first four WFTs, assembly has started. A two-story platform for installation of the cable tree into the HVFT port is installled in the clean room area, including a small electric hoist to lift the feedthrough plate plus wire feedthroughs. HV corona test equipment is now in place to start testing the HV cable tree in Argon inside the HVFT Testvessel.

1.3.2.2.4 Installation

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Ship End-Cap C to CERN | 5-Mar-01 | -- | 15-Jul-01 | Delayed (See #1) |
| Ship Barrel to CERN | 1-May-01 | -- | 1-Aug-01 | Delayed (See #2) |
| End-Cap C Install Complete | 5-Sep-01 | 25-Sep-01 | 25-Nov-01 | Delayed (See #3) |
| Installation HVFT ports on Endcap C | 5-Sep-01 | 25-Sep-01 | 25-Nov-01 | Delayed (See #4) |

Note #1  Delayed due to FT delay. Not on critical path.

Note #2-4  Delay will match the cryostat availability

Michal Rijssenbeek (SUNY Stony Brook)

We are designing and fabricating a shipping container for the FT ports. Details and order of installation are under discussion with CERN and BNL personnel. Current plans are to install/weld the HVFT before Signal FTs (as in the original plan), but to install the HV cable tree and do the routing afterwards (i.e. with the signal FT cables in place).

1.3.3 LAr Cryogenics

1.3.3.1 LN2 Refrigerator System

1.3.3.1.2 LN2 Ref. System Procurement

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Proposal Assessment & Contract Start | 1-Feb-01 | 10-May-01 | 10-Jul-01 | Delayed (See #1) |
| Bid Return | 15-Mar-01 | -- | 10-May-01 | Completed |
| LN2 Ref. System Procurement Complete | 2-Apr-01 | 15-May-01 | 15-Jul-01 | Delayed (See #2) |
| Start Production | 1-Aug-01 | -- | 1-Aug-01 | On Schedule |

Note #1-2  Bids are higher than expected. Negotiations continue.

Jack Sondericker (Brookhaven National Lab.)

LN2 Refrigerator Procurement Request for Proposal (RFP)

Two Proposals for the ATLAS Nitrogen Refrigerator System (ANRS) were received at BNL before the closing date of April 28th. Members of the Source Selection Board read and evaluated the technical portion of the submissions. Both offerors were deemed technically capable of supplying a reliable refrigerator system to CERN and the selection process essentially defaulted to that proposer with the lowest cost. Upon opening price information, both offerors were considerably more expensive than estimates. Negotiations were initiated with both contenders to reduce costs by any means possible. By months end negotiations are continuing.

1.3.3.1.3 LN2 Ref. System Fabrication

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Ln2 Ref. System Fabrication | 1-Jun-01 | 11-Oct-02 | 1-Sep-03 | Delayed (See #1) |
| LN2 Ref. System Fabrication Start | 1-Jun-01 | 1-Jun-01 | 1-Aug-01 | Delayed (See #2) |

Note #1  The completion date of system installation matches new ATLAS installation schedule.

Note #2  Delay is due to continuing price negotiations. Not on the critical path.

1.3.3.2 LN2 Quality Meter System

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| LN2 Quality Meter System | 19-Nov-03 | [New] | 19-Nov-03 | On Schedule |

1.3.3.2.2 Quality Meter Prototype

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Quality Meter Prototype | 1-May-00 | -- | 21-Aug-01 | Delayed (See #1) |
| Final Design Review | 1-May-01 | -- | 21-Aug-01 | Delayed (See #2) |
| Specification PRR Review | 1-Aug-01 | -- | 1-Aug-01 | On Schedule |

Note #1  The prototype exist. An improved design with higher reliability is under development.

Note #2  Will match the cryostat installation schedule

Quality Meter Prototype	Jack Sondericker (Brookhaven National Lab.)

Progress continued to be made in the month of May in that an optimized mechanical design was adopted as the official prototype. Meanwhile changes were made in the design of the electronic circuitry to afford better stability, greater overall accuracy and complete insensitivity to effects of distributed cable capacity.

A prototype meter will be constructed and tested in time for the Production Readiness Review scheduled next August.

1.3.3.2.3 Quality Meter Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Parts and Material Start | 29-Aug-01 | -- | 29-Aug-01 | On Schedule |
| Quality Meter Production | 1-Oct-01 | -- | 30-Oct-02 | Delayed (See #1) |

Note #1  Delay matches the new ATLAS schedule

1.3.4 EM Electronics/MB System

1.3.4.2 Motherboard System

1.3.4.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Delivery of Module 3 boards | 15-Mar-01 | -- | 15-Apr-01 | Completed |
| Delivery of Module 4 boards | 15-Apr-01 | -- | 15-Apr-01 | Completed |
| 10% MB System Production Complete | 14-May-01 | -- | 30-Apr-01 | Completed |
| Delivery of Module 5 boards | 1-Jun-01 | [New] | 1-Jun-01 | On Schedule |
| Delivery of Module 6 boards | 20-Jun-01 | [New] | 20-Jun-01 | On Schedule |
| Delivery of Module 7 boards | 15-Jul-01 | [New] | 15-Jul-01 | On Schedule |
| 25% MB System Production Complete | 6-Aug-01 | -- | 6-Aug-01 | On Schedule |

Srini Rajagopalan (Brookhaven National Lab.)

Module 13: Completed, packed, shipped to Saclay on May 3, 2001

Module 12: Completed, packed, shipped to Annecy on May 6, 2001

Module 11: Completed, packed, shipped to Saclay on May 31, 2001

Module 10: Target ship date June 11, 2001

Summing Boards: All boards received. Visual inspection and test in process.

High Voltage Boards: Completed, packed and ready for shipment

All Motherboards: Completed, packed and ready for shipment

Alignment Boards: All boards will be packed and ready for shipment by 6/4/01.

Module 9 Target ship date June 30, 2001

Summing Boards: Targeted vendor ship date June 15,2001

High Voltage Boards: Targeted vendor ship date June 15, 2001

Front Motherboards: Received 14 out of 16 printed circuit board assemblies. They have been inspected and testing is in process.

Back Motherboards: Received 13 out of 14 printed circuit board assemblies. They have been inspected and testing is in process.

Alignment Boards: In BNL stock

1.3.4.2.4 Installation Complete 	Srini Rajagopalan (Brookhaven National Lab.)

Installation of Module 15 has been completed at Saclay

Installation of Module 14 is in progress at Annecy

Installation/Test of Module 13 is in progress at Annecy

1.3.5 Preamp/Calibration

1.3.5.1 Preamps

1.3.5.1.3 Production (QTY=30000)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Preamp Deliveries to FEB | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |

Hong Ma (Brookhaven National Lab.)

Hybrid production is going well.

IO-826: 1056 received. 1043 passed and ready for shipment. Unchanged from last month.

IO-824: Received 576 from vendor since last report.

Total: 1056 received. 288 test in progress. 697 passed and ready for shipment.

IO-823: Received 1536 from vendor since last report.

Total: 2752 received. 864 test in progress. 1809 passed and ready for shipment.

Test Station-I experienced timing jitter. This is being worked on.

Test Station-II is in use.

1.3.5.2 Precision Calor. Calibration

1.3.5.2.3 Production Support to LAPPL/LAL

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Production Readiness Review | 1-May-01 | -- | 1-Aug-01 | Delayed (See #1) |

Note #1  Delay in DMILL chip production

1.3.6 System Integration

1.3.6.1 Pedestal

1.3.6.1.1 Design 	Helio Takai (Brookhaven National Lab.)

The barrel pedestal design is concluded. The pedestal design for the other systems is being finalized.

1.3.6.1.3 Production 	Helio Takai (Brookhaven National Lab.)

Qualification part is expected to be delivered June 15.

1.3.6.2.3 Production	Helio Takai (Brookhaven National Lab.)

An award for baseplane construction was awarded to Tyco. Tyco was chosen for being cheaper although it is not clear if they understood clearly what needs to be done.

1.3.6.3.2 Prototype 	Helio Takai (Brookhaven National Lab.)

Qualification piece to be delivered June15.

1.3.6.4 Power and Services

1.3.6.4.1 Design 	Helio Takai (Brookhaven National Lab.)

The design of the power supply exists. The prototype is now being concluded for initial phase of testing.

1.3.6.4.2 Prototype 	Helio Takai (Brookhaven National Lab.)

Two DC-DC converters, 300 V in, 4V out were manufactured by Modular Devices. These two units are designed to meet the radiation requirements. A procurement for MOSFETs in die form was also purchased. We should have the remaining 10 (ten) DC-DC converters for testing in about 2-4 weeks. The tests include radiation tests, magnetic field test, stability, and noise. The tests are expected to take a minimum of two months. Help is welcome.

1.3.6.5 Cooling

1.3.6.5.1 Design 	Helio Takai (Brookhaven National Lab.)

A new cooling plate design is being evaluated.

1.3.6.5.2 Prototype 	Helio Takai (Brookhaven National Lab.)

Prototypes delivered to us by Showa Aluminum are under test. So far only accelerated corrosion tests were performed. Dynamic parameters and cooling efficiency need to be carried out.

1.3.7 Front End Board

1.3.7.1 FEB

1.3.7.1.1 Design 	John Parsons (Columbia University)

The DMILL DMUX ASIC and the DMILL TTCRx were successfully integrated into the 1/4 Digital FEB. We now have 5 DMILL chips (these plus SPAC Slave, ConfigControl and GainSel) working together, along with an FPGA emulator of the final ASIC, the SCA Controller (for which DMILL and DSM versions are expected by July).

Design of the FEB continues, with work concentrating on the digital part.

The STm development of rad-tol voltage regulators has suffered another setback, with the latest prototype proving to be non-functional. STM is working to understand the latest problem, but it is clear prototypes will not be available now until at least November, an additional 6 month delay. This poses a serious problem for the FEB schedule, which is now held up by the regulators; we are in the process of re-evaluating the schedule in light of this problem. Due to the continued failure of the STm development, we have also diverted significant engineering manpower to investigation of possible alternative solutions.

An agreement has been reached within LAr on how to divide procurement responsibilities among the various labs involved in the FEB. This was necessary to allow orders (e.g. for ADCs) to proceed within the next few months.

1.3.7.1.2 Pre-Proto/Mod 0/Atlas Prototype

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Freeze Component for ATLAS Prototype | 1-Mar-01 | -- | 1-Aug-01 | Delayed (See #1) |
| Freeze Connector Location | 1-May-01 | 1-May-01 | 1-Jul-01 | Delayed (See #2) |
| Rad Tol. FEB Design Review | 1-May-01 | 1-May-01 | 3-Sep-01 | Delayed (See #3) |
| 1st Delivery of Layer Sum Boards | 2-Jul-01 | -- | 2-Jul-01 | On Schedule |
| Feb - ATLAS Layout Complete | 21-Aug-01 | -- | 21-Aug-01 | On Schedule |
| Critical Design Review | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |
| Start Assembly | 11-Sep-01 | -- | 11-Sep-01 | On Schedule |
| Rad Hard. - All Components | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |

Note #1  Delayed due to requirement for additional radiation testing of COTs.

Note #2  Delayed due to delay in finalizing TTC connector.

Note #3  Delayed due to late delivery of rad-tol voltage regulators.

1.3.7.1.5 Radiation Testing 	John Parsons (Columbia University)

Proton-irradiation tests were performed of the DMILL GainSel and ConfigControl ASICs. The chips survived, as expected for DMILL, the total dose. Online monitoring detected the occurrence of SEUs at a low rate; further analysis of the data is ongoing to understand the types of errors seen and the impact for operation within ATLAS.

1.3.7.2 SCA

1.3.7.2.1 Design 	John Parsons (Columbia University)

SCA testing with the robotic test setup at Grenoble is being prepared for the chips from the engineering run; tests should start by July.

Due to the reassignment of procurement responsibilities, the US will no longer pay for SCA chips, which will be paid for by our European colleagues. Therefore, the milestones associated with submission of the US order for SCA chips have been deleted.

1.3.7.4 Optical Links

1.3.7.4.1 Design 	John Parsons (Columbia University)

Work is continuing with our Taiwanese colleagues to finalize the optical link integration on the FEB.

1.3.7.4.2 Prototype/Module 0

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| ATLAS Prototype | 1-Jun-01 | -- | 1-Jun-01 | On Schedule |
| Optical Links ATLAS Prototype | 1-Jun-01 | -- | 1-Jun-01 | On Schedule |

1.3.8 Trigger Summation

1.3.8.1 Layer Sums

1.3.8.1.3 Production (Qty = 3,441 Boards)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Last Delivery of Layer Sum Bds | 1-Jul-01 | -- | 1-Jul-01 | On Schedule |
| Start Deliveries to FEB (ORSAY/Nevis) | 2-Jul-01 | 2-Jul-01 | 1-Jan-02 | See Note #1 |

Note #1  Delivery will be started to Nevis or Orsay only when requested.

Bill Cleland (University Of Pittsburgh)

The production of LSBs continues apace. The S2x8 have been completed and are in storage. The S1x16 have been tested, but a small modification is required on the G=2 version to prevent the output from going to the voltage rails whenever the input is disconnected. This will be done in the fall.

The S4x4 boards have been delivered and are in the burn-in process. There is a problem at the moment with the testing software, which is causing a few days delay in the testing of the S4x4 boards.

1.3.8.2 Interface to Level 1

1.3.8.2.1 Design/Electronic Tooling/Comp. Specs

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Circuit Design of ATLAS receiver Complete | 12-Aug-01 | -- | 12-Aug-01 | On Schedule |
| Final Design Complete | 4-Oct-01 | -- | 4-Oct-01 | On Schedule |

Bill Cleland (University Of Pittsburgh)

A set of test boards for evaluating the analog chain for the receiver was received this month, and they are being assembled during the month of June. A replacement IC for the variable gain amplifier has been found (CLC522) which has a gain linear in voltage and is well suited for an application with low gain, as in our system. The evaluation board for this IC has been received, so it will be evaluated in June. Layout work on the VGA daughterboard is stalled until the IC question is settled. The control circuit FPGA code has been designed, and a timing simulation has been carried out. The code for the controller card is being developed simultaneously.

1.3.9 ROD System

1.3.9.1 ROD Board

1.3.9.1.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Reconstruct E, T, and chisquare for TB data | 12-Feb-01 | -- | 1-Jul-01 | See Note #1 |
| Complete Code to form averages of Cal. | 18-Jun-01 | -- | 10-Jul-01 | See Note #2 |
| Complete Code to get OFC from CAL. Data | 4-Sep-01 | -- | 4-Sep-01 | See Note #3 |

Note #1  Done, not completely reviewed.

Note #2-3  Calibration procedure not completely defined.

Rod Engelmann (SUNY Stony Brook)

BNL/Stony Brook - ROD demo tests: The DAQ-1 data acquisition software was installed and customization for the BNL hardware was begun. Tests with the calibration board continued.

Nevis Lab: The design of the PU board with a TI C6203 DSP and no dual port memory proceeded and a one-DSP PU board to be fitted on the existing ROD motherboard was submitted for construction.

SMU: Code development for averaging calibration data in the TI C62 DSP continued. SMU also started to look at the new TI C64 DSP and the coding of it as an ongoing R&D project.

1.3.10 Forward Calorimeter

1.3.10.1 FCAL1 Module

1.3.10.1.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FCAL1-C Interconnects Complete | 30-Apr-01 | -- | 30-Jun-01 | Delayed (See #1) |
| FCAL1-C Matrix Plate Inspection-2 | 8-Jun-01 | 8-Jun-01 | 8-May-01 | Completed (See #2) |
| FCAL1-C Matrix on Carrier | 23-Jul-01 | 23-Jul-01 | 15-Jun-01 | On Schedule (See #3) |
| FCAL1-C Tube Swaging Complete | 1-Oct-01 | 1-Oct-01 | 31-Aug-01 | On Schedule (See #4) |

Note #1  The sample panel of interconnects works very well. One HV test went to 3.5 kV in air without breakdown where 250 V in Argon is the operating potential. We'll place the final order for the regular shaped interconnects as soon as we have some spare time. This is not on the critical path and since we are trying to catch up in some more critical areas we will let this slide until time is available.

Note #2  This will be completed well ahead of this schedule. But as I've pointed out many times, we negotiated an addendum to the plate machining contract which accelerated the schedule and these milestones do not reflect this change.

Note #3  We seem to be able to clean plates faster than our conservative estimates of two months ago so we believe we will have the completed matrix on the carrier by this date (if not earlier).

Note #4  I've aggressively moved up the forecast date to our present best estimate.

FCal1 Module	John Rutherfoord (University Of Arizona)

Fourteen (of 18) copper matrix plates for FCal1C have been cleaned and set up on the assembly stand (aka the carrier). The remaining four plates will be stacked before mid-June. At this point we will have met the milestone called "Matrix on Carrier" for FCal1C.

The two ultrasound units which broke during April were fixed more-or-less on schedule and with a little weekend work we were able to limit the lost time to just two weeks. It was discovered that two ground pin holes (out of about 6,000 in each end plate) were not drilled at the machine shop (STC) on each of the two endplates so we did these by hand.

About 25,800 copper electrode rods (24,520 needed) were sent to our machine shop to have holes drilled in one end. These holes will accept the signal pins. About 4,000 have been drilled in the first week and we expect this rate to continue. We will start cleaning the first batch in early June. We anticipate the rod cleaning will be difficult and time-consuming but not a critical path item.

As soon as the matrix is completed we will start inserting the copper electrode rods (completely processed some time ago and now in storage in dry nitrogen) and swaging them in place. Present best guess is that tube stuffing will begin in mid June and be completed by end of August.

We had originally planned to make mirror image modules for the C and A ends. However it was pointed out at the FCal PRR that other systems and the electronics were arranged in a way that made the two ends nearly identical rather than mirror symmetric so we changed plans to make identical modules. However because of the somewhat irregular tiling of our readout we are re-evaluating this decision, quite late in the game. A decision to switch at this point requires agreement from our collaborators within the FCal and some concurrence (procedure unknown) from the management and knowledgeable colleagues. We must make a decision quickly because the FCal1A plates are being machined at this moment so that the decision will soon be made for us. Mirror symmetry (and 180 degree rotational symmetry about the beam axis which we always had) allows each phi segment of the FCal to be identical at each end. It also means that back-to-back particles originating from the interaction point will impact identical shaped readout tiles. We view both these as very desirable, particularly considering reconstructing events in the forward calorimeters. A change in symmetry will require a change order with the STC and a re-negotiation of the complex contract.

1.3.10.2 FCAL Electronics

1.3.10.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| PCBs received at AZ | 21-Nov-00 | -- | 15-Dec-01 | Delayed (See #1) |
| A Cables Delivery from Axon | 2-Jul-01 | -- | 2-Jul-01 | On Schedule (See #2) |

Note #1  The start of the summing board layout was recently delayed by about one month. So yet another schedule was produced showing the boards completed in December of this year. The layout has started so there is slightly more realism to this forecast. (Note spelling of forecast.)

Note #2  No new news on this. This milestone is FAR from the critical path.

Cold Electronics	John Rutherfoord (University Of Arizona)

The relay boards which will be used for production characterization of our Axon cold cables and which will operate in liquid N2 or Argon, arrived back from the fabrication house and were sent out to be stuffed. The control board which operates outside the cryostat has been built and mostly programmed. The on-line computer with programming and data acquisition is largely in place and parts have been tested. We've received some help in interpreting the data from Bill Cleland and his co-workers.

Work continues on laying out the summing boards. We have not yet received quotes on the transmission line transformers, the technically critical component on the summing boards, but expect a response soon. The other components were ordered long ago but with extraordinarily protracted delivery. None of this is yet on the critical path.

1.4 TILE

Milestones with changed forecast dates:

| 1.4.3.2.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| 3-In-1 Card Fab 100% Complete | 16-Jul-01 | 16-Jul-01 | 31-May-01 | Completed |

| 1.4.4.1.3 Production |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Scintillator procurement | 1-Oct-00 | 1-Jul-01 | 1-Aug-01 | Delayed (See #1) |
| Start Scintillator Assembly | 1-Dec-00 | 1-Aug-01 | 1-Sep-01 | Delayed (See #2) |
| Note #1 Prototypes of the ITC extension scintillators were tested at the CERN test beam last summer. Based on the test beam experience, we have made final modifications to the scintillator design. Procurement will follow as soon as final drawings are approved, and funding to buy extension scintillators is available at MSU. Note #2 Prototypes of the ITC extension scintillators were tested at the CERN test beam last summer. Based on the test beam experience, we have made final modifications to the scintillator design. Assembly will follow as soon as funding to buy extension scintillators are available at MSU. |

1.4.1 Extended Barrel Mechanics 	James Proudfoot (Argonne National Lab.)

Submodule production was completed at the University of Chicago, with a total of 194 submodules constructed. Of these, 13 submodules will require rework to correct distorted slots and 3 are oversize and will not fit on the girder. This rework will be carried out at Argonne when deemed necessary. At the other two submodule sites, 136 submodules have been constructed at the University of Illinois and 153 at Argonne. module production is also continuing well on schedule with 33 modules mechanically tested, of which 17 have been shipped to Michigan State University for instrumentation. 28 modules in total have been tested using a radioactive source or LED test system. All modules are meeting the TileCal specification. A total of 24 modules have been shipped to CERN and in addition 4 are ready for shipment (including one module being retained at Argonne for long term testing).

1.4.1.1 Submodules

1.4.1.1.3 Production 	Steven Errede (University Illinois-Urbana-Champaign)

In May 2001, we made 10 ATLAS TileCal submodules. We have now made a total of 143 submodules. Because a significant portion of the floor of our high-bay lab area here at UI is concurrently being replaced (wood to concrete), we shipped 8 fully-completed submodules to Argonne in mid-May. A total of 136 submodules have now been shipped to Argonne from UIUC.

Victor Guarino (Argonne National Lab.)

Six submodules were fabricated completely at ANL during May. An additional 2 were stacked and glued but were not fully welded and painted. Problems arose with the glue dispenser, several seals began leaking and had to be replaced which resulted in production being closed down nearly 1 week. Regular maintenance was performed on the remainder of the equipment.

James Pilcher (University Of Chicago)

At the end of May we closed out submodule production at Chicago. In total, 194 submodules were stacked, glued, and tack welded. In consultation with ANL we agreed that 13 submodules which require re-work because some scintillator slots are too small will be set aside in an incomplete state until the amount of spare materials is known. It would be more straightforward to replace them with new submodules. The raw material status will not be known for several months and any recovery work will be done at other sites.

The work accomplished in May involved stacking, gluing, and tack welding of 2 submodules to bring the total to 194.

Full welding was done on 3 submodules to give a revised and final total of 189. We note that 5 of the 13 incomplete submodules were only tack welded.

Cleaning was done on 3 submodules in May for a revised and final total of 181. Cleaning was not done on the 13 submodules with small slots.

Painting was done this month on 7 for a total of 175. The unpainted ones are the 13 incomplete submodules plus the 6 which exceeded the thickness spec, as mentioned in a previous month’s report.

The QC sheets are not quite up to date at the end of May and will be completed in June. As of the end of May some miscellaneous material such as spare weld bars, paint, spring pins, etc. must still be transferred to ANL. All submodules and spare steel plates have been already shipped.

Our certified welder and his helper have been let go and we have no further manpower. Final cleanup tasks are being handled by U of C personnel.

1.4.1.2 Extended Barrel Module

1.4.1.2.1 Design 	Victor Guarino (Argonne National Lab.)

Design work continued during May on the support saddles and cryostat supports for the Extended Barrel. The preliminary design of the support saddles is now complete and has been sent to CERN to be evaluated for integration with muons and other components of the detector.

Structural analysis work continued on the design of the saddle and cryostat supports. A Finite Element model of EB has been created which included a simplified model of the saddle structures. This FE model was used to find the forces acting between the EB and the saddles. These forces were then applied to a very detailed FE model of the saddles in order to examine stresses in the saddles. The stresses and deflections of the saddles are within acceptable limits.

Detailed analysis is continuing on the cryostat back supports. The basic design is complete and the stresses and deflections are within acceptable limits. However, work is continuing on methods of supporting the cryostat under earthquake conditions.

1.4.1.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Module Completion (30 Cum) | 1-May-01 | -- | 1-May-01 | Completed |

Victor Guarino (Argonne National Lab.)

Two modules were constructed during May, ANL33 and ANL34. No problems were encountered during the construction of these modules. Girders #43-50 were inspected during the month at the factory in Spain. No problems were found with any of them.

1.4.1.4 Testing

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Beam test Series A | 2-Oct-01 | -- | 2-Oct-01 | Delayed (See #1) |

Note #1  Testing of production modules has been delayed due to a delay in the fabrication of production electronics. In particular a major factor in this delay was the unavailability of the TTC chip. This test is now scheduled to commence at the beginning of July 2001.

1.4.2 Extended Barrel Optics

1.4.2.1 Extended Barrel Scintillator

1.4.2.1.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 100% Tile Deliveries from Russia Compl | 2-Jul-01 | -- | 2-Jul-01 | On Schedule |

David G. Underwood (Argonne National Lab.)

At Argonne we completed module ANL 30. There were three scintillation tiles in one pack which gave significantly less light than the rest of the pack. These were replaced.

Optical Instrumentation Summary	Robert Miller (Michigan State University)

Instrumentation of the Tilecal extended barrel modules continued on a normal schedule in May at ANL and MSU. Two modules were completed, one at each site. A total of 29 modules have been instrumented with 3 additional modules in production. A new batch of tiles, sizes 4-11, was received in May. This shipment will be sufficient for the next 16 modules instrumented at MSU and ANL.

At MSU, module ANL-25 was completed in May, scanned with the LED source, and shipped back to ANL. Module ANL-31 was shipped to MSU and prepared for instrumentation. Fibers were glued and polished in module ANL-28. Fiber and profile installation was started in ANL-29. The rate of EB module instrumentation at MSU could increase during the summer months to 3 weeks/module while our students are working full time. This rate will be limited by module construction and other supplies.

1.4.2.2 Extended Barrel Fibers

1.4.2.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 65% Fibers in Profiles from Lisbon to ANL & MSU | 2-Jan-01 | -- | 1-Jul-01 | Delayed (See #1) |
| 50% Module Instrum Complete | 29-Jun-01 | -- | 29-Jun-01 | On Schedule |

Note #1  Initial delivery of WLS fibers and profiles was delayed by about 6 months due to start up problems with the robot facility in Lisbon. Production and delivery of these components is now proceeding at a rate that matches the module instrumentation rate, but is expected to continue on a just-in-time schedule.

David G. Underwood (Argonne National Lab.)

At Argonne we completed module ANL 30. We had much more trouble with fibers than usual. By means of the Cs scan, two fibers were found to have severe damage at locations inside the profiles. These were replaced. The damage must have occurred before the fibers were inserted into profiles.

Also, 5 fibers had very low light output. These were all "A" fibers in long profiles. There is some correlation of the low output with faint marks on the fibers in the area in which they would be inside the asperin tube. These marks may be from the fiber-stuffing machine, or may be from the original fiber production. There is also a correlation with the pattern of light seen at the end of the fiber when the fiber is illuminated by room light or blue LED.

1.4.3 Readout

1.4.3.1 PMT Block

1.4.3.1.3 Production 	Steven Errede (University Illinois-Urbana-Champaign)

We continued with setting up/testing/debugging Step2 hardware/electronics, while waiting for the Step1 reference grid to arrive. Since it was significantly delayed, we instead commenced with Step1 testing of Batch 5 Hamamatsu R-7877 PMTs, at the end of May. The reference grid finally arrived on the last day in May.

1.4.3.2 Front-end 3-in-1 Card

1.4.3.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 3-In-1 Card Test 50% Complete | 1-Jun-01 | -- | 15-Jun-01 | Delayed (See #1) |
| 3-In-1 Card Fab 100% Complete | 16-Jul-01 | 16-Jul-01 | 31-May-01 | Completed |

Note #1  Based on where we are now and the current rate of completion, a two week delay is expected in this milestone. It should be noted that this has no impact on the overall TileCal progress.

James Pilcher (University Of Chicago)

In May we 398 3-in-1 cards to bring the total to 10,600 cards which is 100% of the order. Invoices for these were received and paid in May. The card assembly process is complete.

In May we completed burn-in and testing and shipped to CERN 1600 pieces to bring this total to 4879 or 46% of the total. The monthly average over the 7-month period since burn-in and testing began is now up to 697 cards per month and our most recent 3 month running average is 930 per month. Our original estimates were for 867 per month. Thus our current throughput is above the expected rate and the long-term average will continue to climb slowly.

1.4.3.3 Front-end Motherboards

1.4.3.3.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| MB Card Fab 10% Complete | 29-Jan-01 | -- | 30-Jun-01 | Delayed (See #1) |
| MB Card Fab 25% Complete | 12-Feb-01 | -- | 31-Jul-01 | Delayed (See #2) |
| MB Card Fab 50% Complete | 28-Feb-01 | -- | 31-Jul-01 | Delayed (See #3) |
| MB Card Test 10% Complete | 1-Mar-01 | -- | 31-Jul-01 | Delayed (See #4) |
| MB Card Fab 100% Complete | 6-Apr-01 | -- | 31-Aug-01 | Delayed (See #5) |
| MB Card Test 25% Complete | 1-May-01 | -- | 1-Oct-01 | Delayed (See #6) |
| MB Card Test 50% Complete | 1-Aug-01 | -- | 30-Nov-01 | Delayed (See #7) |

Note #1-7  On track for current forecast.

James Pilcher (University Of Chicago)

In May, based on our prodding, we received a detailed delivery schedule from the assembly firm which calls for volume deliveries to start in June. At the end of May the number of production board-sets received remains at 5 (2% of total).

[NOTE: At the time of writing in mid-June, volume deliveries have in fact begun and we are at 12% of the total.]

1.4.3.6 Read System Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Test BM Calib of 4 Prod. Modls. | 1-Oct-01 | -- | 1-Oct-01 | On Schedule |

James Pilcher (University Of Chicago)

TileCal is on schedule to do test beam calibration of 2 production barrel modules and 4 production extended barrel modules this summer. Materials for the electronics drawers have been provided to Clermont Ferrand for their integration work.

1.4.4 Intermediate Tile Calorimeter

1.4.4.1 Gap Submodules

1.4.4.1.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Scintillator procurement | 1-Oct-00 | 1-Jul-01 | 1-Aug-01 | Delayed (See #1) |
| Start Scintillator Assembly | 1-Dec-00 | 1-Aug-01 | 1-Sep-01 | Delayed (See #2) |
| Ship submodules 33-36 to ANL | 5-Mar-01 | -- | 15-May-01 | Completed |
| Ship submodules 37-40 to ANL | 11-Jun-01 | -- | 11-Aug-01 | Delayed (See #3) |
| Ship submodules 37-40 to BCN | 18-Jun-01 | -- | 18-Jun-01 | On Schedule |
| Ship submodules 41-44 to ANL | 27-Aug-01 | -- | 27-Aug-01 | On Schedule |
| Ship submodules 41-44 to BCN | 3-Sep-01 | -- | 3-Sep-01 | On Schedule |

Note #1  Prototypes of the ITC extension scintillators were tested at the CERN test beam last summer. Based on the test beam experience, we have made final modifications to the scintillator design. Procurement will follow as soon as final drawings are approved, and funding to buy extension scintillators is available at MSU.

Note #2  Prototypes of the ITC extension scintillators were tested at the CERN test beam last summer. Based on the test beam experience, we have made final modifications to the scintillator design. Assembly will follow as soon as funding to buy extension scintillators are available at MSU.

Note #3  Due to delayed startup of production in 1999, we are 2 months behind original schedule. There is no impact on module production.

Kaushik De (University Of Texas At Arlington)

Two submodules were shipped to Argonne in May. Two more were shipped to Barcelona. One of these was the first special ITC submodule. The production of these specials is progressing smoothly. Since these specials require part of the ITC to be truncated, we have successfully made a special out of an old rejected ITC0025 by cutting it down!

We received 250 PMTs and the calibration Grid - both in May. PMT testing has now started at UTA. The first results were shown during the ATLAS Tile week at CERN in May. We plan to finish Phase I testing of these 250 PMTs in June.

1.4.4.2 Cryostat Scintillators

1.4.4.2.3 Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Scintillator procurement | 1-Dec-00 | -- | 1-Dec-01 | Delayed (See #1) |
| Start Scintillator Assembly | 7-Sep-01 | -- | 7-Sep-01 | On Schedule |
| Management Contingency Go-Ahead | 1-Oct-01 | -- | 1-Oct-01 | On Schedule |

Note #1  Scintillator purchase and production of the ITC crack scintillators is delayed pending the decision to authorize this part of the project that was included in the management contingency fund. That decision is scheduled for 1 Oct. 01. Funding for the mechanical components was approved in Feb. 01, and those components will be purchase in FY 01.

Robert Miller (Michigan State University)

Assembly of the clear ITC fibers into the guide plates for the special EB modules continued at MSU in May. The design of the ITC crack scintillator was reviewed and we have decided to reduce the thickness of the Aluminum cover to allow ourselves more tolerance on the 8 mm thickness.

1.5 MUON

Milestones with changed forecast dates:

| 1.5.4.4.1 CSC1 |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| 16 Chambers Complete | 2-Oct-01 | 2-Oct-01 | 30-Apr-02 | Delayed (See #1) |
| Note #1 Please see Note #1. |

| 1.5.4.5 CSC Support Structure |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Start Support Structures Construction | 3-Jan-01 | 3-May-01 | 3-Dec-01 | Delayed (See #1) |
| Note #1 The small wheel fabrication is expected to be launched by the end of the year. The contract and follow-up will be CERN responsibility. |

| 1.5.7.3.3 Series Production Precision Tooling |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Finish Series Production Tooling | 1-Feb-01 | 15-May-01 | 15-Jun-01 | Delayed (See #1) |
| Note #1 All parts are complete for the next series chambers except the gluing of the Bessel bridges. This will be done at HU HEPL after the granite table is free. All BMC tooling will be delivered to Harvard by June 15 - at time of need. |
| 1.5.7.3.11 BMC Chamber Assembly Station |
| Milestone | Baseline | Previous | Forecast | Status |
| EIS1 tooling drawings delivered to BMC | 15-Apr-01 | 15-May-01 | 1-Jun-01 | Delayed (See #1) |
| EIS1 Drawings available | 15-Apr-01 | 15-May-01 | 1-Jun-01 | Delayed (See #2) |
| Note #1 All Brandeis drawings delivered. Sp.Fr Jigging design delayed. Note #2 Brandeis and Engineering Dept. deliver drawings to BMC site. EIS1 drawings are waiting the final determination of the global alignment fixture. This is an integration issue with the support structure, chamber design and the alignment system. |

| 1.5.9.2.1 Signal Hedgehog 3X8 |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Hedgehog PCB Certified | 30-Aug-00 | 1-Jul-01 | 1-Aug-01 | Delayed (See #1) |
| Note #1 Delayed to consider design changes: shortening, coating change. Also the HV capacitor vendor selected is unacceptable to CERN; we must evaluate other vendors and choose a replacement. |

| 1.5.11.1.1 Design |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| System Critical Design Review | 2-Oct-01 | 2-Oct-01 | 1-Dec-01 | Delayed (See #1) |
| Preamp/Shaper Final Design Review | 2-Oct-01 | 2-Oct-01 | 1-Dec-01 | Delayed (See #2) |
| Note #1-2 Delayed to allow us to verify design modifications to preamp/shaper for yield enhancement, reduced crosstalk, and improved overload recovery.. |

| 1.5.11.4.1 Sparsifier Design |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Sparsifier Prelim Design Review | 2-Mar-01 | 15-Jun-01 | 30-May-01 | Completed (See #1) |
| Note #1 Held jointly with ROD PDR on 30-May-01. |

| 1.5.11.5.1 ROD design |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| RODs Prelim Design Review | 31-Oct-00 | 15-Jun-01 | 30-May-01 | Completed (See #1) |
| Note #1 Held jointly with Sparsifier PDR on 30-May-01. |

| 1.5.12.1.3 Multi-Point System (BCAM) |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Design Compete for H8 version of the BCAM | 31-Jan-01 | 1-Jun-01 | 31-May-01 | Completed |

| 1.5.12.1.5 DAQ |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Complete design of H8 alignment DAQ hardware. | 1-Apr-01 | 1-Jun-01 | 30-Jun-01 | Delayed (See #1) |
| Note #1 Responding to the moves of the Big and Small wheel has drained resources needed to complete this job. |

| 1.5.12.4.5 EIS1 (Boston) |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Ship to Site | 16-Feb-01 | 1-Jun-01 | 15-Jun-01 | Delayed (See #1) |
| Note #1 The latest MDT production schedule has shifted the delivery date of the inplane system to Jun 1, 2001. Delays in shop schedules have delayed this item about 2 weeks. |

| 1.5.12.4.17 EMS2 (Seattle) |
| --- |
| Milestone | Baseline | Previous | Forecast | Status |
| Ship to Site | 23-Jan-01 | 1-Jun-01 | 15-Jun-01 | Delayed (See #1) |
| Note #1 The latest MDT production schedule has shifted the delivery date of the inplane system to Jun 1, 2001. Delays in shop schedules have delayed this item about 2 weeks. |

1.5.4 CSC Chambers

1.5.4.2 Tooling

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| QA Systems Complete | 31-Jul-00 | -- | 31-May-01 | Completed |

1.5.4.4 CSC Construction

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Chamber Production | 1-Mar-01 | -- | 1-Sep-01 | Delayed (See #1) |

Note #1  Start of production will likely slip further pending completion of the work on documentation, procurement specification, and other open issues identified during the November 27 PRR.

1.5.4.4.1 CSC1

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 4 Chambers Complete | 1-May-01 | -- | 1-Dec-01 | Delayed (See #1) |
| 16 Chambers Complete | 2-Oct-01 | 2-Oct-01 | 30-Apr-02 | Delayed (See #2) |

Note #1-2  This milestone follows the delay in start of construction, now scheduled for September 1.

1.5.4.5 CSC Support Structure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Support Structures Construction | 3-Jan-01 | 3-May-01 | 3-Dec-01 | Delayed (See #1) |

Note #1  The small wheel fabrication is expected to be launched by the end of the year. The contract and follow-up will be CERN responsibility.

1.5.7 MDT Chamber Production

1.5.7.1 Engineering Management

1.5.7.1.1 Chamber Integration Drawings

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Chamber Integration Drawings | 1-Jul-01 | -- | 1-Oct-01 | Delayed (See #1) |
| Chamber Integration Drawings | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |
| Chamber Integration Drawings | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |

Note #1  The drawing schedule is ahead of need.

Richard Coco (MIT)

Chamber Integration drawings for the next three chambers in the US MDT construction sequence - Series 2 - EIS1 (BMC);EMS4(UM) and EMS2(UW) are in process.

The Series 1 top level chamber assembly drawings for EIL1, EMS5 and EML2 were posted to the CERN drawing directory. CDD assigned drawing numbers are:

ATLMMP_0021 EIL1 - Side A

ATLMMP_0022 EIL1 - Side C

ATLMMS_0041 EMS5 - Side A

ATLMMS_0042 EMS5 - Side C

ATLMMT_0024 EML2 - Side A

ATLMMT_0034 EML2 - Side C

1.5.7.1.2 Engineering Documentation 	Richard Coco (MIT)

Engineering documentation continues to focus on the next series of chambers to be assembled, top chamber assembly drawings for EIS1; EMS4 and EMS2.

The drawings for the 4x6x14Deg; 3x8x14 Deg and 3x8x8.5 Deg faraday cages have been completed. Work is in process to complete the final 4x6x8.5Deg FC design during the next reporting period. Effort will then focus on completing the final mezz card box and H/V power feed box designs.

Type 3 gas bar drawings have been completed for the EIS1, EMS4 and EMS2 chambers.

1.5.7.1.4 QA/QC Engineering Support 	Richard Coco (MIT)

General engineering support is provided to chamber parts procurement and production QA/QC activities as required.

1.5.7.1.5 Project Engineering 	Richard Coco (MIT)

Project engineering activities include supervision of: engineering design and documentation, parts procurement and completion of cost and schedule studies as directed by the program manager.

Activities in early May focused on the PAR review meeting held at Harvard HEPL on 5/4 and 5/5/01.

1.5.7.2 Design of Chambers and Tooling

1.5.7.2.1 Faraday Cages

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Finished Faraday Cage Designs | 21-Dec-00 | -- | 22-Aug-01 | Delayed (See #1) |

Note #1  EIL1 is complete and parts have been made. The 3 layer designs of the base plates are finished and have been sent to vendor for production quote and prototype.

Richard Coco (MIT)

The Faraday Cage design was completed in May for the 3x8x8.5 Deg and 3x8x14 Deg chambers. Much of the effort focused on providing a power distribution box on the H/V side of the chamber. This had not been requested to be part of the initial FC design.

The 4x6x14 Deg FC design completed in April was revised to include the modification to correct these problems.

Efforts will next focus on the final FC design, that for the 4x6x8.5Deg chambers.

The evaluation of the 4x6x14 Deg FC on one of the completed EIL1 chambers found several minor design problems which have been corrected> These corrections were also made to the 3x8 FC drawings.

1.5.7.2.2 Gas System

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Finish Gas System Design | 7-Jun-01 | -- | 7-Jun-01 | On Schedule |

Krzysztof Sliwa (Tufts University)

An initial set of six Noryll gas blocks, produced at the end of April, was submitted to BMC for inspection and testing of the matchup to gas values. The pieces were found to be properly machined and Tufts was given approval to proceed with mass production near the of the month. A review of all drawings for these pieces was carried out by L. McMaster; in consultation with Dick Coco.  A few minor tuneups were discussed and approved. The setup for mass production of gas blocks was ready in the Tufts shop on June 1st, 2001. The production manufacture of 480 pieces will require approximately five weeks.

Richard Coco (MIT)

Drawings were completed for the new Type 3 gas manifold bars for the next series of chambers, EIS1, EMS4 and EMS2. The Noryl gas block design was modified to improve machining. Preliminary layouts of the gas distribution tubing, which supply the gas from the Noryl gas block to each gas manifold bar, were initiated.

1.5.7.2.3 Spacer Farme Design 	Henry Lubatti (University of Washington)

Colin Daly began design and analysis of the EIL2/3 spacer frame.

1.5.7.2.4 Chamber Analysis

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Finish FEA Modeling | 30-Aug-01 | -- | 30-Aug-01 | On Schedule |

Henry Lubatti (University of Washington)

Colin Daly continued his work on thermal analysis of MDT chambers.

1.5.7.2.5 design of Special Chamber Tooling

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Finish all Special Chamber Tooling | 27-Sep-01 | -- | 27-Sep-01 | Delayed (See #1) |

Note #1  Design of special chamber tooling is delayed. Much integration work needs to be done to finish this.

1.5.7.3 Tooling

1.5.7.3.1 Module 0-Precision Tooling

1.5.7.3.3 Series Production Precision Tooling

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Finish Series Production Tooling | 1-Feb-01 | 15-May-01 | 15-Jun-01 | Delayed (See #1) |

Note #1  All parts are complete for the next series chambers except the gluing of the Bessel bridges. This will be done at HU HEPL after the granite table is free. All BMC tooling will be delivered to Harvard by June 15 - at time of need.

1.5.7.3.5 BMC Tube Assembly Station 	Frank Taylor (MIT)

The BMC tube assembly station continues to operate. Tubes for EIS1 are now being fabricated and tested. All tube parameters are within nominal ranges but an investigation of the details of the wire tension measurement is underway. The tube rejection fraction is about 2.3%. The station is a collaboration of personnel from Brandeis, Tufts and MIT.

1.5.7.3.8 BMC Tube Test Station 	Frank Taylor (MIT)

The BMC tube test station continues to operate. EIS1 tubes (BMC series 2) are being fabricated and checked. Good throughput of the tube leak testing is maintained by the Brandeis Schublade which is able to certify 24 tubes at once. A few leaky tubes were recently encountered. One has a definite pinhole in the tube wall. Examination by microscope reveals an inclusion in the die penetrated the tube wall. Sample testing of the wire position is now the standard operating procedure. The tube test station is a collaboration of personnel from Brandeis, Harvard, MIT, and Tufts.

1.5.7.3.11 BMC Chamber Assembly Station

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| EIS1 Drawings available | 15-Apr-01 | 15-May-01 | 1-Jun-01 | Delayed (See #1) |
| EIS1 tooling drawings delivered to BMC | 15-Apr-01 | 15-May-01 | 1-Jun-01 | Delayed (See #2) |
| EIS1 tooling parts delivered to BMC assembly group | 15-May-01 | -- | 10-Jun-01 | Delayed (See #3) |
| Start Retooling for EIS1 | 14-Jun-01 | -- | 14-Jun-01 | See Note #4 |
| Start EIS1 Production | 10-Jul-01 | -- | 10-Jul-01 | See Note #5 |

Note #1  Brandeis and Engineering Dept. deliver drawings to BMC site. EIS1 drawings are waiting the final determination of the global alignment fixture. This is an integration issue with the support structure, chamber design and the alignment system.

Note #2  All Brandeis drawings delivered. Sp.Fr Jigging design delayed.

Note #3  Due one month after tooling drawings delivery. As of 5/25 only the approved Brandeis tooling drawings received by the BMC HU shop. The productions started on May 10. On May 25, HU received additional jobs which originally were assigned to other places.

Note #4  Pending tooling parts and drawings delivery

Note #5  Three weeks after Start Retooling. Pending chamber drawings delivery.

Alex Marin (Boston University)

See the updated 5 milestones for tooling and EIS1 start of production. (Ahlen, Hurst, Haggerdy, Hennessy, Sal, Sansone, Marin)

1.5.7.3.14 BMC Chamber Test Station 	Alex Marin (Boston University)

Cosmic Ray Test Stand: (Steve Ahlen)

Tracking resolution of 80 microns and single tube efficiencies of 97% have been obtained with 93-7 Ar-CO2 at 3 bar, 3080 volts, and threshold at 20 electrons. Early difficulties with AMT-1 and CSM-0 have been resolved by proper tuning of mezzanine card and CSM-0 parameters. Currently using an acquisition program written in C using NI-VXI calls that includes zero suppression for scintillator QDC and TDC data. The acquisition program runs well, with no problems other than buffer errors for scintillator and CSM-0 every few thousand events due to noise. Analysis programs being developed by Ahlen and students Michael Ide and Daniel Sherman to deal with high statistics data sets (20 million events per day) for refined studies of Mod-0 performance.

Gas Test Room (Steve Ahlen)

Students Dan Hoak and Paula Brock working with Ahlen to build gas test system to check for leaks in chambers. Differential manometers, thermometers and pressure transducers are read out by 15 bit Kinetic Systems scanning ADC with LabView/Mac system. Plumbing and monitoring/analysis programs will be completed in June.

1.5.7.5 Chamber Handling and Shipping Containers

1.5.7.5.2 Chamber Shipping Containers 	Richard Coco (MIT)

The design of the next shipping box for the BMC Series 3 chamber EIS2 will be re-worked to allow for removal of the boxer sides to allow installation of services or checkout of electronics without having to removing the chamber from the shipping crate.

1.5.7.6 Common Procurement

1.5.7.6.1 Procurement of Tubes 	Tom Fries (Harvard University)

All 3 US assembly sites have received the 1st & 2nd series tubes. Additionally, batch Nos. 73 & 84 are being prepared at Menziken for delivery to BMC & UW respectively.

1.5.7.6.2 Procurement of Wire 	Tom Fries (Harvard University)

No additional wire was received during this period. There is enough on hand for many months' production requirements.

1.5.7.6.3 Procurement of Endplugs 	Tom Fries (Harvard University)

4,600 NIEF Endplugs were received from CERN and distributed among the 3 US sites. Additionally, the final machining of the 10,000 piece MPI-style Endplugs commenced. This will provide a 6 week buffer inventory once they arrive during June.

1.5.7.6.4 Procurement of Faraday Cage 	Tom Fries (Harvard University)

The balance of the 16-chamber EIL-1 Box-On-Box order arrived at BMC during the 1st week of May. By month's end, 2 orders for 16 chambers each of EMS & EML were on-hold pending final changes to the engineering drawings.

1.5.7.6.5 Procurement of Gas Supply System 	Tom Fries (Harvard University)

Tubeletts:

The domestic supplier (ATB) began shipping production quantities and by month's end had shipped about 75% of the order. The European supplier (Heim) was finishing up the tooling. They plan to complete tooling in June and will then begin series production of tubeletts.

Retainers, Tubelett:

The European supplier (Walter Hugin) of the 8.5 & 14 degree molded plastic retainers for the Type-III gas bars expects to complete final tooling in June.

Extrusion for Gas Bars:

The extrusion tooling for the Type-III bar design was approved. An extrusion order will be placed in early June with delivery expected in early July. The order will be drop-shipped to UW for fabrication.

1.5.7.6.6 Procurement of Spacer Frame + Attachment 	Henry Lubatti (University of Washington)

Josh Wang finished series 2 (EIS1, EMS2 and EMS4) spacer frame part-drawings and submitted them for checking, began the series 3 spacer frame part-drawings, and did some preliminary design of the EIL2-3 spacer frame top establish the material-order requirement.

1.5.7.7 BMC Chamber Construction 104

1.5.7.7.1 EIL 1 Series (WBS 1.5.7.7.1)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| End of EIL1 series production | 14-Jun-01 | -- | 14-Jun-01 | On Schedule |

Frank Taylor (MIT)

All the tubes for EIL1 have been made and are delivered to the chamber makers at the BMC.

Alex Marin (Boston University)

Mod 15 completed as of May 26. See milestone.  (Ahlen, Hurst, Haggerdy, Hennessy, Sal, Sansone, Marin)

1.5.7.7.2 EIS1 series (WBS 1.5.7.7.2) 	Frank Taylor (MIT)

Over a 1,000 tubes for EIS1 have been made. For the complete EIS1 series about 5,376 tubes are required.

Alex Marin (Boston University)

See 1.5.7.3.11 five milestones, containing preparation and schedule for EIS1 production start. (Ahlen, Hurst, Haggerdy, Hennessy, Sal, Sansone, Marin)

1.5.7.8 WBS 1.5.7.8 Michigan Chamber Construction 104

1.5.7.8.1 EMS5 Series (WBS 1.5.7.8.1) 	Ed Diehl (University of Michigan)

We have completed 15 base EMS5 chambers in May, and will complete the 16th and final EMS5 chamber in the first week of June. We finished EMS5 tube production and started changing the wiring room for EMS4 tube production.

We have decided to set up a cosmic-ray stand in the truck bay which is the only available space for it. We'll use the stand to test a complete chamber with full electronics readout.

We had a few small glitches in production. NIEF (endplug maker) recently switched to packaging endplugs in black plastic holders, which are superior to the cardboard which had been used (which left a lot of dust in the endplugs). However, it happens that some of the black plastic rubs on the endplugs and is hard to clean off. Fortunately, the plastic seems to be non-conductive and so it does not seem to cause problems.

We still had some dark current problems. Nearly all were fixed by reverse HV, and long burn-in times.

We did a final BCAL measurement of the comb positions for EMS5. We found the comb positions had been stable to +- 10 microns for the entire EMS5 run.

1.5.7.8.2 EMS4 Series (WBS 1.5.7.8.2) 	Ed Diehl (University of Michigan)

We continued preparing for EMS4 production. We've upgraded most of our computers to Windows2000 which makes them less crash-prone, but run more slowly due to OS bloat. Most of our production programs have been revised for EMS4.

1.5.7.9 WBS 1.5.7.9 Seattle Chamber Construction 96

1.5.7.9.1 EML2 Series (WBS 1.5.7.9.1) 	Henry Lubatti (University of Washington)

We completed 683 tubes in May, which completes the tubes needed for EML2 chambers. We began modifications to tube assembly line needed for next series of chambers. Upgraded all three PC systems used in Tube Assembly and Tube QA/QC from Windows NT to Windows 2000.

1.5.7.9.1.2 Seattle Series Chamber Assembly	Paul Mockett (University of Washington)

We completed the assembly of EML.2C7 to 2C11 (series numbers 12, 13, 14) during April. Chamber production is currently limited by the rate of tube production.

1.5.7.9.1.3 Ship/Store

We have 7 chambers stored at an expeditor’s warehouse. Module 2 has been returned from CERN following the X-Tomo.

1.5.8 MDT Supports

1.5.8.1 Mechanical design

1.5.8.1.1 Kinematic Mounts 	Henry Lubatti (University of Washington)

Colin Daly attended the PAR review meeting in Boston and presented the Forward chamber mount design and production status.

1.5.8.1.3 Integ with Support Structure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| (SM Wheel) CERN Design/FEA Complete | 15-Jul-00 | -- | 1-Dec-01 | Delayed (See #1) |
| (Big Wheel) CERN Design/FEA Complete | 1-Feb-01 | -- | 15-Dec-01 | Delayed (See #2) |
| 50% Complete | 15-Feb-01 | -- | 15-Jul-01 | Delayed (See #3) |
| 50% Complete | 1-Aug-01 | -- | 1-Aug-01 | On Schedule |

Note #1  A large fraction of this work has been completed, but as we depend on CERN for the detailed small wheel design from CERN and others for alignment bar and plumbing information we have a delay. Some small progress was made in April. We forecast that this will not be completed until December 4, 2001.

Note #2  Because we depend on CERN for the detailed big wheel design and others for alignment bar and plumbing information we have a delay. We forecast that this will not be completed until March 15,2002.

Note #3  For reasons given in the delayed small/big wheel the 50% complete point will not be reached until about July 15, 2001.

Henry Lubatti (University of Washington)

Colin Daly attended the Big Wheel Final Design Review at CERN.  Colin Daly continued design work on integration of the chamber mounts with the support structures. Specifically the integration of the mount strut design with the Big and Small wheel structures and chamber support points.

1.5.9 MDT Electronics

1.5.9.1 Mezzanine Card

1.5.9.1.1 MDT-ASD

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| ASD PRR | 19-Oct-01 | -- | 19-Oct-01 | On Schedule |

1.5.9.2 Hedgehog Cards

1.5.9.2.1 Signal Hedgehog 3X8

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Hedgehog PCB Certified | 30-Aug-00 | 1-Jul-01 | 1-Aug-01 | Delayed (See #1) |
| Hedgehog Production Complete | 28-Feb-01 | -- | 31-Dec-02 | Delayed (See #2) |

Note #1  Delayed to consider design changes: shortening, coating change. Also the HV capacitor vendor selected is unacceptable to CERN; we must evaluate other vendors and choose a replacement.

Note #2  Production will most likely now take place at CERN starting in the last quarter of 2001. The first production quantities should be available at the end of 2001. Production will continue during 2002 in parallel with chamber building.

1.5.9.4 Chamber Service Module

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| CSM-1 Prototype | 1-Sep-00 | -- | 1-Jun-02 | Delayed (See #1) |

Note #1  The scope of the CSM-1 has recently changes to a simpler, more robust design. As a result the completion date of the first prototype has moved to spring 02. Work on the design for this more ambitious design is progressing.

Jay Chapman (University of Michigan)

Progress has been made on the five major components of the CSM-1. Each is described below:

a) The main multiplexing task of the CSM-1 has been compressed from 4 FPGAs into one using a scheme of clock phase sampling to remove the need for many independent clock networks, using a large fine pitch ball grid array chip, and using a LVDS compatible FPGA from Xilinx, the XCVnnnnE series. Work to compress the FPGA code into a single chip is underway.

b) Prototype testing of the optical fiber output to the MROD will be done using the ODIN Duplex implementation of S-Link to expedite the project although we expect to use an S-Link core module within our own FPGA in the final design. The final design will use a Simplex optical channel so we must recode the FPGA code from it current Duplex implementation to the Simplex form prior to the final CSM development. Work is being carried out in parallel to do this Duplex to Simplex conversion.

c) The CSM-1 requires clocking and event triggering. The initial prototype, the CSM-0, is configured to use an FPGA for emulation of the TTC system. For the CSM-1 design the Trigger, Timing, and Control will be based on the CERN developed TTC system. Our transition from the internal simulation of the trigger and timing to the externally generated functions implies and integration of the CERN chip into the module and the software integration of the TTCvi module into our environment. This work has begun and will continue throughout year 2001.

d) The initialization of the ASD/TDC mezzanine cards is done via JTAG protocol which in the case of the CSM-0 is built into the VME functions of the CSM-0 module. In the CSM-1 no VME connections is available. The CSM-0 will use an opto-isolated JTAG function as will the final CSM. However, the final CSM will have a DCS connection and a CAN bus interface to provide the programming for the JTAG. To make progress toward this final goal, the opto-isolated JTAG will be driven from a commercial module.

e) The CSM will interconnect to the ASD/TDC modules via shielded ribbon cables that leave the Faraday cages and converge at the spacer place of the MDT. At this location they will attach to a passive interconnect on which the active CSM will reside. This interconnect board is designed. To make use of the current CSM-0 with the new interconnect board, an adapter board will be constructed with the same circuit design as the adapter currently in use with the CSM-0, but designed to attach to the passive interconnect. Following use with the CSM-0, a simple replacement of this new adapter with the CSM-1 will convert a chamber from CSM-0 readout to the MROD readout via the CSM-1.

1.5.9.5 Detector Control System 	Paul Mockett (University of Washington)

1) OPC User Document has gone through initial revision by author and programmer for consistency and correctness. Will give to 3rd person for installation test.

2) As for PVSS not allowing numerical arrays, one method of getting around this is to take our arrays of unsigned chars and converting it to an array of characters and thus creating a text string - which is supported by PVSS in the current version.

3) Our 2 EPC-1316 VME processors have arrived and after some questions about ethernet drivers, the systems were both configured for Windows2000. Both systems function correctly. A third board was acquired and setup in the Chamber Assembly room.

4) The EPC-15 in the Chamber assembly room was replaced with an EPC-1316. The EPC-15 was moved to the Chamber test area to help in the construction of Spacer supports, and installation of the In-Plane Rasnik system on the supports.

5) A ccd multiplexer failed, and when fuses were replaced, an IC exploded. The board will be returned to Brandeis to be evaluated and repaired/replaced.

6) An LED multiplexer failed as well. This was due to the output being shorted when a tube tray accidentally bumped it. The board is also going to be returned to Brandeis for evaluation and repair/replacement. The location of the LED multiplexer has been moved to avoid such a future accident.

7) The new EPC-1316's have been fully tested with the DAWN VME crates. Once the backplane had been jumpered to allow the bus-grant line to be passed to all card, the EPC-1316's functioned as expected with the 2004 ccd driver card. While one system will be used for the BCAM development, the second system will be used for CSM software development and also for testing Linux with the VME hardware.

8) 2 bases have been constructed for the BCAM test station. They allow for alignment of the BCAM ccd and a small block with 3 - 1mm holes for LED's. Used the current generation of CCD driver to implement a test station. The original software developed here and at CERN works fine. Also tested with the DIM software under development by Joe Rothberg.

9) Started to convert the LabWindows/CVI software developed by the CSM people (J. Chapman, et al) to work on our embedded VME system. Need to convert the NI-VXI calls to EPConnect calls. This looks feasible.

10) Have a student now working on database entries for the Chamber assembly data. He is looking at both the real time data, and the data previously taken. He estimates middle to late May for having data into the database.

11) Joe Rothberg chaired a session on controls read out at the H8 workshop held at CERN in early April. He also presented a talk entitled "Control Systems and Read Out of Alignment Devices for H8.

12) Rothberg continues his work on the controls read out using PVASS by utilizing the DIM connectivity protocol. DIM is a Linux based alternative to Microsoft OPC.

1.5.11 CSC Electronics

1.5.11.1 ASM1 Boards

1.5.11.1.1 Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Preamp/Shaper Final Design Review | 2-Oct-01 | 2-Oct-01 | 1-Dec-01 | Delayed (See #1) |
| System Critical Design Review | 2-Oct-01 | 2-Oct-01 | 1-Dec-01 | Delayed (See #2) |

Note #1-2  Delayed to allow us to verify design modifications to preamp/shaper for yield enhancement, reduced crosstalk, and improved overload recovery.

Paul O'Connor (BNL)

Work continued on modifying the IC50 preamp/shaper design for improved yield, reduced input impedance, faster overload recovery, and reduced baseline dispersion. Chip layout 70% done. We changed the chip from a 12 + 4 channel configuration (active + reference) to 24 + 1 to save layout area. ASM 1 board prototype and rigid-flex cable in fabrication in house.

1.5.11.2 ASM II Board

1.5.11.2.1 ASM II Board design 	Paul O'Connor (BNL)

ASM-2b 192-channel prototype board design in progress. Schematics will be completed in mid June, then go to layout. Concept for ASIC MUX will be tested by using small FPGA on ASM-2b. Summer student to start on June 3, will be assigned to help with digital section of ASM.

1.5.11.3 Low Voltage power, Cooling and Cabling

1.5.11.3.1 Design, Identification and Specification 	Paul O'Connor (BNL)

Going for quote on cooling design. Recalculated power and cabling requirements based on 25 + 12 m cable run from power supplies on UX15 floor, assumed regulator dropout.

1.5.11.4 Sparsifiers

1.5.11.4.1 Sparsifier Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Sparsifier Prelim Design Review | 2-Mar-01 | 15-Jun-01 | 30-May-01 | Completed (See #1) |

Note #1  Held jointly with ROD PDR on 30-May-01.

1.5.11.4.2 Sparsifier Prototype

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Sparsifier 1st Proto in Hand | 1-Aug-01 | -- | 15-Jul-01 | On Schedule (See #1) |

Note #1  Generic processing unit prototype complete and tested. Motherboard in layout.

1.5.11.5 ROD's

1.5.11.5.1 ROD design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| RODs Prelim Design Review | 31-Oct-00 | 15-Jun-01 | 30-May-01 | Completed (See #1) |

Note #1  Held jointly with Sparsifier PDR on 30-May-01.

David Stoker (University of California Irvine)

During May we continued coding of the SPU (Sparsifier Processing Unit) C and assembly code. Verilog coding of the revised Clock Generation PLD's was finished. We began layout of the ROD motherboard. Other work centered on preparation for the ROD/Sparsifier PDR (preliminary design review) which has held on May 30.

1.5.11.5.2 ROD Prototype

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| RODs 1st Proto in Hand | 2-Apr-01 | -- | 15-Jul-01 | Delayed (See #1) |

Note #1  Generic processing unit prototype complete and tested. Motherboard in layout.

1.5.11.7 Software

1.5.11.7.1 Software design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| S/W Conceptual Design Review | 2-May-01 | -- | 15-Jul-01 | Delayed (See #1) |

Note #1  Development of code external to ROD and documentation not ready for review.

1.5.12 Global Alignment System 	Jim Bensinger (Brandeis University)

This month work has revolve around the following:

(1) Getting ready for the next round of chamber production. This includes preparations for producing inplane and proximity mounting pieces for next round of chamber production.

(2) The Big Wheel review. This included continuing work responding to the 399 mm move and the new structural design of the wheels.

(3) Getting ready for H8. This includes preparation of layout drawing, work on the phantom chambers, and detailed design of the Version 2 of the DAQ and sensors.

(4) Responding to questions from Technical Coordination.

1.5.12.1 Global Design

1.5.12.1.1 Alignment Bars

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Alignment Bar Design Complete | 30-Mar-01 | -- | 30-Jun-01 | Delayed (See #1) |

Note #1  Due to changes in the big and small wheel positions some of the design work will have to be redone, resulting in several months delay.

Jim Bensinger (Brandeis University)

All the sensors mounts for the H8 bars have at least preliminary designs. This allows final calculations of the positions of the gimbal mounts. Since the gimbals have to be at the effective "Bessel Points" to within 1%, the exact positions of the mounts cannot be known until the complete weight distribution on the bars is known. This has now been established on the long bars. Specifications for the mounting holes have been transmitted to CERN for modification of the H8 chamber supports.

1.5.12.1.2 Proximity Monitors

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Proximity Monitor Design Complete | 29-Sep-00 | -- | 7-Aug-01 | Delayed (See #1) |

Note #1  Delays in H8 and new information from simulation have pushed this item back.

Jim Bensinger (Brandeis University)

The Version 2 design of the sensors was completed. This is a novel design where the readout header board was underneath the optical path and small lens holders which can be positioned over the header. This gives much greater flexibility using the same physical camera size. The extrusions for this device and the mask mounts were ordered.

1.5.12.1.3 Multi-Point System (BCAM)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Design Compete for H8 version of the BCAM | 31-Jan-01 | 1-Jun-01 | 31-May-01 | Completed |

Jim Bensinger (Brandeis University)

The testing of the prototype of Version 2 of the BCAM has been completed. All of the operational features of the BCAM were at or better than expectations and the performance was definitely better the previous version. Some simplifications of the design for manufacturing have been made and the shop drawings detailed. This is now ready to go the shop for H8 production.

The BCAMs that were exposed at the Saclay radiation test facility were returned to Brandeis and tested. The BCAMs received sixty times the ATLAS dose of ionizing radiation and suffered no degradation in performance. A report was written and can be found at

http://www.hep.brandeis.edu/alignment/temporary/ionizing.pdf on the Brandeis server.

1.5.12.1.4 System Design 	Jim Bensinger (Brandeis University)

The 399-mm move of the MDT big wheel and the new design of all the big wheels have made major changes in the layout of the location of the polar and proximity monitors necessary. Moving sensors to accommodate these changes has caused several collisions either with physical objects or with lines of sight that have to be kept clear. This was compounded by the problem of translating files from yet another CAD system (the big wheel design was done in MD5). This work was much more extensive than we anticipated and will not be completed for at least another month. We are preparing a list of changes requested in the design of the Big Wheel for our CERN colleagues. Our preliminary conclusions were presented at the Big Wheel Preliminary Design Review at CERN on May 14 and private discussions for a few days following the review.

1.5.12.1.5 DAQ

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete design of H8 alignment DAQ hardware. | 1-Apr-01 | 1-Jun-01 | 30-Jun-01 | Delayed (See #1) |
| DAQ Design Complete | 28-Sep-01 | -- | 28-Sep-01 | On Schedule |

Note #1  Responding to the moves of the Big and Small wheel has drained resources needed to complete this job.

Jim Bensinger (Brandeis University)

The design of the Version 2 of the DAQ system was completed. A device driver and some headers were sent to the Seattle group for beta testing and they are now fully operational at the University of Washington. This system will be used in H8.

At Brandeis we have built and tested 14 inplane sensor heads, 14 inplane mask heads, and 4 device drivers. This is for distribution of the first set of kits for the inplane system for the second round of MDT chamber construction.

1.5.12.2 Operational Test Stands

1.5.12.2.3 H8 DATCHA

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| H8 Operational | 24-Nov-00 | -- | 30-Jul-01 | Delayed (See #1) |

Note #1  The assembly of support structures and frames at CERN has been slower than expected. We now expect that this will be completed by the end of June 2001. Mounting of alignment devices can only begin when the structural work is complete.

Jim Bensinger (Brandeis University)

All the sensors mounts for the H8 bars have at least preliminary designs. This allows final calculations of the positions of the gimbal mounts. Since the gimbals have to be at the effective "Bessel Points" to within 1%, the exact positions of the mounts cannot be known until the complete weight distribution on the bars is known. This has now been established on the long bars. Specifications for the mounting holes have been transmitted to CERN for modification of the H8 chamber supports.

The testing of the prototype of Version 2 of the BCAM has been completed. All of the operational features of the BCAM were at or better than expectations and the performance was definitely better the previous version. Some simplifications of the design for manufacturing have been made and the shop drawings detailed. This is now ready to go the shop for H8 production.

The design of the Version 2 of the DAQ system was completed. A device driver and some headers were sent to the Seattle group for beta testing and they are now fully operational at the University of Washington. This system will be used in H8.

1.5.12.3 Global System Production

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Align Bar/Prox Monitors PRR | 3-Jan-01 | -- | 31-Oct-01 | Delayed (See #1) |
| Critical System Design Review | 3-Jan-01 | -- | 31-Aug-01 | Delayed (See #2) |

Note #1-2  Delayed due to delays in the construction of H8.

Jim Bensinger (Brandeis University)

The only part of system production that has begun is the part relating to the production of MDT chambers, the inplane system and the camera mounts and mask mounts for the proximity monitors that go on the chambers.

1.5.12.3.1 Alinment Bars

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Bar Production 10% Complete | 1-Oct-01 | -- | 1-Oct-01 | On Schedule |

1.5.12.3.2 Proximity Monitors 	Jim Bensinger (Brandeis University)

All proximity mount components (cameras and mask) needed for the first round of production of MDT chambers have been delivered to the US production sites and Protvino.

1.5.12.4 MDT Inplane Monitors

1.5.12.4.1 Common Items 	Jim Bensinger (Brandeis University)

Almost all of the common parts for the approved MDT chamber production now exists at Brandeis.

1.5.12.4.2 EIL1 (Boston) 	Jim Bensinger (Brandeis University)

The complete set of kits for the first round of production has been delivered to the production site.

1.5.12.4.5 EIS1 (Boston)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Ship to Site | 16-Feb-01 | 1-Jun-01 | 15-Jun-01 | Delayed (See #1) |

Note #1  The latest MDT production schedule has shifted the delivery date of the inplane system to Jun 1, 2001. Delays in shop schedules has delayed this item about 2 weeks.

Jim Bensinger (Brandeis University)

The parts for the EIS1 have been received from Michigan. Because of confusion about the drawings some modifications had to be made at Brandeis. These modifications are in process. The first kit will be distributed to the BMC chamber production facility when modifications are complete.

1.5.12.4.6 EIS2 (Boston)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Ship to Site | 23-Oct-01 | -- | 23-Oct-01 | On Schedule |

1.5.12.4.12 EML2 (Seattle) 	Jim Bensinger (Brandeis University)

The complete set of kits for the first round of production has been delivered to the production site.

1.5.12.4.17 EMS2 (Seattle)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Ship to Site | 23-Jan-01 | 1-Jun-01 | 15-Jun-01 | Delayed (See #1) |

Note #1  The latest MDT production schedule has shifted the delivery date of the inplane system to Jun 1, 2001. Delays in shop schedules has delayed this item about 2 weeks.

Jim Bensinger (Brandeis University)

Drawings for the central mask lens mounts and the mask mounts have been sent to Michigan for manufacture. All other mechanical components are in hand.

1.5.12.4.18 EMS3 (Seattle)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Ship to Site | 7-Sep-01 | -- | 1-Apr-02 | Delayed (See #1) |

Note #1  This chamber is not scheduled to be built until the third round of MDT production.

1.5.12.4.20 EMS5 (Michigan) 	Jim Bensinger (Brandeis University)

The complete set of kits for the first round of production has been delivered to the production site.

The correct name for this WBS item is EMS5 (Michigan)

1.6 TRIGGER

Milestones with changed forecast dates:

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| LVL2 Trigger Prototype Complete | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |

1.6.1 LVL2 SRB

1.6.1.2 SRB Protos

1.6.1.2.1 SRB Protos EDIA 	Robert Blair (Argonne National Lab.)

The 9U prototype RoI Builder is progressing. The general layout of the system was described in last month's report. A requirements document has been circulated for discussion in the group.

1.6.1.2.4 SRB Prototype Travel

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Calo for Integ Study Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |
| Prototype SRB Assy Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |

1.6.2 LVL2 Calorimeter Trg

1.6.2.2 Calo Protos

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Prototype Calo PDR | 31-Mar-01 | -- | 31-Jul-01 | Delayed (See #1) |
| Prototype Calo Assy Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |

Note #1  This PDR as several others has been delayed to conform to the initial review of the Phase 2a prototype. This aligns it with the Atlas wide milestones presented to the LHCC in March.

1.6.3 LVL2 SCT Trg

1.6.3.1 SCT Design

1.6.3.1.1 SCT Design EDIA 	Haimo G. Zobernig (University Of Wisconsin)

The work in May focused on finishing the Performance Evaluation of the Reference Software. Since the Phase 1 Integration Prototype did not attempt to evaluate the performance of any of its components, but just the functionality, a separate performance evaluation of the Reference Software only was undertaken by members of the CERN, RAL and Wisconsin groups. This consisted in carefully attempting to understand the behavior of the Reference Software. To this end, the software was run under well-specified run parameters on small testbeds of 3-6 PC nodes. Three different and complementary tools were used to characterize the behavior of the software. One was a profiling package, called TAU, from LANL (see http://www.acl.lanl.gov/tau). It allowed us to do timing profiles of the multithreaded, dynamically-linked Reference Software at the function/method level. This was used to understand where time is spent in the current implementation and to discover any unexpectedly large time consumers. The use of TAU involved a considerable amount of work to adapt the TAU tool to the Reference Software's environment, and necessitated changes to the RefSW source code because TAU uses a C++ compiler front end (EDG), which is not fully compatible with the compiler used in the Reference Software, g++.

The second tool used was NetLogger from LBL (http://www-didc.lbl.gov/NetLogger). Using NetLogger, we could measure and correlate specific times spent within, and in particular also across applications i.e. inter-node measurements.

Finally, some built-in features of the Reference Software were used to gather timing histograms within each application, with particularly low measurement overheads. The results from using these tools have enabled us to gain a good understanding of the behavior of the Reference Software. They will be presented at the RT2001 Conference in Valencia, Spain, in early June 2001 and have also been submitted there as a contributed paper. This is currently available as

http://bogaerts.home.cern.ch/bogaerts/Hlt/RT2001/rt2001_v8.pdf.

Saul Gonzalez (University Of Wisconsin)

The implementation of the common classes (developed by W. Wiedenmann) will wait until the new HLT software design is finalized. Discussions with the ATLAS offline group - and in particular with the Architecture team - are continuing.

Andrew Lankford (University Of Calif. At Irvine)

Recent UCI activities continued to focus on the interface between TDAQ and front-end electronics. Study of alternative implementations of the ROD/ROB interface continued. A conceptual design was developed for a ROBin (the input and buffering component of the Readout Subsystem (ROS)) that can be mounted directly on each ROD, thus replacing the Readout Link with a standard network connection. This ROBin would be used in a network-based ROS, rather than a VME or PCI bus-based ROS. System issues of such a ROS implementation need further study. Possible Readout Link implementations were discussed with the LArg ROD architecture task force. Issues are bandwidth and cost. These investigations and discussions will continue in June.

1.6.3.1.4 SCT Design Travel

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT for Integ Study Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |

1.6.3.2 SCT Protos

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Prototype SCT PDR | 31-Mar-01 | -- | 31-Jul-01 | Delayed (See #1) |
| Prototype SCT Assy Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |

Note #1  This PDR as several others has been delayed to conform to the initial review of the Phase 2a prototype. This aligns it with the Atlas wide milestones presented to the LHCC in March.

1.6.4 Architecture & LVL2 Global Trigger

1.6.4.1 Arch. Design

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Prototype Project PDR | 31-Mar-01 | -- | 31-Jul-01 | Delayed (See #1) |

Note #1  This PDR as several others has been delayed to conform to the initial review of the Phase 2a prototype. This aligns it with the Atlas wide milestones presented to the LHCC in March.

1.6.4.1.1 Arch. Design EDIA 	Robert Blair (Argonne National Lab.)

Runs on the Argonne 256 node cluster were performed for various size systems. The stability of the jobs (whether they correctly run to completion and/or report results) is not good. Further work is being done to improve this. The results appear to show unusual behavior as the system size rises. This too is being investigated. It may be necessary to significantly revamp the control software to properly use this large cluster.

Maris Abolins (Michigan State University)

Maris Abolins continued his work with Jos Vermeulen et al. on simulation studies of the trigger/daq system using the "paper model" approach. A new intermediate trigger menu was added and updates made to link speeds and processor performance to reflect current realities.

Abolins also served on a committee, chaired by Klaus Pretzl of Bern, to set up guidelines for a "speaker’s committee". This work has been completed and the document will go before the Institutional Board for vote during the T/DAQ workshop in July.

Reiner Hauser’s activities include the following:

1. On the DataCollection software side a simple package was created which allows to use a precompiled installation of the OnlineSW as an 'external package'.

2. A first implementation of the configuration database interface using OKS was written and made available in CVS.

3. A first version of the message passing design document was written and made available on the web.

4. Various discussions on other aspects of data collection took place, most notably the message flow inside the system and possible alterations to the currently accepted "baseline" protocol.

Yuri Ermoline has been asked to contribute to the technical coordination efforts within TDAQ, namely to the ROD coordination in the DIG. This important task involves coordination between ROD designers and external systems like TTC, readout links, etc. LVL2 RODs are included in the scope of that activity.

Andrew Lankford (University Of Calif. At Irvine)

Work resumed with the TDAQ system leaders on project planning for the development and prototyping period preceding the HLT/DAQ/DCS TDR. Steps were taken to address some of the global ATLAS manpower shortfalls in the area of the Data Collection Subsystem. As mentioned in the March report, this subsystem requires a considerable amount of new design work in order to facilitate an appropriate degree of integration of LVL2, EF, and DAQ data flow functionality. Some software issues at the interface of TDAQ with detectors (e.g. data format) and at the interface with Computing (e.g. Event Filter dependencies on offline code) were investigated.

1.6.4.1.3 Arch. Design M&S 	Robert Blair (Argonne National Lab.)

TTC receiver boards were sent for fabrication. When the boards were finished a problem was discovered that requires them to be redone. This still allows time for them to be done prior to the July TDAQ workshop. This would be the first opportunity to use them. They are not critical path items since the previous generation can still be used to synchronize DAQ and Level 2.

1.6.4.1.4 Arch. Design Travel

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Arch Design for Integ Study Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |
| Prototype Project Assy Compl | 30-Sep-01 | -- | 30-Sep-01 | On Schedule |

1.6.4.2 Global Production

1.6.4.2.1 Global Prod Eqmt 	Saul Gonzalez (University Of Wisconsin)

A second meeting of the "Athena suitability task force" was held (led by S.Gonzalez) in May 21st. As identified in the previous meeting, one of the central tasks is the benchmarking of Athena. This benchmarking includes Athena services in order to ensure that there are no 'show-stoppers' in the Athena architecture. During the meeting, Werner Wiedenmann presented some recent results in benchmarking Athena with TAU. He repeated earlier studies performed on StoreGate, which initially gave unacceptable long latencies for registering/retrieving objects from the transient store. Werner found that the initial studies were flawed and that the StoreGate performance was better than initially thought. An agenda (including slides) of this meeting can be found at http://www-wisconsin.cern.ch/~atsaul/HLTAthena Another ongoing effort is in HLT software design. A second cycle of design was recently finished after the review of the HLT SW requirements document and a first cycle. The focus now is in writing a first draft of the Software Design Document.