WBS 1.1.2

ATLAS SCT: Cost & Schedule

US ATLAS DoE/NSF Review

29-Jan/2-Feb-2000

Alex Grillo

U.S. ATLAS E.T.C.

# WBS Summary Cost Estimates

Funding Source:	All	Funding Type:	Project + MC

Institutions:	All

Base	Cont	Cont  	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

WBS	Cost	 %   		Labor	Labor	Matls	Matls	 	Project 	Other

Number	Description	Cost	(k$)	Cost

1.1.2	Silicon Strip System	5812	1581	27	7392	717	890	87	4117	27.6	6.0

1.1.2.1	IC Electronics	3672	983	27	4655	554	61	77	2980	10.6	0.7

1.1.2.1.1	Design	636	51	8	687	537	0	77	21	7.1	0.1

1.1.2.1.2	Development and Prototypes	106	8	7	114	17	0	0	89	0.8	0.0

1.1.2.1.3	Production	2931	925	32	3855	0	61	0	2870	2.8	0.6

1.1.2.2	Hybrids/Cables/Fanouts	973	209	21	1181	76	200	0	697	5.1	3.4

1.1.2.2.1	Design	0	0	0	0	0	0	0	0	0.0	1.6

1.1.2.2.2	Development and prototype 	32	1	3	33	0	0	0	32	0.0	0.1

1.1.2.2.3	Production	941	208	22	1148	76	200	0	665	5.1	1.7

1.1.2.3	Module Assembly and Test	1167	389	33	1555	87	630	10	440	11.9	1.8

1.1.2.3.1	Design of assembly and test 	127	42	33	168	87	40	0	0	1.0	0.7

1.1.2.3.2	Development and prototypes	57	13	24	70	0	50	0	7	0.6	0.0

1.1.2.3.3	Production	983	334	34	1317	0	541	10	433	10.3	1.1

The base cost shown here includes $988k of Management Contingency which is reserved completely in 
1.1.2.1.3 (IC production costs) in FY02.

U.S. ATLAS E.T.C.

# WBS Profile Estimates

Funding Source:	All	Funding Type:	Project

Institutions:	All

WBS	FY 96 	FY 97 	FY 98 	FY 99 	FY 00 	FY 01 	FY 02 	FY 03 	FY 04 	FY 05 	Total

Number	Description	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

1.1.2	Silicon Strip System	0	0	0	0	1101	2537	958	228	0	0	4824

1.1.2.1	IC Electronics	0	0	0	0	626	1759	174	125	0	0	2684

1.1.2.1.1	Design	0	0	0	0	250	131	131	125	0	0	636

1.1.2.1.2	Development and Prototypes	0	0	0	0	106	0	0	0	0	0	106

1.1.2.1.3	Production	0	0	0	0	270	1628	44	0	0	0	1943

1.1.2.2	Hybrids/Cables/Fanouts	0	0	0	0	177	380	383	33	0	0	973

1.1.2.2.1	Design	0	0	0	0	0	0	0	0	0	0	0

1.1.2.2.2	Development and prototype 	0	0	0	0	32	0	0	0	0	0	32

1.1.2.2.3	Production	0	0	0	0	145	380	383	33	0	0	941

1.1.2.3	Module Assembly and Test	0	0	0	0	298	398	401	70	0	0	1167

1.1.2.3.1	Design of assembly and test 	0	0	0	0	127	0	0	0	0	0	127

1.1.2.3.2	Development and prototypes	0	0	0	0	57	0	0	0	0	0	57

1.1.2.3.3	Production	0	0	0	0	114	398	401	70	0	0	983

IC Electronics Costs

The SCT Collaboration has selected as its baseline the single chip solution using the DMILL technology.
(Discussion of this decision will be in the parallel session tomorrow.)

The cost database has been updated to reflect this.  
(i.e. two chip WBS elements replaced with one chip elements).

The production wafer costs assume that listed in the CERN/Temic Frame Contract.
The yield at wafer tests assumes the minimum yield guarantee also listed in the Frame Contract.

The details of this costing were not included in the Cost Book due to the confidentiality agreement between CERN and the wafer foundries.  We have authorization to discuss the details with the DoE reviewers upon agreement to maintain the confidentiality.

The cost model assumes a yield through the assembly, test and installation process of roughly 80%.

Details of the cost model including yields and wafer costs are available in a spreadsheet for backup.

IC Electronics Schedule

Near term milestones:

### Selection of ABCD/DMILL as baseline	24-Feb-2000

Final Design Review of ABCD	06-Mar-2000

Submission of Pre-production fabrication	early Apr-2000

Possible second pre-production fabrication	Jun-2000

Wafers back from foundry	Sep-2000

ICs ready for Module 0	mid Oct-2000

Production milestones:

Production Readiness Review	Feb-2001

Release full production fabrication	Mar-2001

Production fabrication complete	May-2002

Production IC testing complete	Aug-2002

Hybrid & Module Costs

## The SCT Collaboration has recently selected the Kapton technology for the readout hybrid.

The cost estimates in the database and the Cost Book were done assuming the ceramic hybrid technology.

This was viewed by the US to be the more conservative solution from the standpoint of reliability, understanding and cost.

The SCT Collaboration believe the cost of the Kapton hybrid will be approximately 60% that of the ceramic option.

The US has not yet repeated the cost estimate at the level of detailed required for our review.

The new detailed US cost estimate and schedule will be completed by July-2000

Given the current estimates of our collaborators, we do not believe the hybrid costs will exceed those in the current US estimates.

Module costs have been updated in a few areas

Thermal baseboard parts and assembly(now to be done by CERN under formal agreement with ATLAS).

Small changes in tooling/equipment based on experience with prototypes.

However, labor estimates(time) have not changed since baseline. Expect ATLAS and/or US ATLAS review by November-2000.

Hybrid & Module Schedule

Near term milestones:

### Selection of Kapton hybrid as baseline	Feb-2000

New detailed US cost estimate	Jul-2000

Design Review of Hybrid/Module	Nov-2000

Start pre-production module assembly	Nov-2000

Complete pre-production module testing	Mar-2001

Production milestones:

Hybrid Production Readiness Review	Feb-2001

Module Production Readiness Review	Mar-2001

Complete hybrid production assembly and test	Nov-2002

Complete production module assembly, test and ship	Apr-2003