Pixel Completion

May 31, 2005

      - Mechanics

Sector production:

31 production sectors made.

For 2-hit: 1 remains to be made.

Predicted completion: July 1,2005. Current: June 15, 2005

Pixel Support Tube and Insertion System:

Predicted completion of wiring at LBNL: June 10, 2005. Current: June 10, 2005.

Wiring has started.

Predicted ship date to CERN: July 15, 2005. Current: July 15, 2005

LEMO Harness Production

http://www-physics.lbl.gov/~gilg/LEMOHarnessOrder/LEMOProductionLBLQA.xls

Predicted production complete: September 30, 2005. Current: September 30, 2005

LBNL Harness QA

Predicted production complete: October 14, 2005. Current: October 14, 2005

Currently about one-seventh done. Quality is very good.

Heat Exchanger and Disk Pipe Production

http://www-physics.lbl.gov/~gilg/HeatExchangerProduction/HeatExchangerProduction.xls

Predicted production completion: December 2, 2005. December 16, 2005

Currently behind in getting started. However, started trial annealing and bending.

Plan to catch up likely possible.

Service Panel Assembly, QA and Shipping

http://www-physics.lbl.gov/~gilg/ServicePanelProduction/ServicePanelProduction.xls

Predicted production start: June 13, 2005., Current: July 5, 2005

Predicted Completion: January 30, 2006. Current February 14, 2006

Final Tooling Shipment to CERN

Prediction completion: February 27, 2006. Current March 14, 2006

This milestone is 1 month after final service panel at CERN

Disk Assembly

http://www-physics.lbl.gov/~gilg/SectorLoading/DiskPlan.xls

Had to disassemble disks 1C and 3C to complete inspection and rework on HV bonds and MCC encapsulant. Disk 2C assembly started and 7 of 8 sectors are done. With all sectors in hand, it takes about 1 week to assemble and test a disk.

Predicted completion of assembly/test(4 disks=2-hit baseline): July 8, 2005. Current: August 8, 2005

1.1.1.4 Hybrids

Optical hybrids. About 40% complete.

http://www.physics.ohio-state.edu/~jack/atlas/pixel/production_status.gif

Predicted completion date: September 30, 2005. Current: September 30, 2005 but tight.

B-layer boards ordered from CPT and expected by July 15.

      - Modules

Bare die probing(FE-I3 plot from)

http://www-physics.lbl.gov/~gilg/SectorLoading/pixel-lbl-production.xls

12154 shipped. 2846 remain. Projected completion: July 15, 2005. Current: Aug. 1, 2005.

http://www-physics.lbl.gov/~gilg/SectorLoading/DiskPlan.xls

283 bare modules received. Complete.

245 modules have been burned-in. About 7 remain(2-hit)

Predicted completion(2-hit): April 11, 2005. Current: June 8, 2005

170 modules have been mounted on sectors. 22 remain(2-hit).

Predicted completion(2-hit): May 6, 2005. Current: June 20, 2005

168 modules on sectors have been tested. 24 remain(2-hit).

Predicted completion(2-hit): June 1, 2005. Current: June 27, 2005

Beam and System Tests

Predicted system test completion: July 1, 2005. Current: July 1, 2005

Comparison to CD-4a Milestones

| WBS | Item | CD-4a Milestone | Current |
| --- | --- | --- | --- |
| 1.1.1.1 | Pixel Mechanics | 4/15/2006 | 3/14/2006 |
| 1.1.1.2 | Pixel Sensors | 5/1/2005 | Complete |
| 1.1.1.3 | Pixel Electronics | 4/30/2005 | Complete |
| 1.1.1.4 | Pixel Hybrids | 9/30/2005 | 9/30/2005 |
| 1.1.1.5 | Pixel Modules | 9/1/2005 | 8/1/2005 |
| 1.1.1.6 | Beam/System Test | 8/1/2005 | 7/1/2005 |