Pixel Completion

June 30, 2005

      - Mechanics

Sector production:

33 produced. 9 more in advanced assembly. Batch of 10 tubes being prepared for laser welding. Expected completion: September 15, 2005.

Pixel Support Tube and Insertion System:

Predicted completion of wiring at LBNL: June 10, 2005. Current: July 10, 2005.

Wiring has started but requires much more touch labor than required. Also personnel working in other areas.

Predicted ship date to CERN: July 15, 2005. Current: July 30, 2005

LEMO Harness Production

http://www-physics.lbl.gov/~gilg/LEMOHarnessOrder/LEMOProductionLBLQA.xls

Predicted production complete: September 30, 2005. Current: September 30, 2005

LBNL Harness QA

Predicted production complete: October 14, 2005. Current: October 14, 2005

Currently about 30% done. Quality is very good.

Heat Exchanger and Disk Pipe Production

http://www-physics.lbl.gov/~gilg/HeatExchangerProduction/HeatExchangerProduction.xls

Predicted production completion: December 2, 2005. December 16, 2005

Behind schedule but have revised schedule to be in agreement with larger batch size that is now being done. Appears that this will allow us to roughly maintain end date but need more experience.

Service Panel Assembly, QA and Shipping

http://www-physics.lbl.gov/~gilg/ServicePanelProduction/ServicePanelProduction.xls

Predicted production start: June 13, 2005., Current: July 5, 2005

Problems with lamination of PP0 components, being resolved.

Predicted Completion: January 30, 2006. Current February 14, 2006

Final Tooling Shipment to CERN

Prediction completion: February 27, 2006. Current March 14, 2006

This milestone is 1 month after final service panel at CERN

Disk Assembly

http://www-physics.lbl.gov/~gilg/SectorLoading/DiskPlan.xls

Disk 1C reassembled/tested. Disk2C assembled/tested. Disk 3C assembly/test starts July 5..

Predicted completion of assembly/test(4 disks=2-hit baseline): July 8, 2005. Current: August 8, 2005

1.1.1.4 Hybrids

Optical hybrids. 58% complete.

http://www.physics.ohio-state.edu/~jack/atlas/pixel/production_status.gif

Predicted completion date: September 30, 2005. Current: September 30, 2005.

B-layer boards ordered from CPT and expected by July 27.

      - Modules

Bare die probing(FE-I3 plot from)

http://www-physics.lbl.gov/~gilg/SectorLoading/pixel-lbl-production.xls

13964 shipped. 1036 remain. Projected completion: July 15, 2005. Current: Aug. 1, 2005.

http://www-physics.lbl.gov/~gilg/SectorLoading/DiskPlan.xls

Module burn in complete for baseline. Note that barrel modules are behind schedule. US has been asked to test (only) barrel modules and will try to do so with base support.

Baseline module mounting on sectors complete.

186 modules on sectors have been tested. 6 remain(2-hit).

Predicted completion(2-hit): June 1, 2005. Current: July 1, 2005

Beam and System Tests

Complete

Comparison to CD-4a Milestones

| WBS | Item | CD-4a Milestone | Current |
| --- | --- | --- | --- |
| 1.1.1.1 | Pixel Mechanics | 4/15/2006 | 3/14/2006 |
| 1.1.1.2 | Pixel Sensors | 5/1/2005 | Complete |
| 1.1.1.3 | Pixel Electronics | 4/30/2005 | Complete |
| 1.1.1.4 | Pixel Hybrids | 9/30/2005 | 9/30/2005 |
| 1.1.1.5 | Pixel Modules | 9/1/2005 | 8/1/2005 |
| 1.1.1.6 | Beam/System Test | 8/1/2005 | Complete |