Pixel Completion

May 2, 2005

      - Mechanics

Sector production:

31 production sectors made.

For 2-hit: 1 remains to be made.

Predicted completion: July 1,2005. Current: June 15, 2005

Support Frame and Rings

Frame: complete

Rings: complete

Pixel Support Tube and Insertion System:

Predicted completion of mechanical assembly: April 1, 2005. Current: complete

Predicted completion of dry-fit: May 6, 2005. Current: complete

Predicted completion of wiring at LBNL: June 10, 2005. Current: June 10, 2005

Predicted ship date to CERN: July 15, 2005. Current: July 15, 2005

LEMO Harness Production

http://www-physics.lbl.gov/~gilg/LEMOHarnessOrder/LEMOProductionLBLQA.xls

Predicted production start: April 4, 2005. Current: March 30, 2005

Predicted production complete: September 30, 2005. Current: September 30, 2005

LBNL Harness QA

Predicted production started: April 11, 2005. Current: April 11, 2005

Predicted production complete: October 14, 2005. Current: October 14, 2005

Heat Exchanger and Disk Pipe Production

http://www-physics.lbl.gov/~gilg/HeatExchangerProduction/HeatExchangerProduction.xls

Predicted production start: April 4, 2005. Current: April 18, 2005

Predicted production completion: December 2, 2005. December 16, 2005

Service Panel Assembly, QA and Shipping

http://www-physics.lbl.gov/~gilg/ServicePanelProduction/ServicePanelProduction.xls

Predicted production start: June 13, 2005., Current: June 13, 2005

Predicted Completion: January 30, 2006. Current February 14, 2006

Final Tooling Shipment to CERN

Prediction completion: February 27, 2006. Current March 14, 2006

This milestone is 1 month after final service panel at CERN

Disk Assembly

http://www-physics.lbl.gov/~gilg/SectorLoading/DiskPlan.xls

Two disks were assembled. QA problems discovered in HV bonding to modules, which required some dismounting and repair. This will be completed by May 8. Retesting of two disks predicted to be completed by May 16. Assembly of 3rd disk predicted to begin by June 1 and testing of 3rd disk predicted to be completed by June 13. Assembly of 4th disk predicted to begin by July 25 and testing completed by August 8, 2005.

Predicted completion of assembly/test(4 disks=2-hit baseline): July 8, 2005. Current: August 8, 2005

      - Sensors

Complete.

      - Electronics

Complete

1.1.1.4 Hybrids

Bare flex hybrid production is complete.

Optical hybrid production is just starting.

http://www.physics.ohio-state.edu/~jack/atlas/pixel/production_timeline.gif

http://www.physics.ohio-state.edu/~jack/atlas/pixel/production_status.gif

300 delivered from CPT.180 with passive components mounted.

77 with optical components mounted of which 39 passed QA, 13 failed and 25 are

in some stage of production.

Predicted completion date: September 30, 2005. Current: September 30, 2005 but tight.

B-layer boards ordered from CPT and expected by July 15.

      - Modules

Bare die probing(FE-I3 plot from)

http://www-physics.lbl.gov/~gilg/SectorLoading/pixel-lbl-production.xls

10610 shipped. 4390 remain. Projected completion: July 15, 2005. Current: Sep 1, 2005.

Note that wrong number was reported here last month. 2nd setup added to speed up.

http://www-physics.lbl.gov/~gilg/SectorLoading/DiskPlan.xls

251 bare modules received. About 11 remain(2-hit).

Predicted completion(2-hit): April 1, 2005. Current: May 20, 2005

223 modules have been burned-in. About 29 remain(2-hit)

Predicted completion(2-hit): April 11, 2005. Current: June 8, 2005

144 modules have been mounted on sectors. 48 remain(2-hit).

Predicted completion(2-hit): May 6, 2005. Current: July 4, 2005

138 modules on sectors have been tested. 54 remain(2-hit).

Predicted completion(2-hit): June 1, 2005. Current: July 11, 2005

Beam and System Tests

Beam tests are complete.

Predicted system test completion: July 1, 2005. Current: July 1, 2005

Comparison to CD-4a Milestones

| WBS | Item | CD-4a Milestone | Current |
| --- | --- | --- | --- |
| 1.1.1.1 | Pixel Mechanics | 4/15/2006 | 3/14/2006 |
| 1.1.1.2 | Pixel Sensors | 5/1/2005 | Complete |
| 1.1.1.3 | Pixel Electronics | 4/30/2005 | Complete |
| 1.1.1.4 | Pixel Hybrids | 9/30/2005 | 9/30/2005 |
| 1.1.1.5 | Pixel Modules | 9/1/2005 | 9/1/2005 |
| 1.1.1.6 | Beam/System Test | 8/1/2005 | 7/1/2005 |