## Modules
Date | Planned Modules Started | Planned Modules Completed | Actual Modules Started | Actual Modules Screened | Weeks | Started Per Week | Completed per Week | Start Average Required | Complete Average Required | Extrapolated Modules Started | Revised per Week | Extrapolated Modules Screened | Revised per Week
2003-03-17 | 41 | 19 | 41 | 19 | 0
2003-03-24 | 45 | 22 | 43 | 24 | 1 | 2 | 5
2003-03-31 | 50 | 25 | 48 | 24 | 2 | 5 | 0 |  |  | 48 |  | 24
2003-04-07 | 55 | 28 | 51 | 24 | 3 | 3 | 0
2003-04-14 | 60 | 31 | 51 | 32 | 4 | 0 | 8
2003-04-21 | 65 | 36 | 58 | 32 | 5 | 7 | 0
2003-04-28 | 70 | 41 | 59 | 35 | 6 | 1 | 3 |  |  | 59 |  | 35
2003-05-05 | 75 | 45 | 63 | 38 | 7 | 4 | 3
2003-05-12 | 80 | 50 | 73 | 40 | 8 | 10 | 2 |  |  | 73 |  | 40
2003-05-19 | 86 | 55 | 79 | 40 | 9 | 6 | 0 |  |  | 79 |  | 40
2003-05-26 | 93 | 60 | 84 | 41 | 10 | 5 | 1 |  |  | 84 |  | 41
2003-06-02 | 100 | 65 | 87 | 43 | 11 | 3 | 2 |  |  | 87 |  | 43
2003-06-09 | 107 | 70 | 96 | 45 | 12 | 9 | 2 |  |  | 96 |  | 45
2003-06-16 | 115 | 75 | 102 | 47 | 13 | 6 | 2 | 9.4762 | 9.6383 | 102 |  | 47
2003-06-23 | 123 | 80 | 108 | 47 | 14 | 6 | 0 | 9.561 | 9.8478 | 108 |  | 47
2003-06-30 | 132 | 86 | 110 | 47 | 15 | 2 | 0 | 9.75 | 10.0667 | 110 |  | 47
2003-07-07 | 142 | 93 | 111 | 52 | 16 | 1 | 5 | 9.9744 | 10.1818 | 111 |  | 52
2003-07-14 | 152 | 100 | 116 | 59 | 17 | 5 | 7 | 10.1053 | 10.2558 | 116 |  | 59
2003-07-21 | 162 | 107 | 118 | 67 | 18 | 2 | 8 | 10.3243 | 10.3095 | 118 |  | 67
2003-07-28 | 172 | 115 | 124 | 73 | 19 | 6 | 6 | 10.4444 | 10.4146 | 124 |  | 73
2003-08-04 | 182 | 123 | 131 | 78 | 20 | 7 | 5 | 10.5429 | 10.55 | 131 | 7 | 78 | 5
2003-08-11 | 192 | 132 | 142 | 83 | 21 | 11 | 5 | 10.5294 | 10.6923 | 142 | 11 | 83 | 5
2003-08-18 | 202 | 142 | 147 | 89 | 22 | 5 | 6 | 10.697 | 10.8158 | 147 | 5 | 89 | 6
2003-08-25 | 212 | 152 | 158 | 97 | 23 | 11 | 8 | 10.6875 | 10.8919 | 158 | 11 | 97 | 8
2003-09-01 | 222 | 162 | 167 | 102 | 24 | 9 | 5 | 10.7419 | 11.0556 | 167 | 9 | 102 | 5
2003-09-08 | 232 | 172 | 177 | 111 | 25 | 10 | 9 | 10.7667 | 11.1143 | 177 | 10 | 111 | 9
2003-09-15 | 242 | 182 | 186 | 117 | 26 | 9 | 6 | 10.8276 | 11.2647 | 186 | 9 | 117 | 6
2003-09-22 | 252 | 192 | 197 | 124 | 27 | 11 | 7 | 10.8214 | 11.3939 | 197 | 11 | 124 | 7
2003-09-29 | 262 | 202 | 207 | 132 | 28 | 10 | 8 | 10.8519 | 11.5 | 207 | 10 | 132 | 8
2003-10-06 | 272 | 212 | 213 | 143 | 29 | 6 | 11 | 11.0385 | 11.5161 | 213 | 6 | 143 | 11
2003-10-13 | 282 | 222 | 225 | 147 | 30 | 12 | 4 | 11 | 11.7667 | 225 | 12 | 147 | 4
2003-10-20 | 292 | 232 | 236 | 147 | 31 | 11 | 0 | 11 | 12.1724 | 236 | 11 | 147 | 0
2003-10-27 | 302 | 242 | 243 | 155 | 32 | 7 | 8 | 11.1739 | 12.3214 | 243 | 7 | 155 | 8
2003-11-03 | 312 | 252 | 258 | 162 | 33 | 15 | 7 | 11 | 12.5185 | 258 | 15 | 162 | 7
2003-11-10 | 322 | 262 | 270 | 176 | 34 | 12 | 14 | 10.9524 | 12.4615 | 270 | 12 | 176 | 14
2003-11-17 | 332 | 272 | 282 | 185 | 35 | 12 | 9 | 10.9 | 12.6 | 282 | 12 | 185 | 9
2003-11-24 | 337 | 277 | 300 | 189 | 36 | 18 | 4 | 10.5263 | 12.9583 | 300 | 18 | 189 | 4
2003-12-01 | 347 | 287 | 306 | 191 | 37 | 6 | 2 | 10.7778 | 13.4348 | 306 | 6 | 191 | 2
2003-12-08 | 357 | 297 | 324 | 196 | 38 | 18 | 5 | 10.3529 | 13.8182 | 324 | 18 | 196 | 5
2003-12-15 | 367 | 307 | 336 | 205 | 39 | 12 | 9 | 10.25 | 14.0476 | 336 | 12 | 205 | 9
2003-12-22 | 377 | 317 | 338 | 218 | 40 | 2 | 13 | 10.8 | 14.1 | 338 | 2 | 218 | 13
2003-12-29 | 377 | 317 | 338 | 218 | 41 | 0 | 0 | 11.5714 | 14.8421 | 338 | 0 | 218 | 0
2004-01-05 | 377 | 317 | 338 | 218 | 42 | 0 | 0 | 12.4615 | 15.6667 | 338 | 0 | 218 | 0
2004-01-12 | 387 | 327 | 345 | 232 | 43 | 7 | 14 | 12.9167 | 15.7647 | 345 | 15 | 232 | 14
2004-01-19 | 397 | 337 | 359 | 239 | 44 | 14 | 7 | 12.8182 | 16.3125 | 359 | 14 | 239 | 7
2004-01-26 | 407 | 347 | 373 | 241 | 45 | 14 | 2 | 12.7 | 17.2667 | 373 | 14 | 241 | 2
2004-02-02 | 417 | 357 | 387 | 266 | 46 | 14 | 25 | 12.5556 | 16.7143 | 387 | 14 | 266 | 25
2004-02-09 | 427 | 367 | 401 | 282 | 47 | 14 | 16 | 12.375 | 16.7692 | 401 | 14 | 282 | 16
2004-02-16 | 437 | 377 | 415 | 293 | 48 | 14 | 11 | 12.1429 | 17.25 | 415 | 14 | 293 | 11
2004-02-23 | 447 | 387 | 429 | 300 | 49 | 14 | 7 | 11.8333 | 18.1818 | 429 | 14 | 300 | 7
2004-03-01 | 457 | 397 | 442 | 313 | 50 | 13 | 13 | 11.6 | 18.7 | 442 | 13 | 313 | 13
2004-03-08 | 467 | 407 | 456 | 323 | 51 | 14 | 10 | 11 | 19.6667 | 456 | 14 | 323 | 10
2004-03-15 | 477 | 417 | 477 | 333 | 52 | 21 | 10 | 7.6667 | 20.875 | 477 | 21 | 333 | 10
2004-03-22 | 487 | 427 | 491 | 338 | 53 | 14 | 5 | 4.5 | 23.1429 | 491 | 14 | 338 | 5
2004-03-29 | 497 | 437 | 505 | 353 | 54 | 14 | 15 | -5 |  | 505 | 14 | 352 | 14
2004-04-05 | 507 | 447 |  |  | 55 |  |  |  |  | 520 | 15 | 363 | 11
2004-04-12 |  | 457 |  |  | 56 |  |  |  |  | 535 | 15 | 374 | 11
2004-04-19 |  | 467 |  |  | 57 |  |  |  |  | 550 | 15 | 385 | 11
2004-04-26 |  | 477 |  |  | 58 |  |  |  |  | 565 | 15 | 396 | 11
2004-05-03 |  | 487 |  |  | 59 |  |  |  |  | 580 | 15 | 407 | 11
2004-05-10 |  | 497 |  |  | 60 | [6 empty] | 418 | 11
2004-05-17 |  | 507 |  |  | 61 | [6 empty] | 429 | 11
2004-05-24 |  |  |  |  | 62 | [6 empty] | 440 | 11
2004-05-31 |  |  |  |  | 63 | [6 empty] | 451 | 11
2004-06-07 |  |  |  |  | 64 | [6 empty] | 462 | 11
2004-06-14 |  |  |  |  | 65 | [6 empty] | 473 | 11
2004-06-21 | [11 empty] | 484 | 11
2004-06-28 | [11 empty] | 495 | 11
2004-07-05 | [11 empty] | 506 | 11
2004-07-12 | [11 empty] | 518 | 12
2004-07-19 | [11 empty] | 530 | 12
2004-07-26
2004-08-02
2004-08-09
2004-08-16
2004-08-23
2004-08-30
2004-09-06
2004-09-13
2004-09-20
2004-09-27
2004-10-04
2004-10-11