## ProductionStatus
Module | Hybrid | Glue top | Glue bottom | Cure | Metrology | IV 4 dets | Hybrid attach | Metrology | Wire bond | IV | Initial Test | Thermal Cycle | Metrology | Long Term | Ship
P001 | None
P002 | 20220040200008
P003 | 20220040200010
P004 | 20220040200009
P005 | None
P006 | 20220040200011
P007 | 20220040200012
P008 | 20220040200014
P009 | 20220040200016
P010 | 20220040200017
P011 | 20220040200018
P012 | 20220040200019
P013 | 20220040200023
P014 | 20220040200015
P015 | 20220040200020
P016 | 20220040200037
P017 | 20220040200038
P018 | 20220040200028
P019 | 20220040200040
P020 | In progress
P021 | In progress
P022 | Broken
P023 | In progress
P024 | In progress
P025 | In progress
P026 | In progress
P027 | In progress

## ModuleSummary
Module | Hybrid No. | I sum 4 det(mA) | I after bond(mA) | Total bad chan |  | Metrology
P001 | None | 0.49433 | 1.8519 | n/a |  | Wrong DIMS file loaded
P002 | 20220040200008 | 0.53844 | 4.2558 | 11 |  | Module thickness of 0.114 exceeds 0.1 tolerance, shim error
P003 | 20220040200010 | 0.51463 | 0.71878 | 2 |  | b parameter-3.2 vs tolerance of 3mrad, loCoolingFacing 0.034 vs 0.03, remeasure
P004 | 20220040200009 | 0.73987 | 0.46436 | 14 |  | midyf -6.7
P005 | None | 0.55987 | 0.42 | n/a |  | stereo -0.168 vs 0.13,a2 0.147 vs 0.13
P006 | 20220040200011 | n/a | 0.69045 | 22 | * | midyf -5.4
P007 | 20220040200012 | 0.40218 | 0.62 | 14 |  | midyf -5.7
P008 | 20220040200014 | n/a | 0.78 | 16 | * | In current spec
P009 | 20220040200016 | 0.37187 | 0.40483 | 20 | * | In current spec
P010 | 20220040200017 | 0.33238 | 0.80717 | 15 | * | In current spec
P011 | 20220040200018 | 0.3731 | 0.73775 | 11 |  | midyf -6.4
P012 | 20220040200019 | 0.38631 | 0.70291 | 11 | * | midyf -6.4
P013 | 20220040200023 | 0.38611 | 0.83128 | 13 |  | In current spec
P014 | 20220040200015 | 0.46025 | 0.99752 | 12 |  | upper hybrid height
P015 | 20220040200020 | 0.41633 | 0.54828 | 12 |  | In current spec
P016 | 20220040200037 | 0.34893 | 0.50039 | 6 |  | Module thickness .101 vs .100 and one hybrid height off, shim error
P017 | 20220040200038 | 0.38399 | 0.38594 | 7 |  | In current spec
P018 | 20220040200028 | 0.39677 | 0.36 | 0 |  | In current spec
P019 | 20220040200040 | 0.38589 | 0.48 | In progress |  | midyf 5.1, b 4.2
P020 | In progress | 0.331 | In progress | In progress |  | midyf 7.6
P021 | In progress | 0.33209 | In progress | In progress |  | stereo .165
P022 | Broken | Broken | Broken | Broken |  | Was in current spec
P023 | In progress | 0.33336 | In progress | In progress |  | sepb -15
P024 | In progress | 0.42 | In progress | In progress |  | In current spec
P025 | In progress | 98 | In progress | In progress |  | sepf -11
P026 | In progress | 0.34 | In progress | In progress |  | sepf -23
P027 | In progress | 0.35 | In progress | In progress |  | In current spec
[5 empty] | * | to be rebonded

## ProductionSummary
Date | Hybrids Started | Hybrids up to Fanouts | Modules Started | Modules Completed
2003-01-06 |  | 22 | 10 | 2
2003-01-13 | 53 | 36 | 12 | 2
2003-01-20 | 58 | 37 | 14 | 3
2003-01-27 | 59 | 40 | 18 | 3
2003-02-03 | 71 | 40 | 22 | 7
2003-02-10 | 71 | 43 | 26 | 10
2003-02-17 | 71 | 47 | 27 | 10
2003-02-24
2003-03-03
2003-03-10
2003-03-17
2003-03-24
2003-03-31
2003-04-07
2003-04-14
2003-04-21
2003-04-28
2003-05-05
2003-05-12
2003-05-19
2003-05-26
2003-06-02
2003-06-09
2003-06-16
2003-06-23
2003-06-30
2003-07-07
2003-07-14
2003-07-21
2003-07-30
2003-08-08
2003-08-19
2003-08-28
2003-09-08
2003-09-17
2003-09-26
2003-10-07
2003-10-16
2003-10-27
2003-11-05
2003-11-14
2003-11-25
2003-12-04
2003-12-15
2003-12-24
2004-01-02

## IVSummary
Modules | N-sensors | N-modules | Sum-I-Sensors | I-Module
[name] | [1] | [1] | [10^-6A] | [10^-6A]
P001 | 4 | 1 | 0.49433 | 1.8519
P002 | 4 | 1 | 0.53844 | 4.2558
P003 | 4 | 1 | 0.51463 | 0.71878
P004 | 4 | 1 | 0.73987 | 0.46436
P005 | 4 | 2 | 0.55987 | 0.42
P006 | 0 | 3 | n/a | 0.69045
P007 | 4 | 2 | 0.40218 | 0.62
P008 | 0 | 3 | n/a | 0.78
P009 | 4 | 1 | 0.37187 | 0.40483
P010 | 4 | 1 | 0.33238 | 0.80717
P011 | 4 | 1 | 0.3731 | 0.73775
P012 | 4 | 1 | 0.38631 | 0.70291
P013 | 4 | 1 | 0.38611 | 0.83128
P014 | 4 | 1 | 0.46025 | 0.99752
P015 | 4 | 1 | 0.41633 | 0.54828
P016 | 4 | 1 | 0.34893 | 0.50039
P017 | 4 | 1 | 0.38399 | 0.38594
P018 | 4 | 1 | 0.39677 | 0.36
P019 | 4 | 1 | 0.38589 | 0.48
P020 | 4 | 0 | 0.331
P021 | 4 | 0 | 0.33209
P022 | 4 | 0 | 0.35331
P023 | 4 | 0 | 0.33336
P024 | 4 | 0 | 0.42
P025 | 4 | 0 | 98 |  | Redo IV
P026 | 4 | 0 | 0.34
P027 | 4 | 0 | 0.35
Currents @500 V and about 19.5C
N sensors should be 4(for the 4 individual sensor measurements)
N modules should be one for measurement after bonding. The 0 indicates not yet bonded.
Some measurements are missing(as noted) and in some cases not clear after bonding. Best guess is shown.
n/a means files not available

## XYMetrology
-------------------<Parameters>--------------> | Mhx | Mhy | Msx | Msy | Sepf | Sepb | Midxf | Midyf | Stereo | a1 | a2 | a3 | a4 | Fixture
--------------------<Units>----------------------> | mm | mm | mm | mm | mm | mm | mm | mm | mrad | mrad | mrad | mrad | mrad
--------------------<Tolerances>--------------> | 30 | 30 | 100 | 30 | 10 | 10 | 10 | 5 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
CU-FF-H-Survey-P002-Dec05-after_hybrid-test.xls | 0 | 3.3 | 69.8 | 1.5 | -4.5 | -1.1 | -4.7 | 2.4 | -0.05 | 0.018 | 0.059 | -0.012 | -0.029 | A1
CU-FF-H-Survey-P002-Sep30-after_hybrid.xls | 1.8 | 3.2 | 44.4 | -2.2 | -6.4 | -2 | -4.7 | 3.3 | -0.057 | 0.044 | 0.056 | -0.018 | -0.022 | A1
CU-FF-H-Survey-P003-Dec06-after_hybrid-test.xls | -1.3 | 6.2 | 32.3 | 2.1 | -3.5 | -5.4 | -2.7 | -4.7 | -0.111 | -0.032 | 0.047 | -0.069 | -0.016 | A1
CU-FF-H-Survey-P003-Oct03-after_hybrid.xls | 0.5 | 7.6 | 0.6 | 9.8 | -4.3 | -7.6 | -1.5 | -3 | -0.12 | -0.008 | 0.053 | -0.078 | -0.017 | A1
CU-FF-H-Survey-P004-Dec06-after_hybrid-test.xls | 0.5 | 1 | 13.2 | 5.2 | -5.8 | -0.9 | -2.6 | -6.7 | -0.126 | -0.005 | 0.041 | -0.105 | -0.016 | A1
CU-FF-H-Survey-P004-Oct08-after_hybrid.xls | 3 | 2.6 | 50 | 5.6 | -8.4 | -4.5 | -0.5 | -5.9 | -0.136 | 0.016 | 0.05 | -0.105 | -0.025 | A1
CU-FF-H-Survey-P006-Jan10-after_hybrid-test.xls | 5.8 | -13 | 48.6 | -8.7 | -7.6 | -6.2 | -1.4 | -5.4 | 0.021 | 0.023 | 0.052 | -0.048 | -0.023 | A1
CU-FF-H-Survey-P007-Jan09-after_hybrid.xls | 26.4 | -21.7 | 67.9 | -5.9 | -3.2 | -0.6 | 0.6 | -5.1 | 0.024 | 0.047 | 0.04 | -0.07 | -0.01 | A1
CU-FF-H-Survey-P007-Jan27-after_hybrid-test.xls | 33 | -21.6 | 48.7 | -1.6 | -4.5 | -2.1 | 3.5 | -5.6 | 0.029 | 0.054 | 0.024 | -0.075 | 0.007 | A1
CU-FF-H-Survey-P008-Dec20-after_hybrid.xls | 2.2 | -13.8 | 1.6 | -9.1 | -0.5 | -4 | 7 | -0.4 | 0.01 | 0.028 | 0.012 | -0.038 | -0.045 | A1
CU-FF-H-Survey-P008-Jan13-after_hybrid-test.xls | 9.8 | -13.1 | 54.7 | -7 | -0.7 | -4.5 | 7.2 | -1.3 | 0.011 | 0.025 | 0.02 | -0.039 | -0.024 | A1
CU-FF-H-Survey-P009-Jan08-after_hybrid.xls | 9.2 | -7 | 16.7 | -7.2 | -2.3 | -2.4 | 0.5 | -3.8 | 0.027 | 0.012 | 0.033 | -0.043 | 0.001 | A1
CU-FF-H-Survey-P009-Jan31-after_hybrid-test.xls | 12.5 | -8.2 | 75.9 | -9.9 | -2.9 | -3.6 | 3.7 | -3.2 | 0.024 | 0.018 | 0.024 | -0.037 | -0.002 | A1
CU-FF-H-Survey-P010-Feb04-after_hybrid-test.xls | 6.9 | -17.3 | 64.2 | -5.2 | -0.3 | 0.4 | 3.2 | -3 | 0.026 | 0.08 | 0.051 | -0.024 | 0.023 | A1
CU-FF-H-Survey-P010-Jan09-after_hybrid.xls | 6 | -15.8 | 29.1 | -1.8 | -0.3 | 0.9 | 0 | -3.2 | 0.031 | 0.096 | 0.045 | -0.032 | 0.018 | A1
CU-FF-H-Survey-P011-Feb05-after_hybrid-test.xls | 12.9 | -10.6 | -18.5 | 2.4 | -4.2 | -3.4 | 3.7 | -6.1 | 0.024 | 0.038 | 0.075 | -0.045 | -0.006 | A1
CU-FF-H-Survey-P011-Jan14-after_hybrid.xls | 10.8 | -11 | 27.2 | 6.8 | -3.3 | -2.3 | 1.8 | -6.4 | 0.023 | 0.044 | 0.062 | -0.05 | -0.011 | A1
CU-FF-H-Survey-P012-Feb05-after_hybrid-test.xls | 19.4 | -6.5 | 0.6 | -1 | -3.6 | -4.6 | 8.8 | -6.6 | 0.02 | 0.064 | 0.008 | -0.051 | -0.069 | A1
CU-FF-H-Survey-P012-Jan16-after_hybrid.xls | 19.2 | -10.2 | 35.1 | -5 | -2.4 | -3.5 | 7 | -6.4 | 0.017 | 0.053 | 0.026 | -0.061 | -0.069 | A1
CU-FF-H-Survey-P013-Feb05-after_hybrid-test.xls | 8.1 | -14.6 | 44.9 | 6.4 | -3.9 | -8.1 | 2.5 | 2.9 | 0.016 | 0.041 | 0.032 | 0.006 | 0.037 | A1
CU-FF-H-Survey-P013-Jan22-after_hybrid.xls | 6.3 | -18.6 | 45.2 | 3.6 | -3.7 | -7.9 | 3 | 2.7 | 0.014 | 0.038 | 0.037 | 0.005 | 0.021 | A1
CU-FF-H-Survey-P014-Feb6-after_hybrid-test.xls | 16.6 | -12.1 | 9.4 | -10.7 | -5.6 | -8.4 | 2.5 | 4 | 0.009 | 0.011 | 0.053 | -0.06 | 0.011 | A1
CU-FF-H-Survey-P015-Jan29-after_hybrid.xls | 12.6 | -11 | -27 | -0.4 | -7.2 | -5.3 | -1.2 | 4.9 | 0.033 | 0.038 | 0.029 | -0.035 | 0.023 | A1
CU-FF-H-Survey-P016-Jan31-after_hybrid.xls | -6.2 | 1.9 | 19.8 | -13.5 | -3.6 | -4.4 | 9.3 | -1.5 | 0.087 | 0.041 | 0.043 | -0.015 | -0.072 | A0
CU-FF-H-Survey-P017-Feb03-after_hybrid.xls | 13.1 | -11.9 | 101 | 2 | -4.9 | -4.1 | 0.1 | 3.3 | 0.034 | 0.026 | 0.042 | -0.043 | 0.023 | A1
CU-FF-H-Survey-P018-Feb06-after_hybrid.xls | 13.5 | -10 | 52.6 | -7.9 | -3 | -8.6 | 1.5 | 4.6 | 0.002 | 0.029 | 0.045 | -0.059 | -0.031 | A0
CU-FF-H-Survey-P019-Feb11-after_hybrid.xls | 8.3 | -3.4 | -13.1 | -5.2 | -6.4 | -3.2 | 9.2 | 5.1 | 0.107 | 0.018 | 0.086 | -0.007 | -0.062 | A0
CU-FF-Survey-P001-Aug12-after_heat.xls | 11.4 | -51 | 19.6 | -29.1 | -5.7 | -2.8 | -5.3 | -53 | 0.394 | 0.065 | 0.039 | -0.085 | -0.062 | A1
CU-FF-Survey-P002-Sep26-after_heat.xls | 2.3 | 3.7 | 37 | -0.8 | -5.7 | -2.1 | -3.4 | 2.6 | -0.055 | 0.02 | 0.051 | -0.014 | -0.015 | A1
CU-FF-Survey-P003-Sep30-after-heat2-XXX.xls | 2.4 | 6 | 82.7 | 5.9 | -5 | -7.7 | -1 | -4.2 | -0.082 | -0.016 | 0.062 | -0.073 | -0.007 | A1
CU-FF-Survey-P004-Oct4-after-glue2-XXX.xls | 4.7 | 1.7 | 26.6 | 11.1 | -7 | -3.4 | -2.2 | -5.7 | -0.05 | 0.004 | 0.06 | -0.098 | -0.011 | A1
CU-FF-Survey-P005-Oct9-after-heat3-XXX-3.xls | 2.4 | -2 | 32.4 | 5.5 | -9.6 | -6.2 | 2.2 | 0.1 | -0.252 | 0.104 | 0.151 | -0.024 | -0.008 | A1
CU-FF-Survey-P006-Dec02-afterheat.xls | 6.9 | -12.8 | 29.5 | -1.6 | -7.5 | -5.8 | -1.9 | -5.7 | 0.03 | 0.024 | 0.056 | -0.04 | -0.021 | A1
CU-FF-Survey-P007-Dec05-clear.xls | 24.1 | -14.5 | 83.7 | 0.9 | -3.2 | -0.7 | 1.2 | -4.6 | 0.021 | 0.053 | 0.032 | -0.076 | 0.009 | A1
CU-FF-Survey-P008-Dec13-clear.xls | 7.2 | -9.8 | 78.2 | -6.9 | -0.1 | -3.9 | 7.2 | -1.1 | 0.012 | 0.013 | 0.019 | -0.022 | -0.022 | A1
CU-FF-Survey-P009-Dec23-clear.xls | 9.5 | -8 | 34 | -11.3 | -2.1 | -2.5 | 1.4 | -2.9 | 0.018 | 0.021 | 0.04 | -0.043 | -0.006 | A1
CU-FF-Survey-P010-Jan07-clear.xls | 10.8 | -18.6 | 43.8 | 1.4 | -0.4 | 0.5 | -0.2 | -3.7 | 0.029 | 0.062 | 0.064 | -0.043 | 0.029 | A1
CU-FF-Survey-P011-Jan10-clear.xls | 4.4 | -6.8 | 48 | 8.7 | -3.4 | -2.3 | 1.9 | -6.4 | 0.014 | 0.053 | 0.07 | -0.049 | -0.028 | A1
CU-FF-Survey-P012-Jan13-clear.xls | 8 | -5.7 | 19.4 | -2.9 | -2.5 | -4.2 | 7 | -6.8 | 0.03 | 0.036 | 0.017 | -0.055 | -0.051 | A1
CU-FF-Survey-P013-Jan15-clear.xls | 18.8 | -15.9 | 82.4 | 6.1 | -3.6 | -6.5 | 0.7 | 3.2 | 0.011 | 0.037 | 0.031 | -0.009 | 0.024 | A1
CU-FF-Survey-P014-Jan21-clear.xls | 12.8 | -12 | 44.3 | -3 | -6.4 | -8.1 | 3.6 | 3.7 | -0.005 | 0.01 | 0.05 | -0.063 | 0 | A1
CU-FF-Survey-P015-Jan23-clear.xls | 17.3 | -10 | -32 | -1.8 | -7 | -4.3 | 0 | 4.5 | 0.032 | 0.032 | 0.027 | -0.053 | 0.018 | A1
CU-FF-Survey-P016-Jan24-clear.xls | 8.4 | -1.8 | 37.8 | -9.6 | -3.8 | -3 | 10.2 | -1.5 | 0.094 | 0.036 | 0.025 | -0.01 | -0.063 | A0
CU-FF-Survey-P017-Jan28-clear.xls | 19.4 | -11.3 | 130.8 | 5.5 | -5.1 | -3.3 | 1.3 | 3.2 | 0.034 | 0.024 | 0.021 | -0.048 | 0.02 | A1
CU-FF-Survey-P018-Jan30-clear.xls | 20.1 | -8.7 | 59.3 | -5 | -3 | -9 | 1.7 | 4.7 | 0.011 | 0.019 | 0.032 | -0.071 | -0.021 | A0
CU-FF-Survey-P019-Jan30-clear.xls | -2.1 | 1.2 | 42.8 | 8.5 | -6 | -3.1 | 8 | 4.7 | 0.117 | 0.003 | 0.082 | -0.01 | -0.054 | A1
CU-FF-Survey-P020-Jan31-clear.xls | 8 | -0.6 | 34.8 | -2.7 | -8 | -10 | 0.8 | 7.6 | 0.026 | 0.081 | 0.039 | -0.082 | 0.017 | A1
CU-FF-Survey-P021-Jan31-clear.xls | 5.3 | 5.9 | 32 | 3.3 | -2.4 | 0.4 | 2.5 | 2.1 | 0.165 | 0.049 | 0.118 | -0.016 | -0.026 | A0
CU-FF-Survey-P022-Feb03-clear.xls | -7.3 | -21.8 | 8.1 | -32.3 | -10 | -2.5 | -0.5 | 1.9 | 0.009 | 0.008 | 0.069 | -0.015 | 0.049 | A2
CU-FF-Survey-P023-Feb04-clear.xls | 14.3 | -8.4 | 83.3 | -0.6 | -2.8 | -15.1 | 4.4 | -1.1 | 0.024 | 0.009 | 0.011 | -0.052 | 0.016 | A1
CU-FF-Survey-P024-Feb07-clear.xls | 22.2 | 6.2 | 128.3 | 56.2 | -6.9 | -1.3 | 5.5 | 2.2 | -0.054 | 0.045 | 0.047 | -0.037 | 0.023 | A0
CU-FF-Survey-P024-Feb10-clear-manual.xls | 15.5 | 7.2 | 75.1 | 24.5 | -6.7 | -1.8 | 5.3 | 2 | -0.054 | 0.046 | 0.046 | -0.041 | 0.036 | A0
CU-FF-Survey-P025-Feb07-clear.xls | 9.9 | -5.5 | 43.7 | -6.4 | -10.7 | -6.7 | 1.3 | 0.6 | -0.007 | 0.03 | 0.057 | -0.021 | -0.032 | A2
CU-FF-Survey-P026-Feb07-clear.xls | 4.3 | 6.5 | 55.9 | 12.8 | -23.1 | -5.7 | 3 | -0.6 | -0.01 | 0.059 | 0.038 | -0.07 | -0.005 | A1
CU-FF-Survey-P027-Feb11-clear.xls | 13.4 | -5.6 | 431.9 | -44.3 | 4.1 | 1.7 | 7.8 | -1.9 | 0.026 | -0.023 | 0.013 | -0.082 | -0.019 | A1
CU-FF-Survey-P027-Feb11-clear-manual.xls | 14.5 | -6.5 | 19.5 | 5.7 | 4.1 | 1.7 | 7.8 | -1.9 | 0.026 | -0.023 | 0.013 | -0.082 | -0.019 | A1
Note that the nomenclature has evolved. The standard set of files should be
clear.xls measurements before hybrid attach
after_hybrid.xls after hybrid attach but before thermal cycling/testing
after_hybrid-test.xls after thermal cycling/testing
manual measurements required in last few modules to measure slot correctly

## ZMetrology
-------------------<Parameters>--------------> | maxZlower | maxZupper | moduleThickness | N shape | loCoolingFacing-a | b | loCoolingFacingConcavity
-------------------<Units>------------------------> | [mm] | [mm] | [mm] | [1] | [mrad] | [mrad] | [mm]
--------------------<Tolerances>--------------> | -0.2 | 0.2 | 0.1 | 4 | 0.5 | 3 | 0.03
surveyZ-241-P001-Aug08-after_glue.xls | -0.012 | 0.031 | 0.095 | 4 | 0.058 | -2.848 | 0.02
surveyZ-241-P001-Aug12-after_heat.xls | -0.02 | 0.023 | 0.094 | 4 | 0.105 | -3.403 | 0.025
surveyZ-241-P002-Dec05-after_hybrid-test.xls | -0.05 | 0.001 | 0.114 | 4 | 0.126 | -1.707 | 0
surveyZ-241-P002-Sep25-after_glue.xls | -0.012 | 0.002 | 0.114 | 4 | 0.103 | -1.4 | 0.006
surveyZ-241-P002-Sep26-after_heat.xls | -0.03 | -0.005 | 0.111 | 4 | 0.124 | -1.839 | 0.007
surveyZ-241-P002-Sept30-after_hybrid.xls | -0.021 | -0.003 | 0.116 | 4 | 0.074 | -0.711 | 0.003
surveyZ-241-P003-Dec06-after_hybrid-test.xls | -0.068 | 0.003 | 0.02 | 4 | 0.037 | -3.193 | 0.024
surveyZ-241-P003-Oct03-after_hybrid.xls | -0.069 | 0.001 | 0.019 | 4 | 0.094 | -4.091 | 0.034
surveyZ-241-P003-Sep30-after_heat.xls | -0.052 | 0.003 | 0.019 | 4 | -0.041 | -1.677 | -0.004
surveyZ-241-P004-Dec06-after_hybrid-test.xls | -0.003 | 0.026 | 0.017 | 4 | -0.034 | -0.437 | -0.007
surveyZ-241-P004-Oct03-after_glue.xls | -0.002 | 0.021 | 0.019 | 4 | -0.005 | -1.682 | 0.001
surveyZ-241-P004-Oct08-after_hybrid.xls | -0.001 | 0.019 | 0.019 | 4 | -0.064 | -0.574 | -0.004
surveyZ-241-P005-Oct08-clear-after-heat.xls | -0.04 | 0.001 | 0.015 | 4 | 0.019 | -1.578 | 0.004
surveyZ-241-P006-Dec02-afterheat.xls | -0.006 | 0.021 | 0.052 | 4 | 0.03 | -0.787 | -0.003
surveyZ-241-P006-Jan10-after_hybrid-test.xls | -0.011 | 0.025 | 0.051 | 4 | -0.114 | 2.278 | -0.017
surveyZ-241-P006-Nov27-clear.xls | -0.005 | 0.047 | 0.051 | 4 | 0.034 | -0.889 | -0.003
surveyZ-241-P007-Dec05-clear.xls | -0.027 | 0.009 | 0.033 | 4 | 0.026 | -2.091 | 0.011
surveyZ-241-P007-Dec12-after_hybrid.xls | -0.064 | 0.02 | 0.036 | 4 | -0.082 | 1.737 | -0.005
surveyZ-241-P007-Jan09-after_hybrid.xls | -0.074 | 0.042 | 0.034 | 4 | -0.139 | 2.429 | -0.007
surveyZ-241-P007-Jan27-after_hybrid-test.xls | -0.088 | 0.026 | 0.032 | 4 | -0.062 | 0.902 | -0.003
surveyZ-241-P007-Jan27-after_hybrid-test.xls | -0.088 | 0.026 | 0.032 | 4 | -0.062 | 0.902 | -0.003
surveyZ-241-P008-Dec16-clear.xls | -0.049 | -0.002 | 0.018 | 4 | 0.033 | -0.844 | 0.002
surveyZ-241-P008-Dec20-after_hybrid.xls | -0.039 | 0 | 0.023 | 4 | -0.008 | 0.293 | -0.005
surveyZ-241-P008-Jan13-after_hybrid-test.xls | -0.047 | -0.001 | 0.023 | 4 | -0.001 | -0.274 | -0.002
surveyZ-241-P008-Jan13-after_hybrid-test.xls | -0.047 | -0.001 | 0.023 | 4 | -0.001 | -0.274 | -0.002
surveyZ-241-P009-Dec23-clear.xls | -0.029 | 0.019 | 0.036 | 4 | 0.069 | -1.637 | 0.008
surveyZ-241-P009-Jan07-after_hybrid.xls | -0.046 | 0.021 | 0.039 | 4 | 0.006 | -0.373 | 0.002
surveyZ-241-P009-Jan31-after_hybrid-test.xls | -0.055 | 0.02 | 0.034 | 4 | -0.007 | -0.708 | 0.004
surveyZ-241-P010-Feb04-after_hybrid-test.xls | -0.032 | 0.056 | 0.024 | 4 | 0.013 | 1.362 | -0.012
surveyZ-241-P010-Jan07-clear.xls | -0.015 | 0.004 | 0.027 | 4 | -0.006 | -0.599 | -0.006
surveyZ-241-P010-Jan09-after_hybrid.xls | -0.031 | 0.008 | 0.027 | 4 | 0.011 | 1.2 | -0.013
surveyZ-241-P011-Feb05-after_hybrid-test.xls | -0.074 | 0.004 | 0.034 | 4 | -0.006 | 0.448 | 0.001
surveyZ-241-P011-Jan10-clear.xls | -0.053 | 0.001 | 0.036 | 4 | 0.075 | -2.03 | 0.013
surveyZ-241-P011-Jan14-after_hybrid.xls | -0.072 | 0.051 | 0.037 | 3 | 0.007 | 0.788 | 0.002
surveyZ-241-P012-Feb05-after_hybrid-test.xls | -0.029 | 0.039 | 0.066 | 2 | 0 | 0.372 | -0.001
surveyZ-241-P012-Jan13-clear.xls | -0.032 | 0.037 | 0.073 | 2 | 0.056 | -0.42 | 0.001
surveyZ-241-P012-Jan16-after_hybrid.xls | -0.027 | 0.044 | 0.072 | 2 | 0.007 | 0.229 | -0.003
surveyZ-241-P013-Feb05-after_hybrid-test.xls | -0.042 | 0.018 | 0.009 | 4 | -0.073 | 2.214 | -0.013
surveyZ-241-P013-Jan15-clear.xls | -0.001 | 0.014 | 0.015 | 4 | 0.021 | -1.4 | 0
surveyZ-241-P013-Jan22-after_hybrid.xls | -0.038 | 0.02 | 0.01 | 4 | -0.038 | 2.898 | -0.012
surveyZ-241-P014-Feb6-after_hybrid-test.xls | -0.061 | 0.058 | 0.021 | 3 | -0.086 | 0.325 | -0.012
surveyZ-241-P014-Jan21-clear.xls | -0.031 | 0 | 0.023 | 4 | 0.016 | -1.884 | -0.008
surveyZ-241-P015-Jan23-clear.xls | -0.008 | 0.003 | -0.024 | 4 | -0.019 | -1.262 | 0.005
surveyZ-241-P015-Jan29-after_hybrid.xls | -0.044 | 0.001 | -0.022 | 4 | -0.053 | 1.616 | -0.008
surveyZ-241-P016-Jan24-clear.xls | -0.007 | 0.005 | 0.098 | 4 | 0.051 | -1.426 | 0.002
surveyZ-241-P016-Jan31-after_hybrid.xls | -0.053 | 0.01 | 0.101 | 4 | -0.006 | -0.027 | -0.003
surveyZ-241-P017-Feb03-after_hybrid.xls | -0.045 | 0.003 | 0.006 | 4 | -0.043 | 0.723 | -0.014
surveyZ-241-P017-Jan28-clear.xls | -0.041 | -0.002 | 0.006 | 4 | -0.012 | -1.132 | -0.007
surveyZ-241-P018-Feb06-after_hybrid.xls | -0.049 | 0.003 | 0.012 | 4 | 0.074 | 0.52 | -0.005
surveyZ-241-P018-Jan30-clear.xls | -0.056 | 0.007 | 0.01 | 4 | 0.107 | -2.533 | 0.009
surveyZ-241-P019-Feb11-after_hybrid.xls | -0.029 | 0.024 | -0.008 | 4 | -0.058 | 4.137 | -0.013
surveyZ-241-P019-Jan30-clear.xls | -0.037 | -0.002 | -0.007 | 4 | 0.021 | -2.066 | 0.007
surveyZ-241-P020-Jan31-clear.xls | -0.078 | 0.002 | 0.017 | 4 | 0.08 | -1.09 | 0.003
surveyZ-241-P021-Jan31-clear.xls | -0.021 | 0.007 | -0.011 | 4 | 0.008 | 0.772 | -0.012
surveyZ-241-P022-Feb03-clear.xls | -0.052 | 0 | 0.018 | 4 | 0.017 | -1.903 | 0.005
surveyZ-241-P023-Feb04-clear.xls | -0.026 | 0.003 | 0.026 | 4 | 0.015 | -0.547 | -0.005
surveyZ-241-P024-Feb07-clear.xls | -0.011 | 0.003 | -0.001 | 3 | 0.026 | -1.643 | 0.001
surveyZ-241-P025-Feb07-clear.xls | -0.037 | 0.025 | 0.038 | 4 | 0.04 | -1.465 | 0.004
surveyZ-241-P026-Feb07-clear.xls | -0.011 | 0.064 | 0.018 | 3 | -0.006 | -1.724 | 0.001
surveyZ-241-P027-Feb11-clear.xls | -0.004 | 0.011 | 0.011 | 4 | 0.005 | -1.623 | -0.001

## TestSummary
| Serial # | ok | Chip repl | Noisy/ dead | Negative Offset masked | High Offset (>50) masked | LTT |  | ok | lost after fanout | Total bad channels (Hybrid) | ok | Module | ok | max LC 150C 500V before TC (mA) | max LC 150C 500V after TC+Metr (mA) | max LC 150C 500V after rebonding (mA) | max LC 00C 500V after LTT (mA) | Noisy/dead | Unbonded | After rebonding | Total bad channels (Module) | TESTS Completed
[7 empty] | cold | warm
1 | 20220040200008 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P2 | 1 | 0.963 | 0.922 |  | 0.092 | 2 | 9 |  | 11 | 1
1 | 20220040200009 | 1 |  | 0 |  | 1 | 0 | 0 | 1 | 4 | 5 | 1 | P4 | 1 | 0.256 | 0.266 |  | 0.072 | 7 | 7 |  | 14 | 1
1 | 20220040200010 | 1 |  | 0 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 | P3 | 1 | 0.287 | 0.297 |  | 0.092 | 1 | 1 |  | 2 | 1
1 | 20220040200011 | 1 | 1 | 0 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 | P6 | 1 | 1.917 | 0.758 |  | 0.307 | 1 | 21 |  | 22 | 1
1 | 20220040200012 | 1 |  | 0 |  |  | 0 | 0 | 1 | 3 | 3 | 1 | P7 | 1 | 0.307 |  | 0.318 |  | 0 | 16 | 14 | 14 | 1
1 | 20220040200013 | 1 | 1 | 0 |  |  | 0 | 0 | 1
1 | 20220040200014 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P8 | 1 | 0.738 | 0.656 |  | 0.348 | 0 | 16 |  | 16 | 1
1 | 20220040200015 | 1 |  | 1 |  |  | 0 | 0 | 1 | 0 | 1 | 1 | P14 | 1 | 0.482 |  | 0.451 |  | 1 | 21 | 11 | 12
1 | 20220040200016 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P9 | 1 | 0.287 |  |  |  |  | 20 |  | 20 | 1
1 | 20220040200017 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P10 | 1 | 0.43 | 0.512 |  |  | 1 | 14 |  | 15 | 1
1 | 20220040200018 | 1 |  | 0 |  |  | 0 | 0 | 1 | 2 | 2 | 1 | P11 | 1 | 0.328 | 0.748 | 0.502 |  | 0 | 22 | 11 | 11 | 1
1 | 20220040200019 | 1 |  | 1 |  |  | 0 | 0 | 1 | 0 | 1 | 1 | P12 | 1 | 0.605 |  |  |  | 2 | 9 |  | 11
1 | 20220040200020 | 1 | 1 | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P15 | 1 | 0.307 |  | 0.461 |  | 0 | 22 | 12 | 12
1 | 20220040200021 |  | 1 | 0
1 | 20220040200022 |  | 1 | 0
1 | 20220040202223 | 1 |  | 1 |  |  | 0 | 0 | 1 | 0 | 1 | 1 | P13 | 1 | 0.4 | 1.681 | 0.471 |  | 3 | 20 | 10 | 13 | 1
1 | 20220040200024 | 1 |  | 0 |  |  | 0 | 1 | 1 | 0 | 1 | 1
1 | 20220040200025 | 1 |  | 1 |  | 1 | 1 | 0 | 1 | 0 | 3 | 1
1 | 20220040200026 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200027 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1
1 | 20220040200028 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P18 | 1 | 0.246
1 | 20220040200029 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1
1 | 20220040200030 | 1 |  | 1 |  |  | 0 | 0 | 1 | 0 | 1 | 1
1 | 20220040200031 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200032 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1
1 | 20220040200033 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200034 | 1 |  | 0 | 1 |  | 0 | 0 | 1
1 | 20220040200035 |  | 1
1 | 20220040200036 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200037 | 1 |  | 1 |  |  | -1 | 0 | 1 | 0 | 0 | 1 | P16 | 1 | 0.451 |  |  |  |  | 6 |  | 6
1 | 20220040200038 | 1 |  | 0 |  |  | 1 | 0 | 1 | 0 | 0 | 1 | P17 | 1 | 0.225 |  |  |  | 3 | 4 |  | 7
1 | 20220040200039 |  | 1 | 0 |  |  | 3 | 0 |  | 0 | 0
1 | 20220040200040 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1 | P19 | 1 | 0.246
1 | 20220040200041 | 1 |  | 1 |  |  | 0 | 0 | 1 | 0 | 0 | 1
1 | 20220040200042 | 1 |  | 0 |  |  | 1 | 0 | 1 | 0 | 0 | 1
1 | 20220040200043 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1
1 | 20220040200044 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 0 | 1
1 | 20220040200045 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200046 |  | 1
1 | 20220040200047 |  | 1
1 | 20220040200048
1 | 20220040200049 | 1 |  | 0 |  |  | 0 | 0 | 1
| Serial # | ok | Chip repl | Noisy/ dead | Negative Offset masked | High Offset (>50) masked | LTT |  | ok | lost after fanout | Total bad channels (Hybrid) | ok | Module | ok | max LC 150C 500V before TC (mA) | max LC 150C 500V after TC+Metr (mA) | max LC 150C 500V after rebonding (mA) | max LC 00C 500V after LTT (mA) | Noisy/dead | Unbonded | After rebonding | Total bad channels (Module) | TESTS Completed
[7 empty] | cold | warm
1 | 20220040200050 | 1 |  | 0 |  |  | 1 | 1 | 1
1 | 20220040200051 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200052 | 1 |  | 0 | 1 |  | 1 | 0 | 1
1 | 20220040200053 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200054 | 1
1 | 20220040200055 | 1
1 | 20220040200056
1 | 20220040200057 | 1 |  | 0 | 2 |  | 1 | 0 | 1
1 | 20220040200058
1 | 20220040200059
1 | 20220040200060
1 | 20220040200061 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200062 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200063 | 1 |  | 0 |  | 2 | 0 | 0 | 1
1 | 20220040200064 | 1 |  | 0 |  |  | 1 | 0 | 1
1 | 20220040200065 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200066 | 1 |  | 0 |  | 1
1 | 20220040200067 | 1 |  | 1 |  |  | 0 | 0 | 1
1 | 20220040200068 | 1 |  | 1 |  |  |  | 0
1 | 20220040200069 | 1 |  | 0 |  |  | 0 | 0 | 1
1 | 20220040200070 | 1 |  | 0
1 | 20220040200071 | 1 |  | 0
1 | 20220040200072 | 1 |  | 0
1 | 20220040200073 |  | 1
1 | 20220040200074 | 1 |  | 0
1 | 20220040200075
1 | 20220040200076
1 | 20220040200077 | 1
1 | 20220040200078
20220040200078
20220040200079
20220040200080
20220040200081
20220040200082
20220040200083
20220040200084
20220040200085
20220040200086
20220040200087
Hybrids Built |  | Hybrids tested OK |  |  | Chip replaced or pending |  |  | Hybrids up to fanout |  |  | Hybrids to module |  |  | Modules | [7 empty] | Module Test Completed
71 |  | 56 |  |  | 10 |  |  |  | 47 |  |  | 27 |  | 17 | [8 empty] | 10
in Santa Cruz
on hold for study or chip replacement
modules rebonded