## ProductionStatus
Module | Hybrid | Glue top | Glue bottom | Cure | Metrology | IV 4 dets | Hybrid attach | Metrology | Wire Bond | IV | Initial Test | Thermal Cycle | Long Term | Metrology | Final Test Done | Ship
P001 | Fail
P002 | 20220040200008
P003 | 20220040200010
P004 | 20220040200009
P005 | On hold
P006 | 20220040200011
P007 | 20220040200012
P008 | 20220040200014
P009 | 20220040200016
P010 | 20220040200017
P011 | 20220040200018
P012 | 20220040200019
P013 | 20220040200023
P014 | 20220040200015
P015 | 20220040200020
P016 | 20220040200037
P017 | 20220040200038
P018 | 20220040200028
P019 | 20220040200040
P020 | 20220040200024
P021 | On hold
P022 | 20220040200029 | [7 empty] | Fail
P023 | 20220040200041
P024 | 20220040200025
P025 | On hold
P026 | On hold
P027 | 20220040200042
P028 | 20220040200030
P029 | 20220040200032
P030 | 20220040200031 | [8 empty] | Repair
P031 | 20220040200043
P032 | 20220040200027
P033 | 20220040200044
P034 | 20220040200069
P035 | 20220040200045
P036 | 20220040200049
P037 | 20220040200051
P038 | 20220040200033
P039 | 20220040200061
P040 | 20220040200034
P041 | 20220040200053
P042 | 20220040200036
P043 | Fail
P044 | 20220040200063
P045 | 20220040200055 | [8 empty] | Repair
P046 | 20220040200062
P047 | 20220040200065
P048 | Started
P049 | 20220040200013 | [8 empty] | Repair
P050 | 20220040200072
P051 | Started
P052 | Started
P053 | 20220040200071
P054 | Started
P055 | Started
P056 | Started
P057 | Started
P058 | Fail
P059 | Started
P060 | Started
P061 | Started
P062 | Started
P063 | Started

## ProductionSummary
Date | Hybrids Started | Hybrids up to Fanouts | Modules Started | Modules Completed
2003-01-06 |  | 22 | 10 | 2
2003-01-13 | 53 | 36 | 12 | 2
2003-01-20 | 58 | 37 | 14 | 3
2003-01-27 | 59 | 40 | 18 | 3
2003-02-03 | 71 | 40 | 22 | 7
2003-02-10 | 71 | 43 | 26 | 10
2003-02-17 | 71 | 47 | 27 | 10
2003-02-24 | 73 | 52 | 28 | 13
2003-03-03 | 73 | 56 | 31 | 19
2003-03-10 | 73 | 63 | 35 | 17
2003-03-17 | 73 | 63 | 41 | 19
2003-03-24 | 78 | 63 | 43 | 24
2003-03-31 | 85 | 69 | 48 | 24
2003-04-07 | 90 | 71 | 51 | 24
2003-04-14 | 94 | 76 | 51 | 32
2003-04-21 | 100 | 76 | 58 | 32
2003-04-28 | 111 | 81 | 59 | 35
2003-05-05 | 123 | 102 | 63 | 38
2003-05-12
2003-05-19
2003-05-26
2003-06-02
2003-06-09
2003-06-16
2003-06-23
2003-06-30
2003-07-07
2003-07-14
2003-07-21
2003-07-30
2003-08-08
2003-08-19
2003-08-28
2003-09-08
2003-09-17
2003-09-26
2003-10-07
2003-10-16
2003-10-27
2003-11-05
2003-11-14
2003-11-25
2003-12-04
2003-12-15
2003-12-24
2004-01-02

## ModuleSummary
Module | Hybrid No. | I 4 (mA)@ 500V | I after bond(mA) | Total bad chan | Done | Hybrid Osc? | Module Osc? | Metrology | Good | Pass | Hold | Fail | Rework
P001 | Fail | 0.49433 | 1.8519 |  |  |  |  | Wrong DIMS file loaded |  |  |  | 1
P002 | 20220040200008 | 0.53844 | 4.2558 | 12 | 1 | No | Yes | Module thickness of 0.114 exceeds 0.1 tolerance, shim error |  |  | 1
P003 | 20220040200010 | 0.51463 | 0.71878 | 2 | 1 | No | Yes | b parameter-3.2 |  | 1
P004 | 20220040200009 | 0.73987 | 0.46436 | 14 | 1 | No | Yes | midyf -6.7 |  | 1
P005 | On hold | 0.55987 | 0.42 | On hold |  |  |  | stereo -0.168 vs 0.13,a2 0.147 vs 0.13 |  |  | 1
P006 | 20220040200011 | n/a | 0.69045 | 10 | 1 | No | Yes | midyf -5.4 |  | 1
P007 | 20220040200012 | 0.40218 | 0.62 | 14 | 1 | No | No | midyf -5.7 |  | 1
P008 | 20220040200014 | n/a | 0.78 | 8 | 1 | No | No | In current spec | 1
P009 | 20220040200016 | 0.37187 | 0.40483 | 10 | 1 | No | No | In current spec | 1
P010 | 20220040200017 | 0.33238 | 0.80717 | 5 | 1 | No | Yes | In current spec | 1
P011 | 20220040200018 | 0.3731 | 0.73775 | 11 | 1 | Yes | Yes | midyf -6.4 |  | 1
P012 | 20220040200019 | 0.38631 | 0.70291 | 7 | 1 | No | Yes | midyf -6.4 |  | 1
P013 | 20220040200023 | 0.38611 | 0.83128 | 13 | 1 | No | Yes | In current spec | 1
P014 | 20220040200015 | 0.46025 | 0.99752 | 12 | 1 | No | Yes | upper hybrid height |  |  | 1
P015 | 20220040200020 | 0.41633 | 0.54828 | 12 | 1 | No | Yes | In current spec | 1
P016 | 20220040200037 | 0.34893 | 0.50039 | 2 | 1 | No | Yes | One hybrid height off, shim error |  |  | 1
P017 | 20220040200038 | 0.38399 | 0.38594 | 7 | 1 | No | No | In current spec | 1
P018 | 20220040200028 | 0.39677 | 0.36 | 0.1 | 1 | No | Yes | In current spec | 1
P019 | 20220040200040 | 0.38589 | 0.48 | 0.1 | 1 | No | No | midyf 5.1 |  | 1
P020 | 20220040200024 | 0.331 | 0.33 | 1 | 1 | No | Yes | midyf 7.6 |  | 1
P021 | On hold | 0.33209 | On hold | On hold |  |  |  | stereo .165 |  |  | 1
P022 | Fail | Broken-fixture and procedure changed | [5 empty] | Was in current spec |  |  |  | 1
P023 | 20220040200041 | 0.33336 | 0.71 | 3 | 1 | No | Yes | sepb -15, hybrid has hi-gain chip |  |  | 1
P024 | 20220040200025 | 0.42 | 0.76 | 4 | 1 | No | No | In current spec | 1
P025 | On hold | High | On hold | On hold |  |  |  | sepf -11, no visual explanation for high I on one detector |  |  | 1
P026 | On hold | 0.34 | On hold | On hold |  |  |  | sepf -23 |  |  | 1
P027 | 20220040200042 | 0.35 | 0.37 | 2 | 1 | No | Yes | In current spec | 1
P028 | 20220040200030 | 0.38 | 3 but condition req. | 4 | 1 | No | Yes | In current spec |  |  | 1
P029 | 20220040200032 | 0.39 | 0.59 | 1 | 1 | No | Yes | In current spec | 1
P030 | 20220040200031 | 0.48 | [5 empty] | Hybrid height, remove and reglue |  |  |  |  | 1
Module | Hybrid No. | I 4 (mA)@ 500V | I after bond(mA) | Total bad chan | Done | Hybrid Osc? | Module Osc? | Metrology | Good | Pass | Hold | Fail | Rework
P031 | 20220040200043 | 0.37 | 0.5 | 3 | 1 | No | Yes | In current spec | 1
P032 | 20220040200027 | 0.37 | 0.38 | 0.1 | 1 | No | Yes | In current spec | 1
P033 | 20220040200044 | 0.46 | 0.5 | 0.1 | 1 | No | Yes | In current spec | 1
P034 | 20220040200069 | 0.56 | 0.51 | 0.1 | 1 | No | Yes | In current spec
P035 | 20220040200045 | 0.56 | 0.52 | 0.1 | 1 | No | Yes | In current spec | 1
P036 | 20220040200049 | 2.86 | 0.78 | 0.1 | 1 | No | No | In current spec | 1
P037 | 20220040200051 | 0.59 | 0.63 | 3 | 1 | No | No | In current spec | 1
P038 | 20220040200033 | 0.61 | 0.57 | 0.1 | 1 | No | Yes | In current spec | 1
P039 | 20220040200061 | 0.49 | 0.56 | 0.1 | 1 | No | Yes | In current spec | 1
P040 | 20220040200034 | 0.51 | 0.53 | 3 | 1 | No | Yes | In current spec | 1
P041 | 20220040200053 | 0.43 | 0.44 | 0.1 | 1 | No | No | In current spec | 1
P042 | 20220040200036 | 0.41 | 0.47 | 0.1 | 1 | No | Yes | In current spec | 1
P043 | Fail | Glue leak top side-operator error, procedure changed | [9 empty] | 1
P044 | 20220040200063 | 0.5 | 0.57 | 0.1 | 1 | Yes | Yes | hyb2Gap,hyb2Concavity |  |  | 1
P045 | 20220040200055 | 0.5 | Bonds damaged in hybrid attach |  |  |  |  | In current spec |  |  |  |  | 1
P046 | 20220040200062 | 0.46 | 0.46 | 1 | 1 | No | Yes | In current spec | 1
P047 | 20220040200065 | 0.46 | 0.49 | 1 | 1 | No | Yes | In current spec | 1
P048 | 20220040200070 | 0.44 | 0.46 | 2 |  | No |  | In current spec | 1
P049 | 20220040200013 | 0.45 |  |  |  | No |  | Hybrid heights out |  |  |  |  | 1
P050 | 20220040200072 | 0.49 | 0.53 |  |  | No |  | In current spec
P051 | Started | 0.48 | [5 empty] | In current spec
P052 | Started | 0.35 | [5 empty] | In current spec
P053 | 20220040200071 | 0.37 | 0.4 | 0.1 | 0 | No |  | In current spec | 1
P054 | Started | 0.4 | [5 empty] | In current spec
P055 | Started | 0.4 | [5 empty] | In current spec
P056 | Started | 0.36 | [5 empty] | In current spec
P057 | Started | 0.41 | [5 empty] | In current spec
P058 | Fail | Glue leak top side-operator error, procedure changed | [9 empty] | 1
P059 | Started | 0.36 | [5 empty] | In current spec
P060 | Started | [6 empty] | In current spec
P061 | Started | 0.34 | [5 empty] | midyf 5.5
P062 | Started | [6 empty] | In current spec
P063 | Started | [6 empty] | In current spec
|  |  |  | Modules Completed | 38 |  |  |  | 25 | 8 | 10 | 4 | 3
[8 empty] | Modules Classified | 50
[8 empty] | Good+Pass | 33 |  | 66%
[8 empty] | Good+Pass+Hold | 43 |  | 86%
[8 empty] | Good+Pass+Hold+Rework | 46 |  | 92%
[9 empty] | Good | Pass | Hold | Fail | Rework
Note on C1: Gilchriese: At about 19.8C
Note on D1: Gilchriese: At about 19.8C. Just after bonding.
Note on F1: Gilchriese: All metrology and tests complete.
Note on H1: Gilchriese: L=large osc M=medium S=minimal,small or some No =none
Note on C32: Gilchriese: At about 19.8C
Note on D32: Gilchriese: At about 19.8C. Just after bonding.
Note on F32: Gilchriese: All metrology and tests complete.
Note on H32: Gilchriese: L=large osc M=medium S=minimal,small or some No =none

## XYMetrology
-------------------<Parameters>--------------> | Mhx | Mhy | Msx | Msy | Sepf | Sepb | Midxf | Midyf | Stereo | a1 | a2 | a3 | a4 | hymxf | hymyf | hymaf | hymxb | hymyb | hymab | conp1x | conp1y
--------------------<Units>----------------------> | mm | mm | mm | mm | mm | mm | mm | mm | mrad | mrad | mrad | mrad | mrad | um | um | mrad | um | um | mrad | um | um
--------------------<Tolerances>--------------> | 30 | 30 | 100 | 30 | 10 | 10 | 10 | 5 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 100 | 100 | 3.145 | 100 | 100 | 3.145 | 320.126 | 100
CU-FF-Survey-P001-Aug08-after_glue.xls | 9.7 | -51.3 | 29.2 | -33 | -5.9 | -2.9 | -6.2 | -52.9 | 0.399 | 0.074 | 0.039 | -0.076 | -0.074
CU-FF-Survey-P001-Aug08-after_glue2.xls | 10.2 | -51.1 | 29.7 | -33 | -5.9 | -2.7 | -5.6 | -52.8 | 0.396 | 0.074 | 0.039 | -0.079 | -0.071
CU-FF-Survey-P001-Aug12-after_heat.xls | 11.4 | -51 | 19.6 | -29.1 | -5.7 | -2.8 | -5.3 | -53 | 0.394 | 0.065 | 0.039 | -0.085 | -0.062
CU-FF-H-Survey-P002-Dec05-after_hybrid-test.xls | 0 | 3.3 | 69.8 | 1.5 | -4.5 | -1.1 | -4.7 | 2.4 | -0.05 | 0.018 | 0.059 | -0.012 | -0.029 | 19.157 | 14.002 | 0.377 | -25.923 | -15.191 | -0.023 | 45.306 | 15.367
CU-FF-H-Survey-P002-Sep30-after_hybrid.xls | 1.8 | 3.2 | 44.4 | -2.2 | -6.4 | -2 | -4.7 | 3.3 | -0.057 | 0.044 | 0.056 | -0.018 | -0.022 | 11.849 | 27.232 | 0.677 | -22.445 | -6.242 | -0.234 | 58.842 | 29.691
CU-FF-Survey-P002-Sep25-after_glue.xls | -0.4 | 3.6 | 36.1 | -0.7 | -5.9 | -1.9 | -3.5 | 3.4 | -0.061 | 0.032 | 0.058 | -0.025 | -0.016
CU-FF-Survey-P002-Sep26-after-glue-XXX.xls | 4.6 | 2.6 | 39.3 | 1.2 | -5.7 | -2.1 | -3.7 | 2.1 | 0.014 | 0.02 | 0.051 | -0.014 | -0.015
CU-FF-Survey-P002-Sep26-after_heat.xls | 2.3 | 3.7 | 37 | -0.8 | -5.7 | -2.1 | -3.4 | 2.6 | -0.055 | 0.02 | 0.051 | -0.014 | -0.015
CU-FF-H-Survey-P003-Dec06-after_hybrid-test.xls | -1.3 | 6.2 | 32.3 | 2.1 | -3.5 | -5.4 | -2.7 | -4.7 | -0.111 | -0.032 | 0.047 | -0.069 | -0.016 | 4.316 | 9.664 | -0.161 | -17.605 | -15.651 | 0.04 | -6.879 | 9.083
CU-FF-H-Survey-P003-Oct03-after_hybrid.xls | 0.5 | 7.6 | 0.6 | 9.8 | -4.3 | -7.6 | -1.5 | -3 | -0.12 | -0.008 | 0.053 | -0.078 | -0.017 | 7.985 | 11.52 | -0.227 | -11.563 | -24.601 | 0.16 | -7.771 | 10.702
CU-FF-Survey-P003-Sep30-after-heat.xls | 1 | 6.4 | 22.7 | 5.8 | -4.9 | -7.4 | -2.2 | -3.3 | -0.124 | -0.007 | 0.075 | -0.072 | -0.004
CU-FF-Survey-P003-Sep30-after-heat2-XXX.xls | 2.4 | 6 | 82.7 | 5.9 | -5 | -7.7 | -1 | -4.2 | -0.082 | -0.016 | 0.062 | -0.073 | -0.007
CU-FF-Survey-P003-Sep30-after-heat2.xls | 0.3 | 6.7 | 80.6 | 5.2 | -5 | -7.7 | -2 | -3.6 | -0.114 | -0.016 | 0.062 | -0.073 | -0.007
CU-FF-H-Survey-P004-Dec06-after_hybrid-test.xls | 0.5 | 1 | 13.2 | 5.2 | -5.8 | -0.9 | -2.6 | -6.7 | -0.126 | -0.005 | 0.041 | -0.105 | -0.016 | 8.61 | 21.946 | -0.061 | -0.791 | 0.822 | 0.022 | 4.402 | 21.727
CU-FF-H-Survey-P004-Oct08-after_hybrid.xls | 3 | 2.6 | 50 | 5.6 | -8.4 | -4.5 | -0.5 | -5.9 | -0.136 | 0.016 | 0.05 | -0.105 | -0.025 | 18.102 | 30.733 | 0.018 | -7.638 | -5.412 | -0.045 | 19.333 | 30.797
CU-FF-Survey-P004-Oct03-after-glue.xls | 2.9 | 1.4 | 29.9 | 7.6 | -7.8 | -3.8 | -0.7 | -6.3 | -0.126 | 0.001 | 0.046 | -0.12 | 0.004
CU-FF-Survey-P004-Oct04-after-glue2.xls | 3.4 | 1.9 | 25.3 | 7.7 | -7 | -3.4 | -0.5 | -5.9 | -0.13 | 0.004 | 0.06 | -0.098 | -0.011
CU-FF-Survey-P004-Oct4-after-glue2-XXX.xls | 4.7 | 1.7 | 26.6 | 11.1 | -7 | -3.4 | -2.2 | -5.7 | -0.05 | 0.004 | 0.06 | -0.098 | -0.011
CU-FF-Survey-P005-Oct08-clear-after-heat.xls | -3 | -3 | 34.4 | 7.3 | -10.5 | -7 | -2.5 | -0.5 | -0.168 | 0.092 | 0.147 | -0.033 | -0.002
CU-FF-Survey-P005-Oct09-clear-after-heat2.xls | 0.5 | -3.2 | 11.3 | 7.8 | -9.7 | -6.2 | -2.1 | -0.5 | -0.167 | 0.096 | 0.141 | -0.033 | 0
CU-FF-Survey-P005-Oct09-clear-after-heat3.xls | 1.3 | -3.2 | 31.3 | 7.9 | -9.6 | -6.2 | -1.7 | -0.6 | -0.173 | 0.104 | 0.151 | -0.024 | -0.008
CU-FF-Survey-P005-Oct9-after-heat2-XXX-2.xls | 2.3 | -2.3 | 13.1 | 5.6 | -9.7 | -6.2 | 2.3 | -0.1 | -0.235 | 0.096 | 0.141 | -0.033 | 0
CU-FF-Survey-P005-Oct9-after-heat2-XXX.xls | 2.4 | 6 | 82.7 | 5.9 | -5 | -7.7 | -1 | -4.2 | -0.082 | -0.016 | 0.062 | -0.073 | -0.007
CU-FF-Survey-P005-Oct9-after-heat3-XXX-3.xls | 2.4 | -2 | 32.4 | 5.5 | -9.6 | -6.2 | 2.2 | 0.1 | -0.252 | 0.104 | 0.151 | -0.024 | -0.008
CU-FF-H-Survey-P006-Jan10-after_hybrid-test.xls | 5.8 | -13 | 48.6 | -8.7 | -7.6 | -6.2 | -1.4 | -5.4 | 0.021 | 0.023 | 0.052 | -0.048 | -0.023 | 2.025 | -8.311 | -0.234 | 5.246 | -14.88 | 0.366 | -14.231 | -9.155
CU-FF-Survey-P006-Dec02-afterheat.xls | 6.9 | -12.8 | 29.5 | -1.6 | -7.5 | -5.8 | -1.9 | -5.7 | 0.03 | 0.024 | 0.056 | -0.04 | -0.021
CU-FF-Survey-P006-Nov27-clear.xls | -0.3 | -12.7 | 20.7 | -8.2 | -8 | -5.8 | -2.8 | -5.7 | 0.028 | 0.035 | 0.043 | -0.05 | -0.027
CU-FF-Survey-P006-Nov27-clear2.xls | 1 | -12.5 | 31.4 | -7.7 | -7.6 | -5.5 | -1.5 | -6 | 0.032 | 0.027 | 0.04 | -0.041 | -0.029
CU-FF-H-Survey-P007-Dec12-after_hybrid.xls | 20.8 | -16.7 | 43.3 | 0.2 | -3.4 | -0.6 | 1.2 | -4.8 | 0.024 | 0.045 | 0.024 | -0.074 | 0.001 | 13.484 | -7.26 | 0.065 | 12.951 | -21.174 | 0.137 | 17.977 | -7.026
CU-FF-H-Survey-P007-Jan09-after_hybrid.xls | 26.4 | -21.7 | 67.9 | -5.9 | -3.2 | -0.6 | 0.6 | -5.1 | 0.024 | 0.047 | 0.04 | -0.07 | -0.01 | 3.979 | -22.807 | 0.039 | 10.517 | -16.803 | 0.15 | 6.709 | -22.665
CU-FF-H-Survey-P007-Jan27-after_hybrid-test.xls | 33 | -21.6 | 48.7 | -1.6 | -4.5 | -2.1 | 3.5 | -5.6 | 0.029 | 0.054 | 0.024 | -0.075 | 0.007 | 9.839 | -19.904 | -0.388 | 10.889 | -12.901 | 0.483 | -17.091 | -21.299
CU-FF-Survey-P007-Dec05-clear.xls | 24.1 | -14.5 | 83.7 | 0.9 | -3.2 | -0.7 | 1.2 | -4.6 | 0.021 | 0.053 | 0.032 | -0.076 | 0.009
CU-FF-H-Survey-P008-Dec20-after_hybrid.xls | 2.2 | -13.8 | 1.6 | -9.1 | -0.5 | -4 | 7 | -0.4 | 0.01 | 0.028 | 0.012 | -0.038 | -0.045 | 6.234 | -14.837 | 0.269 | -10.071 | -60.862 | 0.185 | 24.94 | -13.862
CU-FF-H-Survey-P008-Jan13-after_hybrid-test.xls | 9.8 | -13.1 | 54.7 | -7 | -0.7 | -4.5 | 7.2 | -1.3 | 0.011 | 0.025 | 0.02 | -0.039 | -0.024 | 1.43 | -52.034 | 0.1 | -9.427 | -75.874 | 0.24 | 8.358 | -51.674
CU-FF-Survey-P008-Dec13-clear.xls | 7.2 | -9.8 | 78.2 | -6.9 | -0.1 | -3.9 | 7.2 | -1.1 | 0.012 | 0.013 | 0.019 | -0.022 | -0.022
CU-FF-H-Survey-P009-Jan08-after_hybrid.xls | 9.2 | -7 | 16.7 | -7.2 | -2.3 | -2.4 | 0.5 | -3.8 | 0.027 | 0.012 | 0.033 | -0.043 | 0.001 | 4.533 | -8.584 | -0.208 | -7.982 | 6.428 | 0.298 | -9.9 | -9.333
CU-FF-H-Survey-P009-Jan31-after_hybrid-test.xls | 12.5 | -8.2 | 75.9 | -9.9 | -2.9 | -3.6 | 3.7 | -3.2 | 0.024 | 0.018 | 0.024 | -0.037 | -0.002 | -3.156 | -5.695 | -0.445 | -7.62 | 17.846 | 0.456 | -34.083 | -7.297
CU-FF-Survey-P009-Dec23-clear.xls | 9.5 | -8 | 34 | -11.3 | -2.1 | -2.5 | 1.4 | -2.9 | 0.018 | 0.021 | 0.04 | -0.043 | -0.006
CU-FF-H-Survey-P010-Feb04-after_hybrid-test.xls | 6.9 | -17.3 | 64.2 | -5.2 | -0.3 | 0.4 | 3.2 | -3 | 0.026 | 0.08 | 0.051 | -0.024 | 0.023 | 8.504 | -23.746 | -0.185 | 4.286 | 22.451 | 0.426 | -4.333 | -24.413
CU-FF-H-Survey-P010-Jan09-after_hybrid.xls | 6 | -15.8 | 29.1 | -1.8 | -0.3 | 0.9 | 0 | -3.2 | 0.031 | 0.096 | 0.045 | -0.032 | 0.018 | 8.219 | -22.573 | -0.113 | 5.521 | 16.146 | 0.257 | 0.366 | -22.981
CU-FF-Survey-P010-Jan07-clear.xls | 10.8 | -18.6 | 43.8 | 1.4 | -0.4 | 0.5 | -0.2 | -3.7 | 0.029 | 0.062 | 0.064 | -0.043 | 0.029
CU-FF-H-Survey-P011-Feb05-after_hybrid-test.xls | 12.9 | -10.6 | -18.5 | 2.4 | -4.2 | -3.4 | 3.7 | -6.1 | 0.024 | 0.038 | 0.075 | -0.045 | -0.006 | 14.335 | 18.215 | -0.071 | 7.802 | -46.924 | -0.159 | 9.4 | 17.959
CU-FF-H-Survey-P011-Jan14-after_hybrid.xls | 10.8 | -11 | 27.2 | 6.8 | -3.3 | -2.3 | 1.8 | -6.4 | 0.023 | 0.044 | 0.062 | -0.05 | -0.011 | 7.007 | 20.945 | 0.013 | -1.257 | -44.611 | -0.215 | 7.928 | 20.993
CU-FF-Survey-P011-Jan10-clear.xls | 4.4 | -6.8 | 48 | 8.7 | -3.4 | -2.3 | 1.9 | -6.4 | 0.014 | 0.053 | 0.07 | -0.049 | -0.028
CU-FF-H-Survey-P012-Feb05-after_hybrid-test.xls | 19.4 | -6.5 | 0.6 | -1 | -3.6 | -4.6 | 8.8 | -6.6 | 0.02 | 0.064 | 0.008 | -0.051 | -0.069 | 16.571 | -27.191 | -0.062 | 12.496 | -4.629 | -0.221 | 12.233 | -27.417
CU-FF-H-Survey-P012-Jan16-after_hybrid.xls | 19.2 | -10.2 | 35.1 | -5 | -2.4 | -3.5 | 7 | -6.4 | 0.017 | 0.053 | 0.026 | -0.061 | -0.069 | 22.187 | -32.808 | -0.057 | 14.17 | -13.668 | -0.464 | 18.234 | -33.013
CU-FF-Survey-P012-Jan13-clear.xls | 8 | -5.7 | 19.4 | -2.9 | -2.5 | -4.2 | 7 | -6.8 | 0.03 | 0.036 | 0.017 | -0.055 | -0.051
CU-FF-H-Survey-P013-Feb05-after_hybrid-test.xls | 8.1 | -14.6 | 44.9 | 6.4 | -3.9 | -8.1 | 2.5 | 2.9 | 0.016 | 0.041 | 0.032 | 0.006 | 0.037 | 3.161 | -0.732 | -0.226 | 14.213 | 3.243 | 0.198 | -12.503 | -1.545
CU-FF-H-Survey-P013-Jan22-after_hybrid.xls | 6.3 | -18.6 | 45.2 | 3.6 | -3.7 | -7.9 | 3 | 2.7 | 0.014 | 0.038 | 0.037 | 0.005 | 0.021 | 0.222 | -1.405 | -0.149 | 10.006 | 2.326 | 0.23 | -10.096 | -1.94
CU-FF-Survey-P013-Jan15-clear-afterJohn.xls | 15.2 | -18.6 | 102.9 | 5.8 | -3.7 | -8.1 | 3 | 2.7 | 0.015 | 0.048 | 0.03 | -0.007 | 0.038
CU-FF-Survey-P013-Jan15-clear.xls | 18.8 | -15.9 | 82.4 | 6.1 | -3.6 | -6.5 | 0.7 | 3.2 | 0.011 | 0.037 | 0.031 | -0.009 | 0.024
CU-FF-H-Survey-P014-Feb6-after_hybrid-test.xls | 16.6 | -12.1 | 9.4 | -10.7 | -5.6 | -8.4 | 2.5 | 4 | 0.009 | 0.011 | 0.053 | -0.06 | 0.011 | 10.383 | -25.529 | 0.071 | 26.444 | -1.846 | 0.806 | 15.285 | -25.274
CU-FF-Survey-P014-Jan21-clear.xls | 12.8 | -12 | 44.3 | -3 | -6.4 | -8.1 | 3.6 | 3.7 | -0.005 | 0.01 | 0.05 | -0.063 | 0
CU-FF-H-Survey-P015-Jan29-after_hybrid.xls | 12.6 | -11 | -27 | -0.4 | -7.2 | -5.3 | -1.2 | 4.9 | 0.033 | 0.038 | 0.029 | -0.035 | 0.023 | 12.581 | 7.894 | -0.46 | -8.001 | -28.537 | -0.924 | -19.334 | 6.242
CU-FF-H-Survey-P015-March04-after_hybrid-test.xls | 15.8 | -8.6 | 43.9 | 3.3 | -7.2 | -5.1 | 0.7 | 4.8 | 0.03 | 0.042 | 0.023 | -0.045 | 0.02 | 14.137 | 0.481 | -0.473 | -8.128 | -31.109 | -0.881 | -18.684 | -1.218
CU-FF-Survey-P015-Jan23-clear.xls | 17.3 | -10 | -32 | -1.8 | -7 | -4.3 | 0 | 4.5 | 0.032 | 0.032 | 0.027 | -0.053 | 0.018
CU-FF-H-Survey-P016-Feb14-after_hybrid-test.xls | -2.2 | -0.8 | 12.7 | -9.7 | -3.4 | -4 | 10.1 | -1.9 | 0.093 | 0.042 | 0.041 | -0.02 | -0.067 | 5.582 | 12.037 | 0.413 | 13.541 | -59.347 | 0.663 | 34.244 | 13.533
CU-FF-H-Survey-P016-Jan31-after_hybrid.xls | -6.2 | 1.9 | 19.8 | -13.5 | -3.6 | -4.4 | 9.3 | -1.5 | 0.087 | 0.041 | 0.043 | -0.015 | -0.072 | 10.619 | 7.26 | -0.395 | 7.742 | -71.769 | 0.529 | -16.849 | 5.837
CU-FF-Survey-P016-Jan24-clear.xls | 8.4 | -1.8 | 37.8 | -9.6 | -3.8 | -3 | 10.2 | -1.5 | 0.094 | 0.036 | 0.025 | -0.01 | -0.063
CU-FF-H-Survey-P017-Feb03-after_hybrid.xls | 13.1 | -11.9 | 101 | 2 | -4.9 | -4.1 | 0.1 | 3.3 | 0.034 | 0.026 | 0.042 | -0.043 | 0.023 | 4.796 | -8.078 | -0.023 | 11.302 | 39.079 | 0.499 | 3.196 | -8.161
CU-FF-H-Survey-P017-Feb25-after_hybrid-test.xls | 17.4 | -13.8 | 104 | 2.3 | -4.4 | -3.3 | 1.1 | 3.5 | 0.034 | 0.024 | 0.044 | -0.041 | 0.023 | 7.728 | -13.802 | -0.07 | 14.274 | 38.941 | 0.382 | 2.891 | -14.053
CU-FF-Survey-P017-Jan28-clear.xls | 19.4 | -11.3 | 130.8 | 5.5 | -5.1 | -3.3 | 1.3 | 3.2 | 0.034 | 0.024 | 0.021 | -0.048 | 0.02
CU-FF-H-Survey-P018-Feb06-after_hybrid.xls | 13.5 | -10 | 52.6 | -7.9 | -3 | -8.6 | 1.5 | 4.6 | 0.002 | 0.029 | 0.045 | -0.059 | -0.031 | 17.464 | 0.515 | -0.396 | 25.71 | 25.848 | 0.287 | -10.006 | -0.908
CU-FF-H-Survey-P018-Feb25-after_hybrid-test.xls | 12.8 | -7.6 | 42.7 | -3.9 | -2.5 | -8.7 | 1.5 | 4.3 | 0.016 | 0.008 | 0.029 | -0.067 | -0.009 | 12.722 | 3.528 | -0.559 | 26.139 | 27.645 | 0.54 | -26.115 | 1.519
CU-FF-Survey-P018-Jan30-clear.xls | 20.1 | -8.7 | 59.3 | -5 | -3 | -9 | 1.7 | 4.7 | 0.011 | 0.019 | 0.032 | -0.071 | -0.021
CU-FF-H-Survey-P019-Feb11-after_hybrid.xls | 8.3 | -3.4 | -13.1 | -5.2 | -6.4 | -3.2 | 9.2 | 5.1 | 0.107 | 0.018 | 0.086 | -0.007 | -0.062 | -1.841 | -20.299 | 0.062 | -23.261 | 24.02 | -0.753 | 2.435 | -20.076
CU-FF-H-Survey-P019-Feb25-after_hybrid-test.xls | 9.2 | 1.8 | -12.1 | 1.4 | -5.7 | -3 | 8.9 | 5 | 0.106 | 0.014 | 0.082 | -0.009 | -0.068 | -4.834 | -38.613 | -0.056 | -19.95 | 17.216 | -0.439 | -8.724 | -38.815
CU-FF-Survey-P019-Jan30-clear.xls | -2.1 | 1.2 | 42.8 | 8.5 | -6 | -3.1 | 8 | 4.7 | 0.117 | 0.003 | 0.082 | -0.01 | -0.054
CU-FF-H-Survey-P020-Feb19-after_hybrid.xls | 7.8 | 1.1 | 11.9 | -1.8 | -8.5 | -10.6 | -0.1 | 7.2 | 0.024 | 0.073 | 0.034 | -0.083 | 0.012 | 35.21 | 17.143 | -0.147 | 56.446 | -49.278 | -0.199 | 25.029 | 16.614
CU-FF-H-Survey-P020-Mar11-after_hybrid-test.xls | 7.6 | 5.2 | 40.3 | -2.3 | -8.4 | -10.9 | 0.3 | 7.7 | 0.023 | 0.078 | 0.049 | -0.078 | 0.009 | 38.795 | 9.646 | -0.487 | 56.935 | -45.93 | 0.147 | 4.998 | 7.896
CU-FF-Survey-P020-Jan31-clear.xls | 8 | -0.6 | 34.8 | -2.7 | -8 | -10 | 0.8 | 7.6 | 0.026 | 0.081 | 0.039 | -0.082 | 0.017
CU-FF-Survey-P021-Jan31-clear.xls | 5.3 | 5.9 | 32 | 3.3 | -2.4 | 0.4 | 2.5 | 2.1 | 0.165 | 0.049 | 0.118 | -0.016 | -0.026
CU-FF-Survey-P022-Feb03-clear.xls | -7.3 | -21.8 | 8.1 | -32.3 | -10 | -2.5 | -0.5 | 1.9 | 0.009 | 0.008 | 0.069 | -0.015 | 0.049
CU-FF-H-Survey-P023-Feb24-after_hybrid.xls | 17 | -8.2 | 75.2 | 0.5 | -2.5 | -16.5 | 6.5 | -1.5 | 0.022 | 0.002 | 0 | -0.052 | 0.016 | 14.082 | -3.599 | -0.403 | 36.078 | 27.513 | 0.138 | -13.878 | -5.047
CU-FF-H-Survey-P023-Mar12-after_hybrid-test.xls | 16.7 | -7.2 | 21.2 | -1.6 | -2.9 | -16.3 | 5.6 | -4.1 | 0.021 | 0.005 | 0.01 | -0.055 | 0.037 | 9.337 | -0.906 | -0.431 | 25.63 | 33.879 | 0.273 | -20.626 | -2.457
CU-FF-Survey-P023-Feb04-clear.xls | 14.3 | -8.4 | 83.3 | -0.6 | -2.8 | -15.1 | 4.4 | -1.1 | 0.024 | 0.009 | 0.011 | -0.052 | 0.016
CU-FF-H-Survey-P024-Feb27-after_hybrid.xls | 20.4 | 6.6 | 154.6 | 54.9 | -6 | -1 | 5.4 | 1.9 | -0.051 | 0.054 | 0.039 | -0.048 | 0.022 | 5.855 | 10.855 | -0.127 | 27.444 | -7.1 | 0.115 | -2.998 | 10.395
CU-FF-H-Survey-P024-Mar18-after_hybrid-test.xls | 19.7 | 7.1 | 156.3 | 54.8 | -6.2 | -1.3 | 5.1 | 2.4 | -0.052 | 0.048 | 0.04 | -0.04 | 0.021 | 7.505 | 17.601 | -0.159 | 19.73 | -2.566 | 0.079 | -3.531 | 17.027
CU-FF-Survey-P024-Feb07-clear.xls | 22.2 | 6.2 | 128.3 | 56.2 | -6.9 | -1.3 | 5.5 | 2.2 | -0.054 | 0.045 | 0.047 | -0.037 | 0.023
CU-FF-Survey-P024-Feb10-clear-manual.xls | 15.5 | 7.2 | 75.1 | 24.5 | -6.7 | -1.8 | 5.3 | 2 | -0.054 | 0.046 | 0.046 | -0.041 | 0.036
CU-FF-Survey-P024-Feb10-clear.xls | 19.4 | 9.4 | 168.7 | 57.8 | -6.7 | -1.8 | 5.3 | 2 | -0.054 | 0.046 | 0.046 | -0.041 | 0.036
CU-FF-Survey-P025-Metro1-Apr10-clear.xls | 7.6 | -4.8 | 37.5 | -8.6 | -10.4 | -7.6 | 0.4 | 0.3 | 0.004 | 0.024 | 0.042 | -0.017 | -0.018
CU-FF-Survey-P025-Metro2-Apr15-clear.xls | 10.7 | -6.3 | -13.3 | -15.4 | -10.1 | -6.8 | 0.1 | -1.1 | 0.007 | 0.027 | 0.046 | -0.014 | -0.027
CU-FF-Survey-P025-Metro3-Apr15-clear.xls | 11.1 | -4.8 | 56.1 | -8.4 | -10 | -7.5 | -0.4 | -0.5 | 0.013 | 0.012 | 0.051 | -0.024 | -0.014
CU-FF-Survey-P025-Metro4-Apr15-clear.xls | 12.3 | -5 | 34.8 | -14.2 | -10.3 | -6.5 | 0.6 | -0.1 | 0.004 | 0.019 | 0.043 | -0.023 | -0.023
CU-FF-Survey-P025-Feb07-clear.xls | 9.9 | -5.5 | 43.7 | -6.4 | -10.7 | -6.7 | 1.3 | 0.6 | -0.007 | 0.03 | 0.057 | -0.021 | -0.032
CU-FF-Survey-P026-Feb07-clear.xls | 4.3 | 6.5 | 55.9 | 12.8 | -23.1 | -5.7 | 3 | -0.6 | -0.01 | 0.059 | 0.038 | -0.07 | -0.005
CU-FF-H-Survey-P027-Feb27-after_hybrid.xls | 16.2 | -5.3 | 110.5 | 6.5 | 4.7 | 1.8 | 7.9 | -2.3 | 0.029 | -0.015 | 0.021 | -0.068 | -0.013 | 29.943 | 8.366 | -0.423 | 39.651 | 22.041 | -0.157 | 0.567 | 6.845
CU-FF-H-Survey-P027-Mar19-after_hybrid-test.xls | 11 | -2.7 | 1117 | 61.9 | 4.6 | 1.3 | 8.3 | -1.9 | 0.027 | -0.014 | 0.008 | -0.079 | -0.018 | 31.06 | -2.283 | -0.331 | 34.482 | 11.459 | -0.11 | 8.064 | -3.475
CU-FF-Survey-P027-Feb11-clear-manual.xls | 14.5 | -6.5 | 19.5 | 5.7 | 4.1 | 1.7 | 7.8 | -1.9 | 0.026 | -0.023 | 0.013 | -0.082 | -0.019
CU-FF-Survey-P027-Feb11-clear.xls | 13.4 | -5.6 | 431.9 | -44.3 | 4.1 | 1.7 | 7.8 | -1.9 | 0.026 | -0.023 | 0.013 | -0.082 | -0.019
CU-FF-H-Survey-P028-Feb28-after_hybrid.xls | 9.6 | 6.2 | 61.1 | -1.7 | 1.8 | 2.3 | 6.7 | 0.5 | -0.002 | 0.001 | -0.004 | -0.047 | 0.014 | 6.447 | -8.929 | -0.125 | -8.163 | 15.652 | 0.216 | -2.244 | -9.381
CU-FF-H-Survey-P028-Mar26-after_hybrid-test.xls | 8.1 | 5.2 | 53 | 1.1 | 1.7 | 1.7 | 5.8 | 0.7 | 0.023 | 0.006 | 0 | -0.042 | 0.023 | 6.262 | -4.845 | -0.177 | -12.263 | 27.082 | 0.359 | -6.04 | -5.484
CU-FF-Survey-P028-Feb21-clear.xls | 9.9 | 4.7 | 44 | 5.4 | 1.6 | 2.3 | 4.7 | 0.1 | 0.023 | 0.004 | 0.008 | -0.034 | 0.014
CU-FF-H-Survey-P029-Mar20-after_hybrid-test.xls | 22.1 | -12.6 | 90.3 | 7.9 | 3 | 1.8 | 2.1 | 0.9 | 0.045 | 0.019 | 0.02 | -0.024 | 0.005 | 2.996 | -15.418 | 0.544 | 9.927 | 24.883 | 0.255 | 40.745 | -13.445
CU-FF-H-Survey-P029-March04-after_hybrid.xls | 16.5 | -8.8 | 27.6 | 1 | 3.6 | 2.7 | 1.4 | 0.5 | 0.043 | 0.02 | 0.016 | -0.05 | -0.006 | 0.999 | -13.009 | 0.451 | 9.393 | 23.737 | 0.24 | 32.303 | -11.374
CU-FF-Survey-P029-Feb27-clear.xls | 30 | -9.3 | 97.8 | 3.8 | 3.5 | 3.4 | 1.9 | 0.4 | 0.041 | 0.02 | 0.015 | -0.035 | -0.011
CU-FF-H-Survey-P030-March11-after_hybrid.xls | 22.4 | -9.8 | 88.5 | 49.9 | 7.1 | 0.8 | 1.6 | 2.5 | 0.02 | -0.009 | 0 | -0.016 | -0.037 | 14.174 | -31.071 | 0.52 | -22.962 | -45.295 | 0.177 | 50.268 | -29.184
CU-FF-Survey-P030-March04-clear.xls | 15.8 | -11.5 | 107.4 | 39.9 | 7.1 | 1.8 | 1.3 | 1.6 | 0.035 | -0.004 | -0.004 | -0.012 | -0.035
CU-FF-H-Survey-P031-April02-after_hybrid-test-newslot.xls | 11.9 | -7.7 | 49.5 | -29.3 | 0.1 | 0.8 | 3.5 | 0.1 | -0.018 | 0.004 | 0.016 | -0.087 | -0.034 | 2.123 | 10.152 | -0.216 | -3.723 | 20.527 | 0.319 | -12.89 | 9.373
CU-FF-H-Survey-P031-April02-after_hybrid-test.xls | 14.2 | -13.4 | 118.3 | -13.7 | 0.2 | 1.1 | 2.8 | 0 | -0.009 | 0.005 | 0.015 | -0.093 | -0.042 | -2.217 | 9.29 | -0.189 | -2.26 | 17.758 | 0.23 | -15.356 | 8.608
CU-FF-H-Survey-P031-March10-after_hybrid.xls | 12 | -9.2 | 108.3 | -14.5 | 0.4 | 1.5 | 3.5 | -0.1 | -0.017 | 0.007 | 0.02 | -0.089 | -0.043 | -3.65 | 22.255 | 0.045 | -6.735 | 21.993 | 0.301 | -0.52 | 22.418
CU-FF-H-Survey-P031-March24-after_hybrid-test.xls | 14.2 | -13.4 | 118.3 | -13.7 | 0.2 | 1.1 | 2.8 | 0 | -0.009 | 0.005 | 0.015 | -0.093 | -0.042 | -2.217 | 9.29 | -0.189 | -2.26 | 17.758 | 0.23 | -15.356 | 8.608
CU-FF-Survey-P031-March04-clear.xls | 7.3 | -5.1 | 85.7 | -13.4 | 0.5 | 2.2 | 3.4 | -0.3 | -0.003 | -0.002 | 0.007 | -0.085 | -0.032
CU-FF-H-Survey-P032-Apr04-after_hybrid-test.xls | 7.6 | 3 | 21.7 | 2.8 | 0.9 | 0.2 | 2.2 | 1.7 | 0 | 0.05 | 0.049 | 0.005 | 0.012 | 2.218 | 2.041 | -0.605 | 20.332 | 23.873 | 0.527 | -39.78 | -0.13
CU-FF-H-Survey-P032-March18-after_hybrid.xls | 8.5 | 3.6 | 81.1 | 3 | 1.1 | 1 | 2.5 | 1.8 | -0.003 | 0.048 | 0.046 | 0.016 | 0.017 | 2.078 | 3.884 | -0.563 | 16.539 | 19.944 | 0.528 | -36.996 | 1.863
CU-FF-Survey-P032-March06-clear.xls | 8.7 | 1 | 55.7 | 2 | 2.2 | 2.4 | 2.3 | 1.7 | 0.004 | 0.039 | 0.058 | 0.009 | 0.024
CU-FF-H-Survey-P033-Apr02-after_hybrid-test.xls | -3.3 | -11.2 | 35.3 | -17.2 | 1.1 | -2.2 | 1.2 | 0.6 | 0.007 | 0.022 | 0.044 | -0.071 | -0.029 | 10.96 | 0.361 | -0.241 | 0.531 | -3.881 | 0.139 | -5.762 | -0.507
CU-FF-H-Survey-P033-April02-after_hybrid-newslot.xls | -4 | -12.7 | 74 | -23.7 | 1.4 | -1.4 | 1.4 | 0.8 | 0.006 | 0.014 | 0.035 | -0.061 | -0.03 | 0.85 | -3.773 | -0.166 | -22.375 | -44.212 | 0.147 | -10.685 | -4.372
CU-FF-H-Survey-P033-March17-after_hybrid.xls | -4 | -12.7 | 165.5 | -26.4 | 1.4 | -1.4 | 1.4 | 0.8 | 0.006 | 0.014 | 0.035 | -0.061 | -0.03 | 0.85 | -3.773 | -0.166 | -22.375 | -44.212 | 0.147 | -10.685 | -4.372
CU-FF-Survey-P033-March07-clear.xls | 19.2 | -18.2 | 140.4 | -21.1 | 1.2 | -1.4 | 1.1 | 0 | 0.01 | 0.02 | 0.035 | -0.056 | -0.036
CU-FF-H-Survey-P034-Apr28-after_hybrid-test.xls | 12.2 | -8 | 45.8 | -7.6 | 3.2 | 1.6 | -0.6 | 2.8 | 0.046 | 0.05 | 0.039 | -0.02 | -0.009 | 12.04 | 28.544 | -0.437 | 38.643 | -34.147 | -0.063 | -18.333 | 26.971
CU-FF-H-Survey-P034-April17-after_hybrid.xls | 11.3 | -9.5 | 102 | -9.1 | 2.7 | 1.2 | -0.3 | 2.8 | 0.061 | 0.014 | -0.081 | -0.02 | -0.006 | 8.285 | 13.762 | -0.492 | 38.038 | -20.893 | 0.373 | -25.915 | 11.992
CU-FF-Survey-P034-Apr03-clear.xls | 12.8 | -6.6 | 55.6 | 2.2 | 3.5 | 2.1 | 1 | 3.6 | 0.051 | 0.046 | 0.033 | -0.021 | -0.008
CU-FF-H-Survey-P035-Apr08-after_hybrid-test.xls | 25.6 | 3 | 85.1 | 19.4 | -3.5 | -4.2 | -6.4 | 3.9 | -0.042 | 0.05 | 0.042 | -0.054 | -0.043 | -3.189 | 9.603 | -0.308 | 23.714 | 30.686 | 0.617 | -24.599 | 8.493
CU-FF-H-Survey-P035-March25-after_hybrid.xls | 27 | 3.2 | 78.7 | 20.2 | -3.2 | -3.5 | -5.4 | 4.6 | -0.042 | 0.051 | 0.038 | -0.051 | -0.037 | -3.565 | 6.823 | -0.097 | 27.192 | 20.563 | 0.329 | -10.333 | 6.471
CU-FF-Survey-P035-March10-clear.xls | 23.4 | 2.3 | 36.4 | 23.3 | -3.2 | -2.9 | -5.7 | 3.9 | -0.034 | 0.043 | 0.024 | -0.062 | -0.016
CU-FF-H-Survey-P036-Apr04-after_hybrid-test.xls | 7.6 | 3 | 21.7 | 2.8 | 0.9 | 0.2 | 2.2 | 1.7 | 0 | 0.05 | 0.049 | 0.005 | 0.012 | 2.218 | 2.041 | -0.605 | 20.332 | 23.873 | 0.527 | -39.78 | -0.13
CU-FF-H-Survey-P036-March21-after_hybrid.xls | 8.1 | -24.2 | 54 | -18.3 | -0.6 | -2.3 | 5 | 1.4 | 0.05 | 0.03 | 0.051 | -0.03 | 0.025 | 1.265 | -0.962 | -0.068 | -20.499 | 37.629 | 0.374 | -3.427 | -1.206
CU-FF-Survey-P036-March10-clear.xls | 5 | -22.8 | 20.8 | -16.5 | -0.5 | -2 | 5.1 | 1.1 | 0.046 | 0.024 | 0.037 | -0.045 | 0.013
CU-FF-H-Survey-P037-Apr02-after_hybrid-test-newslot.xls | 23.5 | -3.4 | -38 | 14.4 | -3 | 0 | -4 | 2.6 | 0.011 | 0.075 | 0.049 | -0.028 | -0.009 | -7.588 | -12.222 | 0.212 | 10.491 | -16.544 | 0.719 | 7.156 | -11.453
CU-FF-H-Survey-P037-Apr02-after_hybrid-test.xls | 23.5 | -3.4 | 89 | 32.8 | -3 | 0 | -4 | 2.6 | 0.011 | 0.075 | 0.049 | -0.028 | -0.009 | -7.588 | -12.222 | 0.212 | 10.491 | -16.544 | 0.719 | 7.156 | -11.453
CU-FF-H-Survey-P037-Apr08-after_hybrid-test.xls | 24.1 | -4.3 | 151.5 | 28.5 | -3.9 | -0.8 | -4.7 | 2.9 | 0.015 | 0.079 | 0.042 | -0.037 | -0.009 | -6.523 | -29.449 | 0.094 | 3.541 | -16.654 | 1.032 | 0.036 | -29.107
CU-FF-H-Survey-P037-March21-after_hybrid.xls | 22.2 | -4.2 | 14 | 33.6 | -3.3 | 0.3 | -4.3 | 2.7 | 0.01 | 0.087 | 0.053 | -0.034 | -0.014 | -3.475 | -33.856 | 0.115 | 9.495 | -26.902 | 0.888 | 4.481 | -33.442
CU-FF-Survey-P037-March12-clear.xls | 22.3 | -3.1 | 53.9 | -43.8 | -3.8 | 0.7 | -5 | 2.8 | 0.015 | 0.085 | 0.039 | -0.027 | -0.018
CU-FF-H-Survey-P038-Apr07-after_hybrid-test.xls | 10.9 | -15 | 45.5 | -15.9 | -4.1 | -2.2 | 0.5 | 1 | 0.034 | 0.035 | 0.044 | -0.043 | -0.059 | -6.301 | 17.066 | -0.809 | 2.007 | 21.212 | 0.633 | -62.467 | 14.168
CU-FF-H-Survey-P038-March26-after_hybrid.xls | 11 | -15.7 | 164.1 | -21.4 | -3.6 | -1 | -0.3 | 1.2 | 0.045 | 0.036 | 0.03 | -0.041 | -0.063 | 2.059 | 14.601 | -0.534 | -3.752 | 13.522 | 0.686 | -35.048 | 12.681
CU-FF-Survey-P038-March12-clear.xls | 10.8 | -13.7 | 49.7 | -11.1 | -3.5 | -0.5 | 0.6 | 1.7 | 0.033 | 0.025 | 0.033 | -0.053 | -0.055
CU-FF-H-Survey-P039-Apr08-after_hybrid-test.xls | 17.4 | -7.8 | 46.4 | 1.8 | 1.2 | 0.5 | -6.7 | 1.3 | 0.02 | 0.009 | 0.03 | -0.049 | -0.041 | -10.373 | -14.261 | -0.23 | 4.814 | 9.132 | 1.084 | -26.329 | -15.089
CU-FF-H-Survey-P039-March25-after_hybrid.xls | 15.8 | -7.9 | 38.5 | 0.6 | 1.4 | 1.2 | -7.9 | 0.9 | 0.03 | 0 | 0.027 | -0.042 | -0.023 | -6.959 | -13.122 | -0.127 | 9.056 | 2.263 | 0.84 | -15.799 | -13.581
CU-FF-Survey-P039-March14-clear.xls | 14 | -6.5 | -9.6 | 5.3 | 1.5 | 2.1 | -7 | 0.8 | 0.028 | -0.007 | 0.022 | -0.038 | -0.027
CU-FF-H-Survey-P040-Apr09-after_hybrid-test.xls | 6.3 | -22.6 | 40.3 | -25.7 | -6.8 | -0.4 | 1.7 | 0.6 | 0.028 | -0.018 | 0.005 | -0.083 | -0.023 | 9.508 | 6.693 | 0.163 | 5.933 | 16.819 | 0.829 | 20.818 | 7.283
CU-FF-H-Survey-P040-March31-after_hybrid.xls | 5.5 | -23.3 | 45.7 | -25.3 | -6.6 | -0.3 | 1.5 | 0.1 | 0.031 | -0.018 | -0.008 | -0.072 | -0.031 | 12.757 | 4.022 | 0.077 | 7.074 | 13.769 | 0.763 | 18.103 | 4.3
CU-FF-Survey-P040-March17-clear.xls | 5.4 | -26.2 | -13.5 | -9.2 | -6.2 | 0.5 | 1 | 0.7 | 0.024 | -0.014 | 0.002 | -0.074 | -0.021
CU-FF-H-Survey-P041-Apr07-after_hybrid.xls | 8.8 | 1 | 36.6 | 1 | 1.8 | -5.5 | -4.3 | 4.8 | 0.047 | 0.037 | -0.026 | -0.011 | -0.003 | 8.288 | 23.117 | 0.012 | 10.757 | 18.856 | 1.019 | 9.142 | 23.161
CU-FF-H-Survey-P041-Apr23-after_hybrid-test.xls | 8.5 | -0.3 | 31.6 | -1.3 | 1.6 | -5.2 | -4.6 | 4.4 | 0.04 | 0.027 | -0.015 | -0.02 | -0.017 | 10.393 | 12.279 | -0.073 | 13.227 | 8.666 | 1.095 | 5.296 | 12.014
CU-FF-Survey-P041-March18-clear.xls | -3.7 | 1.8 | 0.4 | 0 | 2.3 | -3.5 | -4.2 | 5 | 0.029 | 0.044 | -0.023 | -0.02 | -0.044
CU-FF-H-Survey-P042-Apr08-after_hybrid.xls | -13.5 | -15.3 | 28 | -23 | -4 | 3.2 | -7.2 | 1.5 | 0.029 | 0.025 | 0.043 | 0.004 | -0.001 | -12.97 | 18.708 | -0.077 | 0.7 | 14.472 | 0.812 | -18.319 | 18.43
CU-FF-H-Survey-P042-Apr23-after_hybrid-test.xls | -14.9 | -16.8 | 23.9 | -19 | -3.6 | 3 | -7.9 | 0.8 | 0.033 | 0.016 | 0.042 | 0.001 | 0.001 | -11.218 | 5.543 | -0.326 | -0.896 | 12.057 | 0.807 | -33.825 | 4.371
CU-FF-Survey-P042-March20-clear.xls | -9 | -16.9 | 38.7 | -19.7 | -3.2 | 3.7 | -7.1 | 1.7 | 0.028 | 0.021 | 0.05 | 0.003 | 0.008
CU-FF-Survey-P043-March20-clear.xls | 6.7 | -6.8 | 40.6 | -4.6 | -0.6 | 7 | 1.7 | 2.5 | -0.014 | 0.059 | 0.038 | -0.025 | -0.035
CU-FF-H-Survey-P044-Apr10-after_hybrid.xls | -4.6 | -3.4 | 34.6 | -19.8 | 0.5 | -1 | -1.4 | 3.4 | -0.012 | -0.024 | 0 | -0.045 | -0.098 | 2.498 | 2.37 | -0.464 | 17.142 | 23.673 | 0.359 | -29.752 | 0.701
CU-FF-H-Survey-P044-Apr24-after_hybrid-test.xls | -7.2 | -7.4 | 29.3 | -22.1 | 0.1 | -1.4 | -2.7 | 2.3 | -0.007 | -0.033 | -0.004 | -0.048 | -0.099 | 5.279 | -8.476 | -0.358 | 15.969 | 15.839 | 0.394 | -19.613 | -9.766
CU-FF-Survey-P044-March26-clear.xls | -5.6 | -1.2 | 27.9 | -19.5 | 1.3 | -1 | -1.8 | 3.8 | -0.008 | -0.019 | -0.008 | -0.035 | -0.098
CU-FF-H-Survey-P045-Apr17-after_hybrid.xls | -0.1 | -6.5 | 189.8 | -6.8 | -1.5 | -3 | -4 | 2.5 | 0.027 | 0.018 | 0.008 | -0.043 | -0.038 | -6.756 | -35.018 | -0.697 | -6.286 | -7.191 | 0.134 | -55.182 | -37.519
CU-FF-Survey-P045-March28-clear.xls | -3.9 | 4.7 | 54 | -0.1 | -0.7 | -1.8 | -3.6 | 3.2 | 0.035 | 0.008 | 0.008 | -0.03 | -0.038
CU-FF-H-Survey-P046-Apr21-after_hybrid.xls | 10.5 | -0.9 | 61.5 | 9.4 | 3.8 | -2.5 | 4.3 | -0.3 | 0.038 | 0.093 | 0.027 | -0.027 | 0.028 | 2.952 | 30.583 | -0.231 | -7.13 | 34.927 | 0.098 | -13.107 | 29.75
CU-FF-H-Survey-P046-Apr29-after_hybrid-test.xls | 5.1 | 1.7 | 38.6 | 9 | 2.7 | -2.8 | 1.6 | -0.6 | 0.046 | 0.092 | 0.016 | -0.023 | 0.009 | 1.221 | -3.93 | -0.084 | 19.471 | -21.479 | 0.279 | -4.632 | -4.234
CU-FF-Survey-P046-March28-clear.xls | 8 | 3.4 | 40.1 | 5.2 | 3.1 | -1.9 | 3.3 | 1.2 | 0.034 | 0.096 | 0.012 | -0.033 | -0.023
CU-FF-H-Survey-P047-Apr22-after_hybrid.xls | -19.5 | -14.3 | -10.3 | -24.4 | -3.5 | 6.8 | -0.3 | 3.6 | 0.001 | -0.003 | 0.002 | -0.075 | -0.037 | 5.101 | -10.289 | -0.172 | -25.39 | 31.106 | -0.116 | -6.828 | -10.908
CU-FF-H-Survey-P047-Apr29-after_hybrid-test.xls | -20.4 | -12.1 | 2.7 | -20.2 | -3.9 | 6 | -1 | 3.2 | 0.006 | -0.01 | -0.005 | -0.087 | -0.042 | 0.682 | -10.85 | -0.088 | -26.097 | 24.896 | -0.188 | -5.448 | -11.168
CU-FF-Survey-P047-April01-clear.xls | -15.9 | -11.9 | 18.6 | -22.3 | -3.7 | 6.7 | 2 | 4.4 | 0 | -0.005 | 0.011 | -0.082 | -0.045
CU-FF-H-Survey-P048-Apr23-after_hybrid.xls | 13.4 | -15.9 | 76.3 | 6.8 | 0.4 | 1 | -2.2 | 0.5 | 0.02 | 0.027 | 0.04 | -0.019 | -0.009 | 1.309 | -20.955 | -0.109 | -7.833 | 6.558 | 0.546 | -6.257 | -21.348
CU-FF-Survey-P048-April01-clear.xls | 13.6 | -15.2 | 75.6 | 7.3 | 0.8 | 1.4 | -1.1 | 1.8 | 0.023 | 0.025 | 0.04 | -0.004 | -0.001
CU-FF-H-Survey-P049-Apr25-after_hybrid.xls | -7.5 | -15.1 | 46.2 | -22.4 | 0.8 | 1 | -5.1 | 4 | 0.033 | 0.045 | -0.01 | -0.078 | -0.064 | -3.773 | -2.225 | 0.436 | -28.099 | 50.039 | 1.095 | 26.473 | -0.646
CU-FF-Survey-P049-Apr03-clear.xls | -9.6 | -12.8 | 27.5 | -26 | 1.7 | 1.2 | -5.3 | 4.8 | 0.034 | 0.053 | -0.017 | -0.08 | -0.063
CU-FF-H-Survey-P050-Apr30-after_hybrid.xls | -0.9 | 1.1 | 37.9 | 5 | -3 | 5.8 | 1.2 | 0.1 | 0.033 | 0.054 | 0.052 | 0.035 | -0.015 | -4.356 | 22.589 | -0.494 | 2.35 | 5.514 | 0.69 | -38.663 | 20.813
CU-FF-Survey-P050-Apr07-clear.xls | 4.4 | 3.3 | 38.7 | 4 | -3.2 | 5.7 | 2.2 | 1.4 | 0.02 | 0.057 | 0.044 | 0.03 | -0.022
CU-FF-Survey-P051-Apr07-clear.xls | -10.6 | 6.8 | 64.4 | -2.2 | -1 | 4 | -2.1 | 1.1 | 0.026 | 0.008 | -0.013 | -0.006 | 0.015
CU-FF-Survey-P052-Apr21-clear.xls | 7.2 | 3.5 | 43.5 | 6.8 | 6.5 | 3.6 | 0 | 0.3 | 0.032 | 0.054 | -0.035 | -0.048 | -0.027
CU-FF-H-Survey-P053-Apr25-after_hybrid.xls | -6.4 | -8.8 | 29.1 | -11 | 2.7 | 2.3 | 4.2 | -0.7 | 0.048 | 0.002 | 0.011 | -0.048 | -0.04 | 1.939 | 1.532 | 0.057 | -23.697 | 52.219 | 0.555 | 5.926 | 1.739
CU-FF-Survey-P053-Apr18-clear.xls | -6.9 | -3.9 | 26.8 | -9.5 | 3.3 | 1.9 | 5.3 | 0.1 | 0.042 | 0.021 | 0.01 | -0.06 | -0.041
CU-FF-Survey-P054-Apr18-clear.xls | 2.5 | 10 | 36.5 | 6.3 | 3.9 | -0.5 | -1.8 | -1.6 | -0.011 | 0.075 | 0.014 | 0.022 | 0.001
CU-FF-Survey-P055-May01-clear.xls | 6.7 | -0.6 | 59.3 | 11.7 | -0.8 | -1.6 | 2.4 | 0.9 | 0.041 | -0.009 | -0.043 | -0.049 | 0.001
CU-FF-Survey-P056-Apr22-clear.xls | -12.8 | -3.9 | 21.6 | -14.6 | -0.7 | 1.1 | -5.9 | 2.3 | 0.039 | 0.048 | -0.005 | -0.067 | -0.025
CU-FF-Survey-P057-Apr22-clear.xls | 1.7 | 6.6 | 40.1 | 1.1 | 0 | -0.7 | -1.1 | -2.9 | -0.047 | 0.054 | 0.041 | 0.03 | 0.001
CU-FF-Survey-P058-Apr22-clear.xls | 17.3 | -9.2 | 66.5 | -1.7 | 0.2 | -2.4 | -2.3 | 2.4 | -0.033 | -0.067 | 0.031 | -0.005 | -0.026
CU-FF-Survey-P059-May02-clear.xls | 1.6 | 5.7 | -15.6 | 0.8 | 2.2 | 0.9 | -3 | -0.3 | 0.032 | 0.006 | -0.013 | -0.021 | -0.007
CU-FF-Survey-P060-May01-clear.xls | 5.1 | 12.1 | 19.7 | 10.9 | 0.3 | 1.1 | 2.9 | 0.1 | -0.026 | -0.025 | -0.03 | -0.003 | -0.013
CU-FF-Survey-P061-May01-clear.xls | 20.1 | -8.2 | 68.9 | 1.4 | 1.7 | 3.8 | -3.2 | 5.5 | -0.029 | -0.042 | -0.058 | -0.016 | -0.026

## Zmetrology
-------------------<Parameters>--------------> | maxZlower | maxZupper | moduleThickness | optimalMaxZerrorLower | optimalMaxZerrorUpper | optimalRMSZerrorLower | optimalRMSZerrorUpper | loCoolingFacing-a | b | loCoolingFacingConcavity | capMaxThickness | hyb1LeftNearH | hyb1RightNearH | hyb1LeftFarH | hyb1RightFarH | hyb2LeftNearH | hyb2RightNearH | hyb2LeftFarH | hyb2RightFarH | hyb1Concavity | hyb2Concavity | hyb1Gap | hyb2Gap | hyb1CapMaxH | hyb2CapMaxH | hybridMaxThickness
-------------------<Units>------------------------> | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mrad] | [mrad] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm]
--------------------<Tolerances>--------------> | -0.2 | 0.2 | 0.1 | 0.05 | 0.05 | 0.025 | 0.025 | 0.5 | 3 | 0.03 | 0.66 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.15 | 0.15 | 0.2 | 0.2 | 0.3 | 0.3 | 0.44
surveyZ-241-P001-Aug08-after_glue.xls | -0.012 | 0.031 | 0.095 | 0.035 | 0.023 | 0.01 | 0.009 | 0.058 | -2.848 | 0.02
surveyZ-241-P001-Aug12-after_heat.xls | -0.02 | 0.023 | 0.094 | 0.037 | 0.021 | 0.011 | 0.009 | 0.105 | -3.403 | 0.025
surveyZ-241-P002-Dec05-after_hybrid-test.xls | -0.05 | 0.001 | 0.114 | 0.024 | 0.022 | 0.009 | 0.008 | 0.126 | -1.707 | 0 | -0.056 | -0.099 | -0.099 | -0.12 | -0.104 | -0.101 | -0.01 | -0.078 | -0.019 | 0.005 | 0.034 | -0.101 | -0.018 | -0.068 | 0.004 | -0.099
surveyZ-241-P002-Sep25-after_glue.xls | -0.012 | 0.002 | 0.114 | 0.025 | 0.024 | 0.009 | 0.008 | 0.103 | -1.4 | 0.006
surveyZ-241-P002-Sep26-after_heat.xls | -0.03 | -0.005 | 0.111 | 0.029 | 0.027 | 0.01 | 0.008 | 0.124 | -1.839 | 0.007
surveyZ-241-P002-Sept30-after_hybrid.xls | -0.021 | -0.003 | 0.116 | 0.027 | 0.024 | 0.009 | 0.008 | 0.074 | -0.711 | 0.003 | -0.071 | -0.097 | -0.101 | -0.111 | -0.077 | -0.112 | -0.02 | -0.094 | -0.058 | 0.007 | 0.016 | -0.089 | -0.054 | -0.057 | -0.024 | -0.109
surveyZ-241-P003-Dec06-after_hybrid-test.xls | -0.068 | 0.003 | 0.02 | 0.027 | 0.037 | 0.012 | 0.01 | 0.037 | -3.193 | 0.024 | -0.028 | -0.054 | -0.077 | -0.075 | -0.053 | 0.019 | 0.162 | -0.105 | -0.079 | 0.005 | 0.079 | -0.06 | 0.078 | -0.004 | -0.033 | 0.096
surveyZ-241-P003-Oct03-after_hybrid.xls | -0.069 | 0.001 | 0.019 | 0.029 | 0.039 | 0.012 | 0.011 | 0.094 | -4.091 | 0.034 | -0.037 | -0.051 | -0.081 | -0.079 | -0.073 | 0.011 | 0.15 | -0.109 | -0.08 | 0.006 | 0.084 | -0.065 | 0.077 | -0.014 | -0.035 | 0.084
surveyZ-241-P003-Sep30-after_heat.xls | -0.052 | 0.003 | 0.019 | 0.03 | 0.04 | 0.012 | 0.011 | -0.041 | -1.677 | -0.004
surveyZ-241-P004-Dec06-after_hybrid-test.xls | -0.003 | 0.026 | 0.017 | 0.029 | 0.03 | 0.01 | 0.01 | -0.034 | -0.437 | -0.007 | -0.001 | -0.11 | -0.043 | -0.101 | -0.055 | -0.071 | 0.053 | -0.041 | -0.015 | 0.003 | 0.037 | -0.074 | 0.018 | -0.032 | 0.021 | 0.018
surveyZ-241-P004-Oct03-after_glue.xls | -0.002 | 0.021 | 0.019 | 0.037 | 0.039 | 0.012 | 0.011 | -0.005 | -1.682 | 0.001
surveyZ-241-P004-Oct08-after_hybrid.xls | -0.001 | 0.019 | 0.019 | 0.036 | 0.037 | 0.011 | 0.011 | -0.064 | -0.574 | -0.004 | 0.004 | -0.115 | -0.048 | -0.108 | -0.062 | -0.072 | 0.055 | -0.043 | -0.018 | 0.006 | 0.042 | -0.077 | 0.023 | -0.034 | 0.028 | 0.013
surveyZ-241-P005-Oct08-clear-after-heat.xls | -0.04 | 0.001 | 0.015 | 0.031 | 0.032 | 0.011 | 0.01 | 0.019 | -1.578 | 0.004
surveyZ-241-P006-Dec02-afterheat.xls | -0.006 | 0.021 | 0.052 | 0.03 | 0.024 | 0.01 | 0.009 | 0.03 | -0.787 | -0.003
surveyZ-241-P006-Jan10-after_hybrid-test.xls | -0.011 | 0.025 | 0.051 | 0.025 | 0.026 | 0.009 | 0.009 | -0.114 | 2.278 | -0.017 | -0.096 | -0.063 | -0.063 | -0.094 | -0.07 | -0.078 | -0.067 | -0.051 | -0.077 | -0.021 | -0.001 | -0.093 | -0.069 | -0.058 | -0.037 | -0.119
surveyZ-241-P006-Nov27-clear.xls | -0.005 | 0.047 | 0.051 | 0.025 | 0.029 | 0.009 | 0.009 | 0.034 | -0.889 | -0.003
surveyZ-241-P007-Dec05-clear.xls | -0.027 | 0.009 | 0.033 | 0.032 | 0.024 | 0.011 | 0.008 | 0.026 | -2.091 | 0.011
surveyZ-241-P007-Dec12-after_hybrid.xls | -0.064 | 0.02 | 0.036 | 0.036 | 0.021 | 0.012 | 0.009 | -0.082 | 1.737 | -0.005 | -0.003 | -0.062 | -0.006 | -0.101 | -0.029 | 0.168 | 0.395 | -0.102 | -0.032 | 0.016 | 0.19 | -0.033 | 0.297 | 0.023 | -0.02 | 0.381
surveyZ-241-P007-Jan09-after_hybrid.xls | -0.074 | 0.042 | 0.034 | 0.038 | 0.026 | 0.012 | 0.009 | -0.139 | 2.429 | -0.007 | -0.003 | -0.066 | -0.01 | -0.275 | 0.002 | -0.053 | -0.031 | -0.122 | -0.068 | 0.066 | 0.105 | -0.021 | 0.036 | 0.057 | -0.053 | -0.046
surveyZ-241-P007-Jan27-after_hybrid-test.xls | -0.088 | 0.026 | 0.032 | 0.042 | 0.027 | 0.013 | 0.009 | -0.062 | 0.902 | -0.003 | 0.004 | -0.059 | -0.005 | -0.105 | -0.01 | -0.045 | -0.028 | -0.104 | -0.043 | 0.021 | 0.027 | -0.024 | -0.028 | 0.04 | -0.031 | -0.036
surveyZ-241-P008-Jan13-after_hybrid-test.xls | -0.047 | -0.001 | 0.023 | 0.028 | 0.021 | 0.009 | 0.007 | -0.001 | -0.274 | -0.002 | -0.075 | -0.082 | -0.105 | -0.114 | -0.107 | -0.056 | -0.109 | -0.069 | -0.104 | 0.028 | 0.033 | -0.074 | -0.052 | -0.057 | -0.015 | -0.039
surveyZ-241-P008-Dec16-clear.xls | -0.049 | -0.002 | 0.018 | 0.03 | 0.022 | 0.009 | 0.007 | 0.033 | -0.844 | 0.002
surveyZ-241-P008-Dec20-after_hybrid.xls | -0.039 | 0 | 0.023 | 0.03 | 0.025 | 0.009 | 0.008 | -0.008 | 0.293 | -0.005 | -0.071 | -0.084 | -0.102 | -0.108 | -0.1 | -0.054 | -0.1 | -0.072 | -0.102 | 0.02 | 0.026 | -0.079 | -0.056 | -0.054 | -0.015 | -0.025
surveyZ-241-P008-Jan13-after_hybrid-test.xls | -0.047 | -0.001 | 0.023 | 0.028 | 0.021 | 0.009 | 0.007 | -0.001 | -0.274 | -0.002 | -0.075 | -0.082 | -0.105 | -0.114 | -0.107 | -0.056 | -0.109 | -0.069 | -0.104 | 0.028 | 0.033 | -0.074 | -0.052 | -0.057 | -0.015 | -0.039
surveyZ-241-P007-Jan27-after_hybrid-test.xls | -0.088 | 0.026 | 0.032 | 0.042 | 0.027 | 0.013 | 0.009 | -0.062 | 0.902 | -0.003 | 0.004 | -0.059 | -0.005 | -0.105 | -0.01 | -0.045 | -0.028 | -0.104 | -0.043 | 0.021 | 0.027 | -0.024 | -0.028 | 0.04 | -0.031 | -0.036
surveyZ-241-P009-Dec23-clear.xls | -0.029 | 0.019 | 0.036 | 0.032 | 0.032 | 0.01 | 0.009 | 0.069 | -1.637 | 0.008
surveyZ-241-P009-Jan07-after_hybrid.xls | -0.046 | 0.021 | 0.039 | 0.031 | 0.027 | 0.01 | 0.009 | 0.006 | -0.373 | 0.002 | -0.078 | -0.066 | -0.078 | -0.099 | -0.085 | -0.1 | -0.028 | -0.077 | -0.084 | -0.025 | 0.006 | -0.107 | -0.066 | -0.033 | -0.051 | -0.095
surveyZ-241-P009-Jan31-after_hybrid-test.xls | -0.055 | 0.02 | 0.034 | 0.032 | 0.028 | 0.01 | 0.009 | -0.007 | -0.708 | 0.004 | -0.129 | -0.065 | -0.075 | -0.083 | -0.091 | -0.106 | -0.028 | -0.072 | -0.078 | -0.019 | 0.005 | -0.098 | -0.066 | -0.085 | -0.05 | -0.096
surveyZ-241-P010-Feb04-after_hybrid-test.xls | -0.032 | 0.056 | 0.024 | 0.037 | 0.047 | 0.01 | 0.012 | 0.013 | 1.362 | -0.012 | -0.124 | -0.053 | -0.075 | -0.116 | -0.053 | -0.098 | -0.054 | -0.047 | -0.031 | -0.03 | -0.006 | -0.105 | -0.063 | -0.093 | -0.006 | -0.056
surveyZ-241-P010-Jan07-clear.xls | -0.015 | 0.004 | 0.027 | 0.038 | 0.027 | 0.01 | 0.01 | -0.006 | -0.599 | -0.006
surveyZ-241-P010-Jan09-after_hybrid.xls | -0.031 | 0.008 | 0.027 | 0.037 | 0.032 | 0.011 | 0.011 | 0.011 | 1.2 | -0.013 | -0.024 | -0.053 | -0.08 | -0.127 | -0.051 | -0.098 | -0.05 | -0.049 | -0.028 | -0.029 | -0.002 | -0.107 | -0.058 | -0.03 | -0.004 | -0.05
surveyZ-241-P011-Feb05-after_hybrid-test.xls | -0.074 | 0.004 | 0.034 | 0.037 | 0.026 | 0.013 | 0.011 | -0.006 | 0.448 | 0.001 | -0.129 | -0.033 | -0.011 | -0.087 | -0.062 | -0.075 | -0.098 | -0.062 | -0.071 | -0.03 | -0.008 | -0.079 | -0.085 | -0.092 | -0.039 | -0.106
surveyZ-241-P011-Jan10-clear.xls | -0.053 | 0.001 | 0.036 | 0.038 | 0.025 | 0.013 | 0.01 | 0.075 | -2.03 | 0.013
surveyZ-241-P011-Jan14-after_hybrid.xls | -0.072 | 0.051 | 0.037 | 0.042 | 0.053 | 0.013 | 0.013 | 0.007 | 0.788 | 0.002 | -0.129 | -0.029 | -0.013 | -0.091 | -0.037 | -0.072 | -0.101 | -0.068 | -0.082 | -0.034 | -0.018 | -0.077 | -0.099 | -0.085 | -0.046 | -0.098
surveyZ-241-P012-Feb05-after_hybrid-test.xls | -0.029 | 0.039 | 0.066 | 0.067 | 0.057 | 0.02 | 0.018 | 0 | 0.372 | -0.001 | -0.077 | -0.079 | -0.041 | -0.105 | -0.038 | -0.078 | -0.076 | -0.063 | -0.105 | 0.019 | 0.01 | -0.047 | -0.071 | -0.037 | -0.054 | -0.076
surveyZ-241-P012-Jan13-clear.xls | -0.032 | 0.037 | 0.073 | 0.066 | 0.057 | 0.02 | 0.018 | 0.056 | -0.42 | 0.001
surveyZ-241-P012-Jan16-after_hybrid.xls | -0.027 | 0.044 | 0.072 | 0.066 | 0.059 | 0.02 | 0.019 | 0.007 | 0.229 | -0.003 | -0.086 | -0.078 | -0.044 | -0.102 | -0.042 | -0.076 | -0.076 | -0.067 | -0.106 | 0.013 | 0.007 | -0.054 | -0.074 | -0.049 | -0.057 | -0.066
surveyZ-241-P013-Feb05-after_hybrid-test.xls | -0.042 | 0.018 | 0.009 | 0.043 | 0.034 | 0.014 | 0.013 | -0.073 | 2.214 | -0.013 | -0.091 | -0.073 | -0.057 | -0.107 | -0.08 | -0.093 | -0.056 | -0.048 | -0.109 | -0.02 | 0.007 | -0.099 | -0.07 | -0.038 | -0.029 | -0.119
surveyZ-241-P013-Jan15-clear.xls | -0.001 | 0.014 | 0.015 | 0.04 | 0.037 | 0.013 | 0.012 | 0.021 | -1.4 | 0
surveyZ-241-P013-Jan22-after_hybrid.xls | -0.038 | 0.02 | 0.01 | 0.043 | 0.034 | 0.014 | 0.013 | -0.038 | 2.898 | -0.012 | -0.111 | -0.08 | -0.059 | -0.087 | -0.075 | -0.096 | -0.054 | -0.045 | -0.117 | -0.034 | -0.011 | -0.109 | -0.089 | -0.073 | -0.035 | -0.118
surveyZ-241-P014-Feb6-after_hybrid-test.xls | -0.061 | 0.058 | 0.021 | 0.032 | 0.057 | 0.011 | 0.013 | -0.086 | 0.325 | -0.012 | -0.079 | 0.226 | 0.322 | -0.111 | -0.052 | -0.105 | 0.042 | -0.097 | -0.078 | -0.002 | 0.113 | 0.094 | 0.053 | -0.022 | -0.065 | 0.368
surveyZ-241-P014-Jan21-clear.xls | -0.031 | 0 | 0.023 | 0.034 | 0.03 | 0.012 | 0.01 | 0.016 | -1.884 | -0.008
surveyZ-241-P015-Jan23-clear.xls | -0.008 | 0.003 | -0.024 | 0.035 | 0.041 | 0.012 | 0.013 | -0.019 | -1.262 | 0.005
surveyZ-241-P015-Jan29-after_hybrid.xls | -0.044 | 0.001 | -0.022 | 0.043 | 0.036 | 0.014 | 0.011 | -0.053 | 1.616 | -0.008 | -0.083 | -0.092 | 0.046 | -0.11 | 0.051 | -0.099 | 0.004 | -0.063 | -0.072 | -0.025 | -0.02 | -0.051 | -0.078 | -0.046 | -0.053 | 0.064
surveyZ-241-P015-March04-after_hybrid-test.xls | -0.05 | -0.002 | -0.023 | 0.04 | 0.032 | 0.013 | 0.01 | -0.027 | 0.635 | -0.004 | -0.089 | -0.089 | 0.056 | -0.105 | 0.038 | -0.099 | -0.001 | -0.07 | -0.063 | -0.03 | -0.02 | -0.055 | -0.078 | -0.054 | -0.053 | 0.071
surveyZ-241-P016-Feb14-after_hybrid-test.xls | -0.052 | 0.008 | 0.099 | 0.035 | 0.034 | 0.011 | 0.01 | -0.002 | -0.336 | -0.003 | -0.056 | -0.083 | 0.068 | -0.102 | 0.02 | 0.105 | 0.237 | -0.081 | -0.097 | 0.013 | 0.121 | -0.011 | 0.161 | 0.025 | -0.071 | 0.31
surveyZ-241-P016-Jan24-clear.xls | -0.007 | 0.005 | 0.098 | 0.034 | 0.037 | 0.011 | 0.011 | 0.051 | -1.426 | 0.002
surveyZ-241-P016-Jan31-after_hybrid.xls | -0.053 | 0.01 | 0.101 | 0.036 | 0.035 | 0.011 | 0.011 | -0.006 | -0.027 | -0.003 | -0.059 | -0.085 | 0.064 | -0.104 | 0.032 | 0.109 | 0.24 | -0.083 | -0.088 | 0.013 | 0.119 | -0.01 | 0.163 | 0.02 | -0.061 | 0.308
surveyZ-241-P017-Feb03-after_hybrid.xls | -0.045 | 0.003 | 0.006 | 0.035 | 0.033 | 0.012 | 0.011 | -0.043 | 0.723 | -0.014 | -0.087 | -0.066 | -0.001 | -0.11 | -0.06 | -0.097 | -0.008 | -0.07 | -0.05 | -0.007 | 0.025 | -0.067 | -0.031 | -0.027 | -0.061 | -0.011
surveyZ-241-P017-Feb25-after_hybrid-test.xls | -0.048 | 0.003 | 0.007 | 0.034 | 0.029 | 0.012 | 0.011 | -0.054 | 0.75 | -0.013 | -0.118 | -0.057 | 0.003 | -0.101 | -0.06 | -0.099 | -0.008 | -0.072 | -0.049 | -0.011 | 0.021 | -0.065 | -0.036 | -0.058 | -0.063 | -0.006
surveyZ-241-P017-Jan28-clear.xls | -0.041 | -0.002 | 0.006 | 0.038 | 0.03 | 0.012 | 0.01 | -0.012 | -1.132 | -0.007
surveyZ-241-P018-Feb06-after_hybrid.xls | -0.049 | 0.003 | 0.012 | 0.038 | 0.027 | 0.012 | 0.01 | 0.074 | 0.52 | -0.005 | -0.145 | -0.07 | 0.015 | -0.088 | -0.009 | -0.105 | -0.076 | -0.087 | -0.089 | -0.019 | -0.025 | -0.057 | -0.114 | -0.073 | -0.065 | -0.052
surveyZ-241-P018-Feb25-after_hybrid-test.xls | -0.057 | 0.001 | 0.01 | 0.036 | 0.025 | 0.012 | 0.01 | 0.068 | 0.247 | -0.003 | -0.139 | -0.068 | 0.017 | -0.093 | -0.006 | -0.113 | -0.084 | -0.087 | -0.085 | -0.024 | -0.031 | -0.061 | -0.123 | -0.071 | -0.059 | -0.056
surveyZ-241-P018-Jan30-clear.xls | -0.056 | 0.007 | 0.01 | 0.039 | 0.024 | 0.012 | 0.01 | 0.107 | -2.533 | 0.009
surveyZ-241-P019-Feb11-after_hybrid.xls | -0.029 | 0.024 | -0.008 | 0.04 | 0.036 | 0.012 | 0.011 | -0.058 | 4.137 | -0.013 | -0.022 | -0.09 | -0.062 | -0.141 | -0.076 | 0.029 | -0.014 | 0.017 | -0.094 | -0.009 | 0.062 | -0.101 | 0.046 | -0.072 | 0.041 | -0.039
surveyZ-241-P019-Feb25-after_hybrid-test.xls | -0.034 | 0.01 | -0.007 | 0.037 | 0.033 | 0.012 | 0.01 | -0.048 | 1.007 | -0.006 | -0.034 | -0.077 | -0.06 | -0.15 | -0.097 | 0.031 | -0.02 | 0.029 | -0.063 | -0.016 | 0.07 | -0.112 | 0.064 | -0.091 | 0.045 | -0.026
surveyZ-241-P019-Jan30-clear.xls | -0.037 | -0.002 | -0.007 | 0.041 | 0.033 | 0.013 | 0.011 | 0.021 | -2.066 | 0.007
surveyZ-241-P020-Feb19-after_hybrid.xls | -0.078 | 0.001 | 0.017 | 0.036 | 0.023 | 0.012 | 0.01 | 0.032 | 0.759 | -0.004 | -0.013 | 0.048 | -0.066 | -0.045 | -0.011 | 0.142 | 0.2 | -0.079 | -0.111 | -0.034 | 0.088 | -0.052 | 0.126 | 0.028 | -0.05 | 0.202
surveyZ-241-P020-Jan31-clear.xls | -0.078 | 0.002 | 0.017 | 0.033 | 0.025 | 0.011 | 0.009 | 0.08 | -1.09 | 0.003
surveyZ-241-P020-Mar11-after_hybrid-test.xls | -0.112 | 0 | 0.018 | 0.035 | 0.023 | 0.012 | 0.009 | 0.047 | 0.158 | -0.001 | -0.011 | 0.045 | -0.062 | -0.017 | 0.016 | 0.136 | 0.198 | -0.083 | -0.113 | -0.033 | 0.066 | -0.037 | 0.1 | 0.034 | -0.055 | 0.193
surveyZ-241-P021-Jan31-clear.xls | -0.021 | 0.007 | -0.011 | 0.048 | 0.031 | 0.015 | 0.012 | 0.008 | 0.772 | -0.012
surveyZ-241-P022-Feb03-clear.xls | -0.052 | 0 | 0.018 | 0.043 | 0.032 | 0.013 | 0.011 | 0.017 | -1.903 | 0.005
surveyZ-241-P023-Feb04-clear.xls | -0.026 | 0.003 | 0.026 | 0.03 | 0.031 | 0.011 | 0.01 | 0.015 | -0.547 | -0.005
surveyZ-241-P023-Feb24-after_hybrid.xls | -0.069 | 0.002 | 0.027 | 0.042 | 0.032 | 0.014 | 0.012 | 0.016 | -0.422 | -0.003 | -0.01 | -0.013 | -0.007 | -0.042 | -0.007 | 0.057 | 0.125 | -0.075 | -0.085 | -0.018 | 0.052 | -0.036 | 0.058 | 0.034 | -0.043 | 0.133
surveyZ-241-P023-Mar12-after_hybrid-test.xls | -0.064 | 0.003 | 0.025 | 0.039 | 0.032 | 0.013 | 0.012 | -0.018 | 0.496 | -0.006 | -0.052 | -0.015 | 0 | -0.03 | -0.006 | 0.059 | 0.133 | -0.074 | -0.086 | -0.029 | 0.045 | -0.042 | 0.053 | -0.027 | -0.037 | 0.144
surveyZ-241-P024-Feb07-clear.xls | -0.011 | 0.003 | -0.001 | 0.053 | 0.039 | 0.016 | 0.014 | 0.026 | -1.643 | 0.001
surveyZ-241-P024-Feb27-after_hybrid.xls | -0.014 | 0.01 | -0.001 | 0.052 | 0.035 | 0.015 | 0.013 | -0.044 | 1.227 | -0.013 | -0.116 | -0.053 | 0.028 | -0.09 | -0.04 | 0.171 | 0.186 | -0.078 | -0.096 | -0.029 | 0.121 | -0.067 | 0.166 | -0.071 | -0.061 | 0.227
surveyZ-241-P024-Mar18-after_hybrid-test.xls | -0.008 | 0.013 | -0.002 | 0.051 | 0.034 | 0.015 | 0.013 | -0.049 | 2.306 | -0.018 | -0.065 | -0.063 | 0.041 | -0.087 | -0.03 | 0.18 | 0.195 | -0.073 | -0.099 | -0.037 | 0.116 | -0.071 | 0.167 | -0.005 | -0.06 | 0.245
surveyZ-241-P025-Metro1-Apr10-clear.xls | -0.059 | -0.001 | 0.06 | 0.074 | 0.054 | 0.021 | 0.019 | 0.049 | -1.465 | 0.002
surveyZ-241-P025-Metro2-Apr15-clear.xls | -0.047 | 0.008 | 0.026 | 0.049 | 0.033 | 0.014 | 0.011 | 0.058 | -1.962 | 0.002
surveyZ-241-P025-Metro3-Apr15-clear.xls | -0.04 | 0.009 | 0.025 | 0.049 | 0.031 | 0.014 | 0.011 | 0.038 | -1.516 | 0
surveyZ-241-P025-Metro4-Apr15-clear.xls | -0.066 | 0.015 | 0.027 | 0.051 | 0.035 | 0.014 | 0.012 | 0.113 | -1.845 | -0.002
surveyZ-241-P025-Feb07-clear.xls | -0.037 | 0.025 | 0.038 | 0.044 | 0.039 | 0.013 | 0.012 | 0.04 | -1.465 | 0.004
surveyZ-241-P026-Feb07-clear.xls | -0.011 | 0.064 | 0.018 | 0.041 | 0.07 | 0.012 | 0.016 | -0.006 | -1.724 | 0.001
surveyZ-241-P027-Feb11-clear.xls | -0.004 | 0.011 | 0.011 | 0.04 | 0.048 | 0.012 | 0.013 | 0.005 | -1.623 | -0.001
surveyZ-241-P027-Feb27-after_hybrid.xls | -0.008 | 0.018 | 0.012 | 0.041 | 0.046 | 0.012 | 0.012 | -0.019 | -0.462 | -0.004 | -0.125 | -0.073 | 0.127 | -0.12 | 0.04 | -0.091 | 0.068 | -0.093 | -0.083 | -0.005 | 0.029 | -0.011 | -0.021 | -0.039 | -0.085 | 0.192
surveyZ-241-P027-Mar19-after_hybrid-test.xls | -0.016 | 0.018 | 0.011 | 0.04 | 0.044 | 0.012 | 0.012 | -0.016 | -0.813 | -0.001 | -0.042 | -0.067 | 0.125 | -0.11 | 0.034 | -0.094 | 0.064 | -0.093 | -0.086 | 0.003 | 0.03 | -0.002 | -0.023 | 0.047 | -0.088 | 0.188
surveyZ-241-P028-Feb21-clear.xls | -0.017 | 0.007 | 0.021 | 0.037 | 0.029 | 0.012 | 0.011 | 0.016 | -1.006 | -0.002
surveyZ-241-P028-Feb28-after_hybrid.xls | -0.034 | 0.024 | 0.005 | 0.035 | 0.023 | 0.011 | 0.011 | -0.047 | 2.464 | -0.016 | -0.099 | -0.088 | -0.099 | -0.116 | -0.101 | -0.062 | -0.069 | -0.092 | -0.112 | -0.01 | 0.02 | -0.111 | -0.063 | -0.02 | -0.085 | -0.105
surveyZ-241-P028-Mar26-after_hybrid-test.xls | -0.036 | 0.021 | 0.02 | 0.037 | 0.026 | 0.011 | 0.011 | -0.032 | 1.544 | -0.013 | -0.077 | -0.063 | -0.07 | -0.098 | -0.104 | -0.05 | -0.064 | -0.082 | -0.093 | -0.015 | 0.023 | -0.098 | -0.049 | -0.011 | -0.072 | -0.079
surveyZ-241-P029-Feb27-clear.xls | -0.026 | 0.016 | 0.024 | 0.026 | 0.026 | 0.009 | 0.008 | -0.012 | -1.315 | -0.002
surveyZ-241-P029-Mar20-after_hybrid-test.xls | -0.034 | -0.002 | 0.021 | 0.024 | 0.02 | 0.01 | 0.008 | -0.031 | -0.599 | -0.005 | -0.04 | -0.028 | 0.044 | -0.091 | -0.007 | 0.043 | 0.092 | -0.073 | -0.091 | -0.005 | 0.07 | -0.026 | 0.063 | 0.024 | -0.064 | 0.146
surveyZ-241-P029-March04-after_hybrid.xls | -0.031 | 0 | 0.024 | 0.024 | 0.021 | 0.01 | 0.008 | -0.031 | -0.526 | -0.006 | -0.105 | -0.029 | 0.059 | -0.095 | -0.01 | 0.048 | 0.102 | -0.067 | -0.094 | -0.015 | 0.073 | -0.034 | 0.07 | -0.056 | -0.059 | 0.168
surveyZ-241-P030-March04-clear.xls | -0.008 | 0.004 | 0.031 | 0.024 | 0.023 | 0.008 | 0.008 | 0.058 | -1.279 | 0.002
surveyZ-241-P030-March11-after_hybrid.xls | -0.035 | 0.012 | 0.028 | 0.025 | 0.026 | 0.009 | 0.009 | -0.003 | 3.121 | -0.013 | -0.086 | 0.095 | 0.234 | -0.118 | -0.065 | -0.117 | -0.08 | -0.093 | -0.102 | 0.006 | 0.063 | 0.043 | -0.035 | -0.009 | -0.072 | 0.159
surveyZ-241-P031-March04-clear.xls | -0.018 | 0.012 | 0.047 | 0.029 | 0.03 | 0.011 | 0.01 | 0.056 | -1.33 | 0.007
surveyZ-241-P031-March10-after_hybrid.xls | -0.071 | 0.007 | 0.047 | 0.036 | 0.025 | 0.012 | 0.01 | 0.022 | -0.09 | 0.003 | -0.071 | -0.054 | -0.051 | -0.076 | -0.037 | -0.006 | 0.059 | -0.085 | -0.072 | -0.022 | 0.032 | -0.077 | 0.006 | -0.001 | -0.06 | 0.016
surveyZ-241-P031-March24-after_hybrid-test.xls | -0.07 | 0.001 | 0.044 | 0.035 | 0.025 | 0.011 | 0.01 | 0.095 | -0.989 | 0.004 | -0.074 | -0.051 | -0.058 | -0.086 | -0.057 | -0.005 | 0.06 | -0.08 | -0.06 | -0.005 | 0.051 | -0.068 | 0.03 | -0.013 | -0.054 | 0.014
surveyZ-241-P032-Apr04-after_hybrid-test.xls | -0.054 | 0.009 | 0.011 | 0.066 | 0.044 | 0.02 | 0.017 | 0.002 | 0.385 | -0.002 | -0.071 | -0.079 | -0.074 | -0.109 | -0.046 | -0.116 | -0.115 | -0.07 | -0.086 | -0.014 | -0.026 | -0.091 | -0.123 | -0.016 | -0.061 | -0.127
surveyZ-241-P032-March06-clear.xls | -0.005 | 0.013 | 0.014 | 0.047 | 0.035 | 0.013 | 0.011 | 0.027 | -1.618 | 0.005
surveyZ-241-P032-March18-after_hybrid.xls | -0.046 | 0.051 | 0.013 | 0.051 | 0.047 | 0.014 | 0.013 | 0.002 | 0.048 | -0.001 | -0.144 | -0.058 | -0.087 | -0.115 | -0.119 | -0.115 | -0.117 | -0.065 | -0.085 | -0.003 | 0.01 | -0.097 | -0.085 | -0.076 | -0.067 | -0.098
surveyZ-241-P033-Apr02-after_hybrid-test.xls | -0.02 | 0.017 | 0.033 | 0.03 | 0.032 | 0.012 | 0.011 | -0.007 | -0.13 | -0.006 | -0.033 | -0.076 | -0.056 | -0.08 | -0.021 | -0.106 | -0.163 | -0.078 | -0.111 | -0.01 | -0.051 | -0.068 | -0.165 | 0.008 | -0.044 | -0.103
surveyZ-241-P033-March07-clear.xls | -0.035 | 0.037 | 0.034 | 0.027 | 0.029 | 0.011 | 0.011 | 0.073 | -1.184 | -0.003
surveyZ-241-P033-March17-after_hybrid.xls | -0.012 | 0.017 | 0.034 | 0.031 | 0.033 | 0.012 | 0.011 | 0.023 | 0.268 | -0.008 | -0.041 | -0.072 | -0.061 | -0.078 | -0.01 | -0.108 | -0.152 | -0.086 | -0.13 | -0.012 | -0.054 | -0.067 | -0.173 | 0.019 | -0.058 | -0.102
surveyZ-241-P034-Apr03-clear.xls | -0.021 | 0.04 | 0.028 | 0.03 | 0.031 | 0.011 | 0.01 | -0.065 | -0.958 | -0.006
surveyZ-241-P034-Apr28-after_hybrid-test.xls | -0.069 | 0.034 | 0.021 | 0.035 | 0.028 | 0.011 | 0.01 | -0.068 | -0.163 | -0.008 | -0.105 | 0.06 | -0.015 | -0.093 | -0.098 | -0.097 | -0.13 | -0.084 | -0.145 | -0.006 | 0.017 | -0.043 | -0.097 | -0.028 | -0.063 | -0.05
surveyZ-241-P034-April17-after_hybrid.xls | -0.056 | 0.034 | 0.017 | 0.036 | 0.026 | 0.011 | 0.011 | -0.046 | 0.66 | -0.012 | -0.119 | 0.049 | -0.024 | -0.104 | -0.104 | -0.095 | -0.129 | -0.08 | -0.143 | -0.003 | 0.024 | -0.048 | -0.088 | -0.049 | -0.059 | -0.053
surveyZ-241-P035-Apr08-after_hybrid-test.xls | -0.06 | -0.003 | 0.027 | 0.039 | 0.024 | 0.011 | 0.01 | 0.004 | -0.509 | 0.001 | 0.019 | -0.058 | -0.09 | 0.007 | 0.066 | -0.048 | -0.122 | -0.083 | -0.152 | -0.029 | -0.103 | -0.047 | -0.204 | 0.117 | -0.069 | -0.048
surveyZ-241-P035-March10-clear.xls | -0.017 | -0.001 | 0.025 | 0.033 | 0.03 | 0.01 | 0.009 | 0.04 | -1.566 | 0.004
surveyZ-241-P035-March25-after_hybrid.xls | -0.045 | -0.003 | 0.027 | 0.034 | 0.026 | 0.01 | 0.009 | -0.004 | -0.563 | -0.001 | 0.014 | -0.07 | -0.103 | -0.007 | 0.061 | -0.054 | -0.12 | -0.077 | -0.154 | -0.015 | -0.093 | -0.045 | -0.194 | 0.126 | -0.078 | -0.063
surveyZ-241-P036-Apr04-after_hybrid-test.xls | -0.056 | 0.007 | 0.012 | 0.054 | 0.032 | 0.016 | 0.013 | 0.002 | 0.385 | -0.002 | -0.147 | -0.053 | -0.088 | -0.102 | -0.115 | -0.116 | -0.115 | -0.07 | -0.086 | -0.007 | 0.002 | -0.097 | -0.095 | -0.077 | -0.061 | -0.098
surveyZ-241-P036-March10-clear.xls | -0.007 | 0.006 | 0.028 | 0.032 | 0.023 | 0.01 | 0.009 | -0.003 | -1.049 | -0.005
surveyZ-241-P036-March21-after_hybrid.xls | -0.011 | 0.024 | 0.027 | 0.029 | 0.027 | 0.01 | 0.009 | -0.077 | 0.809 | -0.013 | -0.167 | -0.084 | -0.076 | -0.112 | -0.109 | -0.125 | -0.146 | -0.085 | -0.106 | -0.007 | -0.008 | -0.102 | -0.124 | -0.103 | -0.064 | -0.179
surveyZ-241-P037-Apr03-after_hybrid-test.xls | -0.028 | 0.006 | 0.02 | 0.036 | 0.024 | 0.012 | 0.01 | -0.023 | -0.337 | 0.003 | -0.09 | -0.081 | -0.072 | -0.103 | -0.046 | -0.119 | -0.144 | -0.101 | -0.132 | -0.013 | -0.035 | -0.089 | -0.159 | -0.016 | -0.075 | -0.168
surveyZ-241-P037-Apr08-after_hybrid-test.xls | -0.024 | 0.011 | 0.019 | 0.036 | 0.024 | 0.012 | 0.01 | -0.028 | -0.508 | 0.004 | -0.092 | -0.08 | -0.073 | -0.11 | -0.048 | -0.12 | -0.146 | -0.107 | -0.138 | -0.014 | -0.033 | -0.091 | -0.161 | -0.013 | -0.074 | -0.173
surveyZ-241-P037-March12-clear.xls | -0.003 | 0.012 | 0.021 | 0.035 | 0.031 | 0.011 | 0.01 | 0.01 | -1.483 | 0.007
surveyZ-241-P037-March21-after_hybrid.xls | -0.022 | 0.011 | 0.02 | 0.037 | 0.024 | 0.012 | 0.01 | -0.032 | -0.527 | 0.004 | -0.091 | -0.074 | -0.075 | -0.11 | -0.043 | -0.12 | -0.147 | -0.103 | -0.136 | -0.019 | -0.037 | -0.094 | -0.164 | -0.011 | -0.077 | -0.169
surveyZ-241-P038-Apr07-after_hybrid-test.xls | -0.049 | 0.011 | 0.044 | 0.035 | 0.038 | 0.011 | 0.011 | 0.041 | -0.77 | 0.002 | -0.108 | -0.05 | -0.038 | -0.111 | -0.114 | -0.105 | -0.114 | -0.09 | -0.115 | -0.012 | 0.012 | -0.09 | -0.094 | -0.049 | -0.064 | -0.109
surveyZ-241-P038-March12-clear.xls | -0.011 | 0.007 | 0.045 | 0.036 | 0.04 | 0.011 | 0.011 | 0.061 | -1.72 | 0.004
surveyZ-241-P038-March26-after_hybrid.xls | -0.026 | 0.002 | 0.044 | 0.033 | 0.038 | 0.011 | 0.01 | 0.072 | -0.842 | 0.002 | -0.111 | -0.05 | -0.039 | -0.115 | -0.117 | -0.101 | -0.105 | -0.08 | -0.105 | -0.007 | 0.021 | -0.087 | -0.077 | -0.06 | -0.054 | -0.101
surveyZ-241-P039-Apr08-after_hybrid-test.xls | -0.055 | 0.011 | 0.029 | 0.045 | 0.033 | 0.014 | 0.012 | -0.026 | 2.252 | -0.017 | -0.024 | -0.065 | -0.117 | 0.006 | -0.086 | -0.052 | -0.147 | -0.077 | -0.144 | -0.001 | -0.043 | -0.067 | -0.148 | 0.034 | -0.061 | -0.03
surveyZ-241-P039-March14-clear.xls | -0.003 | 0.005 | 0.031 | 0.036 | 0.038 | 0.011 | 0.011 | 0.045 | -0.87 | -0.004
surveyZ-241-P039-March25-after_hybrid.xls | -0.045 | 0.019 | 0.031 | 0.043 | 0.034 | 0.013 | 0.012 | -0.043 | 2.143 | -0.019 | -0.025 | -0.067 | -0.109 | -0.004 | -0.076 | -0.047 | -0.149 | -0.071 | -0.146 | -0.004 | -0.043 | -0.069 | -0.146 | 0.025 | -0.054 | -0.044
surveyZ-241-P040-Apr09-after_hybrid-test.xls | 0.001 | 0.021 | 0.043 | 0.03 | 0.033 | 0.01 | 0.01 | -0.035 | 1.149 | -0.008 | -0.013 | -0.052 | -0.113 | -0.031 | -0.04 | -0.062 | -0.12 | -0.042 | -0.102 | -0.012 | -0.046 | -0.071 | -0.127 | 0 | -0.024 | -0.029
surveyZ-241-P040-March17-clear.xls | -0.005 | 0.055 | 0.044 | 0.032 | 0.07 | 0.01 | 0.015 | 0.037 | -1.618 | 0.003
surveyZ-241-P040-March31-after_hybrid.xls | 0.001 | 0.019 | 0.044 | 0.03 | 0.032 | 0.01 | 0.01 | -0.035 | 0.936 | -0.01 | -0.014 | -0.049 | -0.111 | -0.033 | -0.045 | -0.064 | -0.115 | -0.039 | -0.104 | -0.013 | -0.042 | -0.073 | -0.123 | -0.002 | -0.021 | -0.05
surveyZ-241-P041-Apr07-after_hybrid.xls | -0.072 | 0.009 | 0.03 | 0.034 | 0.03 | 0.011 | 0.011 | -0.042 | 2.521 | -0.019 | -0.12 | -0.075 | -0.112 | -0.089 | -0.102 | -0.101 | -0.134 | -0.091 | -0.117 | -0.016 | -0.018 | -0.11 | -0.129 | -0.053 | -0.075 | -0.122
surveyZ-241-P041-Apr23-after_hybrid-test.xls | -0.067 | -0.001 | 0.019 | 0.031 | 0.03 | 0.01 | 0.01 | 0.031 | 1.721 | -0.016 | -0.141 | -0.072 | -0.104 | -0.099 | -0.12 | -0.106 | -0.139 | -0.08 | -0.097 | -0.02 | -0.011 | -0.119 | -0.116 | -0.072 | -0.07 | -0.125
surveyZ-241-P041-March18-clear-newprof.xls | -0.013 | 0.059 | 0.031 | 0.024 | 0.071 | 0.006 | 0.012 | 0.005 | -0.315 | -0.007
surveyZ-241-P041-March18-clear.xls | -0.013 | 0.059 | 0.031 | 0.028 | 0.065 | 0.01 | 0.014 | 0.005 | -0.315 | -0.007
surveyZ-241-P042-Apr08-after_hybrid.xls | 0 | 0.032 | 0.039 | 0.033 | 0.025 | 0.009 | 0.009 | -0.015 | -0.444 | -0.005 | -0.068 | -0.078 | -0.113 | -0.092 | -0.112 | -0.108 | 0.032 | -0.07 | -0.051 | 0.01 | 0.039 | -0.088 | -0.01 | -0.029 | -0.048 | -0.06
surveyZ-241-P042-Apr23-after_hybrid-test.xls | -0.004 | 0.03 | 0.026 | 0.032 | 0.024 | 0.009 | 0.008 | 0.039 | -0.625 | -0.004 | -0.085 | -0.067 | -0.112 | -0.092 | -0.118 | -0.11 | 0.033 | -0.067 | -0.042 | 0.002 | 0.038 | -0.096 | -0.008 | -0.034 | -0.051 | -0.076
surveyZ-241-P042-March20-clear.xls | -0.002 | 0.024 | 0.037 | 0.033 | 0.028 | 0.009 | 0.009 | -0.006 | -1.352 | 0
surveyZ-241-P043-March20-clear.xls | -0.007 | 0.005 | 0.031 | 0.035 | 0.036 | 0.011 | 0.012 | 0.013 | -1.182 | 0.007
surveyZ-241-P044-Apr10-after_hybrid.xls | -0.033 | -0.001 | 0.04 | 0.045 | 0.034 | 0.014 | 0.012 | 0.003 | 0.205 | -0.011 | 0.072 | -0.081 | -0.074 | 0.03 | 0.108 | -0.11 | -0.104 | -0.065 | -0.068 | -0.061 | -0.155 | -0.065 | -0.242 | 0.131 | -0.05 | 0.064
surveyZ-241-P044-Apr24-after_hybrid-test.xls | -0.028 | 0.007 | 0.028 | 0.047 | 0.034 | 0.014 | 0.012 | 0.07 | 1.355 | -0.017 | 0.06 | -0.094 | -0.082 | 0.027 | 0.097 | -0.111 | -0.1 | -0.065 | -0.061 | -0.06 | -0.151 | -0.073 | -0.235 | 0.123 | -0.049 | 0.05
surveyZ-241-P044-March26-clear.xls | -0.04 | 0 | 0.038 | 0.045 | 0.035 | 0.014 | 0.011 | 0.006 | -1.61 | -0.002
surveyZ-241-P045-Apr17-after_hybrid.xls | -0.03 | 0.007 | 0.028 | 0.047 | 0.033 | 0.015 | 0.013 | -0.006 | 2.869 | -0.017 | -0.134 | 0.022 | -0.086 | -0.152 | -0.146 | -0.089 | -0.132 | -0.083 | -0.137 | -0.086 | 0.005 | -0.177 | -0.105 | -0.057 | -0.061 | -0.068
surveyZ-241-P045-March28-clear.xls | -0.019 | 0.016 | 0.041 | 0.039 | 0.036 | 0.012 | 0.011 | 0.079 | -1.448 | 0
surveyZ-241-P046-Apr21-after_hybrid.xls | -0.011 | 0.009 | 0.021 | 0.036 | 0.026 | 0.012 | 0.011 | 0.073 | -0.283 | -0.014 | 0.007 | -0.023 | -0.038 | -0.118 | -0.134 | 0.003 | -0.11 | 0.106 | -0.059 | -0.011 | 0.054 | -0.09 | 0.039 | -0.095 | 0.093 | 0.004
surveyZ-241-P046-Apr29-after_hybrid-test.xls | -0.026 | 0.017 | 0.02 | 0.035 | 0.025 | 0.012 | 0.01 | -0.034 | 0.336 | -0.014 | 0.018 | -0.015 | -0.029 | -0.115 | -0.123 | 0.007 | -0.109 | 0.107 | -0.059 | -0.008 | 0.054 | -0.079 | 0.04 | -0.076 | 0.094 | 0.005
surveyZ-241-P046-March28-clear.xls | -0.009 | 0.013 | 0.031 | 0.039 | 0.033 | 0.011 | 0.01 | 0.026 | -1.336 | -0.007
surveyZ-241-P047-Apr22-after_hybrid.xls | -0.016 | 0.005 | 0.022 | 0.032 | 0.023 | 0.01 | 0.009 | 0.093 | 0.415 | 0 | -0.06 | -0.088 | -0.083 | -0.095 | 0.012 | -0.104 | -0.128 | -0.054 | -0.105 | -0.006 | -0.051 | -0.069 | -0.149 | 0.016 | -0.047 | -0.085
surveyZ-241-P047-Apr29-after_hybrid-test.xls | -0.016 | -0.002 | 0.023 | 0.028 | 0.023 | 0.009 | 0.009 | 0.029 | -0.303 | 0.001 | -0.047 | -0.093 | -0.078 | -0.095 | 0.011 | -0.096 | -0.123 | -0.048 | -0.085 | -0.011 | -0.05 | -0.075 | -0.138 | 0.014 | -0.038 | -0.066
surveyZ-241-P047-April01-clear.xls | -0.009 | 0.015 | 0.034 | 0.032 | 0.03 | 0.011 | 0.01 | 0.062 | -1.286 | 0.007
surveyZ-241-P048-Apr23-after_hybrid.xls | -0.052 | 0.034 | 0.023 | 0.03 | 0.024 | 0.009 | 0.009 | 0.122 | 0.433 | -0.015 | 0.021 | 0.124 | 0.045 | -0.046 | -0.076 | 0.054 | -0.041 | 0.048 | -0.093 | -0.019 | 0.061 | -0.007 | 0.053 | -0.023 | 0.041 | 0.179
surveyZ-241-P048-April01-clear.xls | -0.033 | 0.026 | 0.029 | 0.03 | 0.028 | 0.009 | 0.009 | 0.039 | -2.396 | -0.001
surveyZ-241-P049-Apr03-clear.xls | -0.02 | 0.035 | 0.041 | 0.044 | 0.043 | 0.013 | 0.012 | 0.031 | -2.012 | 0.002
surveyZ-241-P049-Apr25-after_hybrid.xls | -0.002 | 0.065 | 0.011 | 0.076 | 0.076 | 0.026 | 0.026 | -0.026 | 0.799 | -0.014 | 0.035 | 0.308 | 0.15 | -0.11 | -0.042 | 0.118 | 0.27 | -0.103 | -0.021 | 0.004 | 0.214 | 0.081 | 0.28 | 0.022 | 0.041 | 0.415
surveyZ-241-P049-Apr25-after_hybrid_old.xls | -0.003 | 0.067 | 0.009 | 0.076 | 0.077 | 0.027 | 0.027 | -0.038 | 0.637 | -0.015 | 0.032 | 0.314 | 0.164 | -2.334 | -2.274 | 0.116 | 0.26 | -0.109 | -0.026 | 0.373 | 2.068 | -0.66 | 2.129 | 0.026 | 0.036 | 0.417
surveyZ-241-P049-Apr30-after_hybrid.xls | -0.009 | 0.015 | -0.004 | 0.037 | 0.039 | 0.011 | 0.011 | -0.069 | 2.03 | -0.013 | -0.06 | 0.005 | -0.102 | -0.078 | -0.104 | -0.126 | 0.127 | -0.058 | -0.037 | -0.051 | 0.03 | -0.121 | 0.007 | -0.032 | 0.02 | 0.015
surveyZ-241-P050-Apr07-clear.xls | -0.01 | 0.012 | 0.009 | 0.036 | 0.041 | 0.012 | 0.012 | -0.032 | -0.271 | -0.005
surveyZ-241-P051-Apr07-clear.xls | -0.011 | 0.012 | 0.022 | 0.038 | 0.043 | 0.012 | 0.013 | 0.039 | -1.659 | 0.004
surveyZ-241-P052-Apr21-clear.xls | -0.015 | 0.029 | 0.017 | 0.039 | 0.028 | 0.01 | 0.01 | 0.179 | -0.51 | -0.008
surveyZ-241-P053-Apr18-clear.xls | 0.001 | 0.031 | 0.036 | 0.047 | 0.04 | 0.012 | 0.012 | 0.022 | -1.285 | -0.004
surveyZ-241-P053-Apr25-after_hybrid.xls | -0.01 | 0.062 | 0.03 | 0.043 | 0.039 | 0.012 | 0.013 | 0.034 | 2.628 | -0.02 | -0.03 | -0.113 | -0.096 | -0.111 | -0.144 | -0.077 | -0.13 | 0.047 | -0.039 | -0.033 | 0.001 | -0.149 | -0.048 | -0.072 | 0.042 | -0.068
surveyZ-241-P054-Apr18-clear.xls | -0.021 | 0.024 | 0.02 | 0.05 | 0.045 | 0.015 | 0.013 | 0.031 | -2.45 | -0.001
surveyZ-241-P055-May01-clear.xls | -0.044 | 0.027 | 0.025 | 0.036 | 0.043 | 0.015 | 0.015 | 0.239 | 0.11 | -0.009
surveyZ-241-P056-Apr22-clear.xls | -0.003 | 0.014 | 0.018 | 0.027 | 0.026 | 0.009 | 0.008 | 0.007 | -1.124 | 0.008
surveyZ-241-P057-Apr22-clear.xls | -0.015 | 0.058 | 0.024 | 0.029 | 0.033 | 0.011 | 0.01 | 0.041 | -1.487 | 0.003
surveyZ-241-P058-Apr22-clear.xls | -0.009 | 0.035 | 0.001 | 0.028 | 0.03 | 0.009 | 0.009 | -0.08 | -1.238 | -0.004
surveyZ-241-P059-May02-clear.xls | -0.012 | 0.047 | 0.034 | 0.034 | 0.034 | 0.01 | 0.011 | 0.067 | 1.533 | -0.014
surveyZ-241-P060-May01-clear.xls | -0.018 | 0.027 | 0.013 | 0.038 | 0.034 | 0.012 | 0.011 | -0.022 | -1.797 | -0.009
surveyZ-241-P061-May01-clear.xls | -0.022 | 0.031 | 0.014 | 0.042 | 0.046 | 0.014 | 0.013 | -0.082 | -0.975 | -0.009

## TestSummary
|  |  | in Santa Cruz |  |  | on hold for study or chip replacement | [6 empty] | modules rebonded |  |  |  |  | LC measured at 0 degrees |  |  |  | need conditioning
| Hybrid Serial # | ok | Chip repl or study | Noisy dead | Neg Offs | High Offs H/L Gain | LTT |  | ok | Total bad channels (Hybrid) | FO | Module | ok | LC(mA) 150C 350V Initial | LC(mA) 150C 500V Initial | LC(mA) 150C 350V after c | LC(mA) 150C 500V after c | LC(mA) 150C 350V final | LC(mA) 150C 500V final | Noise Occupancy (LTT) |  | T1 | T2 | Noisy dead | Unb | After re bond | Total bad channels (Module) | DONE | Comments, specifically why a hybrid is on hold
Total | 99 | 86 | 15 |  |  |  | cold | wm | 81 |  | 61 |  | 40 | [14 empty] | 39
1 | 20220040200008 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P2 | 1 | 1.373 | 1.783 | 0.758 | 0.963 | 0.738 | 0.922 | 4.5e-07 | 3.6e-06 | 1 | 1 | 3 | 9 |  | 12 | 1
1 | 20220040200009 | 1 |  | 0 |  | 1 | 0 | 0 | 1 | 1 | 1 | P4 | 1 | 0.195 | 0.256 | 0.195 | 0.256 | 0.225 | 0.266 | 1.6e-07 | 6.5e-06 | -3 | -3 | 7 | 7 |  | 14 | 1
1 | 20220040200010 | 1 |  | 0 |  | 1 | 0 | 0 | 1 | 1 | 1 | P3 | 1 | 0.246 | 0.318 | 0.256 | 0.287 | 0.256 | 0.297 | 2.9e-07 | 3e-06 | -2 | 0 | 1 | 1 |  | 2 | 1
1 | 20220040200011 | 1 | 1 | 0 |  | 1 | 0 | 0 | 1 | 1 | 1 | P6 | 1 | 1.332 | 2.234 | 1.097 | 1.917 | 0.748 | 0.861 | 7.2e-07 | 7.1e-06 | 3 | 3 | 1 | 21 | 9 | 10 | 1
1 | 20220040200012 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P7 | 1 | 0.266 | 0.307 | 0.266 | 0.307 | 0.277 | 0.318 | 9.2e-07 | 3.2e-06 | 0 | 0 | 0 | 16 | 14 | 14 | 1
1 | 20220040200013 | 1 | 1 | 0 |  |  | 0 | 0 | 1 | 0 | 1
1 | 20220040200014 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P8 | 1 | 0.666 | 0.738 | 0.666 | 0.738 | 0.625 | 0.707 | 8.1e-07 | 2.3e-05 | 0 | 0 | 0 | 16 | 8 | 8 | 1
1 | 20220040200015 | 1 |  | 1 |  |  | 0 | 0 | 1 | 1 | 1 | P14 | 1 | 0.328 | 0.482 | 0.328 | 0.482 | 0.297 | 0.369 | 7.3e-07 | 3.1e-05 | 2 | 0 | 1 | 21 | 11 | 12 | 1
1 | 20220040200016 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P9 | 1 | 0.184 | 10 | 0.266 | 0.287 | 0.236 | 0.266 | 1.7e-07 | 9.8e-06 | 0 | 0 | 0 | 20 | 10 | 10 | 1
1 | 20220040200017 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P10 | 1 | 0.502 | 0.594 | 0.359 | 0.43 | 0.41 | 0.482 | 7.6e-07 | 1.1e-05 | 0 | -1 | 1 | 14 | 4 | 5 | 1
1 | 20220040200018 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P11 | 1 | 0.318 | 2.89 | 0.285 | 0.328 | 0.4 | 0.502 | 5.2e-07 | 4.3e-06 | -1 | -1 | 0 | 22 | 11 | 11 | 1
1 | 20220040200019 | 1 |  | 1 |  |  | 0 | 0 | 1 | 1 | 1 | P12 | 1 | 0.635 | 0.779 | 0.471 | 0.605 | 0.256 | 0.287 | 6.3e-07 | 5.5e-06 | 0 | 0 | 2 | 9 | 5 | 7 | 1
1 | 20220040200020 | 1 | 1 | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P15 | 1 | 0.277 | 0.318 | 0.277 | 0.307 | 0.41 | 0.461 | 1.4e-07 | 3.8e-06 | 1 | 0 | 0 | 22 | 12 | 12 | 1
1 | 20220040200021 | 1 | 1 | 0 |  |  |  |  | 1
1 | 20220040200022 |  | 1 | 0 | [24 empty] | Chp 7, 10 VERY LOW GAIN. Study shows bypass Chp10 improves results. Replace chip?
1 | 20220040202223 | 1 |  | 1 |  |  | 0 | 0 | 1 | 1 | 1 | P13 | 1 | 0.369 | 0.4 | 0.369 | 0.4 | 0.338 | 0.471 | 1.5e-06 | 4.5e-06 | 0 | 1 | 3 | 20 | 10 | 13 | 1
1 | 20220040200024 | 1 |  | 0 |  |  | 0 | 1 | 1 | 1 | 1 | P20 | 1 | 0.184 | 0.215 | 0.195 | 0.215 | 0.174 | 2.265 | 1.6e-06 | 1.2e-05 | 0 | -1 | 3 | 1 |  | 4 | 1
1 | 20220040200025 | 1 |  | 1 |  | 1 | 1 | 0 | 1 | 3 | 1 | P24 | 1 | 0.41 | 0.471 | 0.41 | 0.471 | 0.4 | 0.461 | 5.5e-08 | 8.4e-06 | 2 | 4 | 0 | 4 |  | 4 | 1
1 | 20220040200026 | 1 |  | 0 |  |  | 0 | 0 | 1 | 1 | 1
1 | 20220040200027 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P32 | 1 | 0.379 | 0.451 | 0.215 | 0.246 |  |  | 1.2e-06 | 1.6e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200028 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P18 | 1 | 0.318 | 0.359 | 0.205 | 0.246 | 0.205 | 0.246 | 1.6e-05 | 6.9e-05 | -1 | -2 | 0 | 0 |  | 0 | 1
1 | 20220040200029 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1
1 | 20220040200030 | 1 |  | 1 |  |  | 0 | 0 | 1 | 1 | 1 | P28 | 1 | 10 | 10 | 1.353 | 10 | 1.302 | 6.888 | 2e-06 | 4.4e-05 | -1 | -1 | 4 | 0 |  | 4 | 1 | High LC
1 | 20220040200031 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1
1 | 20220040200032 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P29 | 1 | 0.246 | 3.946 | 0.256 | 0.287 | 0.225 | 0.266 | 3.6e-06 | 2.8e-05 | 1 | 1 | 0 | 1 |  | 1 | 1
1 | 20220040200033 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P38 | 1 | 0.553 | 0.646 | 0.266 | 0.307 |  |  | 3.1e-06 | 2.6e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200034 | 1 |  | 0 | 1 |  | 0 | 0 | 1 | 1 | 1 | P40 | 1 |  |  | 0.338 | 0.369 |  |  | 1.1e-06 | 2.8e-05 |  |  | 2 | 1 |  | 3 | 1
1 | 20220040200035 |  | 1
1 | 20220040200036 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P42 | 1 |  |  | 0.215 | 0.266 |  |  | 3e-06 | 2e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200037 | 1 |  | 1 |  |  | -1 | 0 | 1 | 0 | 1 | P16 | 1 | 0.41 | 0.471 | 0.379 | 0.451 | 0.225 | 0.256 | 2e-07 | 2e-05 | -1 | 1 | 0 | 6 | 2 | 2 | 1
1 | 20220040200038 | 1 |  | 0 |  |  | 1 | 0 | 1 | 1 | 1 | P17 | 1 | 0.174 | 0.225 | 0.174 | 0.225 | 0.205 | 0.246 | 9.7e-06 | 0.0001 | 0 | 1 | 3 | 4 |  | 7 | 1
1 | 20220040200039 |  | 2 | 0 |  |  | 3 | 0 | 1 | 3 | 1 | [17 empty] | Chp 2, 6 LGS. Fix by Ish => 20? Chip 10 chipped.
1 | 20220040200040 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P19 | 1 | 0.184 | 10 | 0.215 | 0.246 | 0.236 | 0.256 | 1.1e-05 | 5.9e-05 | 0 | 1 | 0 | 0 |  | 0 | 1
1 | 20220040200041 | 1 |  | 1 |  |  | 0 | 0 | 1 | 1 | 1 | P23 | 1 | 0.635 | 0.953 | 0.543 | 0.738 | 0.379 | 0.543 | 2.5e-06 | 1.9e-05 | 0 | 0 | 3 | 0 |  | 3 | 1 | Chp 2 LGS. Shows up only cold.
1 | 20220040200042 | 1 |  | 0 |  |  | 1 | 0 | 1 | 1 | 1 | P27 | 1 | 0.174 | 0.225 | 0.174 | 0.225 | 0.174 | 0.205 | 1.5e-06 | 9.6e-06 | 3 | 2 | 2 | 0 |  | 2 | 1
1 | 20220040200043 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P31 | 1 | 0.195 | 2.46 | 0.195 | 1.138 | 0.246 | 0.359 | 1.7e-06 | 1.2e-05 | 0 | 1 | 1 | 2 |  | 3 | 1
1 | 20220040200044 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P33 | 1 | 0.441 | 0.533 | 0.225 | 0.256 |  |  | 3.1e-06 | 2e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200045 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P35 | 1 | 0.615 | 1.999 | 0.287 | 0.238 |  |  | 4.6e-06 | 1.3e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200046 |  | 1 | [25 empty] | Chp 9 LGS. Fix by Ish => 20?
1 | 20220040200047 |  | 1 | [25 empty] | Chp 0 HIGH gain, negative offset. Replace chip?
1 | 20220040200048 | [27 empty] | F/O done before approp. tests were run. Chp6 some gain spread. Continue testing?
1 | 20220040200049 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P36 | 1 |  |  | 0.297 | 0.348 |  |  | 6.4e-07 | 4.5e-06 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200050 |  |  | 0 |  |  | 1 | 0 | 1 | 1 | 1 | [17 empty] | Chp 10 fail timewalk. Replace chip?
1 | 20220040200051 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P37 | 1 |  |  | 0.307 | 0.348 |  |  | 1.8e-06 | 2.7e-05 |  |  | 0 | 3 |  | 3 | 1
1 | 20220040200052 |  |  | 0 | 1 |  | 1 | 0 | 1 | 2 | 1 | [17 empty] | Chip 7 LGS that shows up only at cold.
1 | 20220040200053 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P41 | 1 |  |  | 0.256 | 0.277 |  |  | 9.1e-07 | 1.2e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200054 |  | 1 | 0 | [24 empty] | Chip 4 LGS. Fix by Ish => 20?
1 | 20220040200055 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1
1 | 20220040200056 | 1 |  | 0 | [24 empty] | Damage after Initial? Chp 6 bad.
1 | 20220040200057 | 1 |  | 0 | 2 |  | 1 | 0 | 1 | 3 | 1
1 | 20220040200058 |  | 1 | [25 empty] | Chip 6 LGS. Fix/ replace chip?
1 | 20220040200059 | 1 |  | 0
1 | 20220040200060 | 1 |  | 0 | 128
1 | 20220040200061 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P39 | 1 |  |  | 0.277 | 0.318 |  |  | 2.7e-06 | 1.4e-05 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200062 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P46 | 1 |  |  |  |  | 0.215 | 0.266 | 1.2e-06 | 1.4e-05 |  |  |  | 1 |  | 1 | 1
1 | 20220040200063 | 1 |  | 0 |  | 2 | 0 | 0 | 1 | 2 | 1 | P44 | 1 |  |  | 0.266 | 0.297 |  |  | 1.2e-06 | 7.1e-06 |  |  | 0 | 0 |  | 0 | 1
1 | 20220040200064 |  |  | 0 |  |  | 1 | 0 | 1 | 1 | 1 | [17 empty] | Failed Redundancy test. Some nonuniformity.
1 | 20220040200065 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P47 | 1 |  |  |  |  | 0.215 | 0.246 | 5.9e-007 a | 1.9e-06 |  |  |  | 1 |  | 1 | 1
1 | 20220040200066 | 1 |  | 0 |  | 1 | 0 | 0 | 1
1 | 20220040200067 | 1 |  | 1 |  |  | 0 | 0 | 1 | 1 | 1 | [16 empty] | 1
1 | 20220040200068 |  | 1 | 1 |  |  |  | 0 | 1 | [19 empty] | Chip 1 LGS, worse at roomtemp. Fix (Ish 20?)/ replace chip?
1 | 20220040200069 | 1 |  | 0 |  |  | 0 | 0 | 1 | 0 | 1 | P34 | 1 |  |  |  |  | 0.246 | 0.287 | 1.7e-05 | 6.3e-05 | [5 empty] | 0 | 1
1 | 20220040200070 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1 | P48 | 1 |  |  |  |  | 0.205 | 0.246 | 7.3e-06 | 2.6e-05 |  |  | 2 |  |  | 2
1 | 20220040200071 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1 | P53 | 1 |  |  |  |  | 0.225 | 0.256 | 3.4e-06 | 9.6e-06 | [5 empty] | 0
1 | 20220040200072 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200073 | 1 | 1 | [5 empty] | 1
1 | 20220040200074 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200075 | 1 |  |  |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200076 | 1 |  |  |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200077 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200078 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200079 | 1 |  | 0 |  |  | 0 | 0 | 1 |  | 1
1 | 20220040200080 | 1 |  | 0 | 1 |  | 0 | 1 | 1 |  | 1
1 | 20220040200081 | 1 |  | 0 | 0 |  | 0 | 0 | 1 |  | 1
1 | 20220040200082 | 1 |  | 1 | 0 |  | 0 | 0 | 1 |  | 1
1 | 20220040200083 | 1 |  | 0 | 0 |  | 0 | 0 | 1
1 | 20220040200084 | 1 |  | 0 | 0 |  | 0 | 0 | 1
1 | 20220040200085 | 1 |  | 0 | 0 |  | 0 | 0 | 1
1 | 20220040200086 | 1 |  | 0 | 0 | 1 |  |  | 1
1 | 20220040200087 | 1 |  | 0 | 0 | 1 |  |  | 1
1 | 20220040200088 | 1 |  | 0 | 0 |  | 0 |  | 1
1 | 20220040200089 | 1 |  | 0 | 0 |  | 0 |  | 1
1 | 20220040200090 | 1 |  | 0 | 0 |  | 0 |  | 1
1 | 20220040200091 | 1 |  | 0 | 0 |  | 0 |  | 1
1 | 20220040200092 | 1 |  | 0 | 0 |  | 0 |  | 1
1 | 20220040200093 | 1 | [6 empty] | 1
1 | 20220040200094 | 1 | [6 empty] | 1
1 | 20220040200095 | 1 | [6 empty] | 1
1 | 20220040200096 | 1 | [26 empty] | Chip 1 0 Nocc Oscill.
1 | 20220040200097 | 1 |  | 0 |  |  |  |  | 1
20220040200098
20220040200099
20220040200100
20220040200101
20220040200102
20220040200103
20220040200104
20220040200105
20220040200106
20220040200107
20220040200108
20220040200109
20220040200110
20220040200111
20220040200112
20220040200113
1 | 20220040200114 | 1 | [6 empty] | 1
1 | 20220040200115 | 1 | [6 empty] | 1
1 | 20220040200116 | 1
20220040200117
20220040200118
20220040200119
20220040200120
20220040200121
20220040200122
20220040200123
20220040200124
20220040200125
20220040200126
20220040200127
20220040200128
20220040200129
20220040200130
20220040200131
20220040200132
1 | 20220040200133 | 1
1 | 20220040200134 | 1
1 | 20220040200135 | 1
1 | 20220040200136 | 1
1 | 20220040200137 | 1
1 | 20220040200138 |  | 1 | [25 empty] | Chip 8 LGS. Fix/ Replace?
20220040200139
20220040200140
20220040200141
20220040200142
20220040200143
20220040200144
20220040200145
20220040200146
20220040200147
20220040200148
20220040200149
20220040200150
20220040200151
20220040200152
20220040200153
20220040200154
20220040200155
20220040200156
20220040200157
20220040200158
20220040200159
20220040200160
20220040200161
20220040200162
20220040200163
20220040200164
20220040200165
20220040200166
20220040200167
20220040200168
20220040200169
20220040200170
20220040200171
20220040200172