## Sheet1
Atlas module production fixture list 5-Sept-01 V2.0 Carl Haber
number | item | quant | source dwg | drawing | source prod | status | comments | cost
1.1 | detector probing
1.1.1 | single detector chuck | 1 | LBL Carl |  |  | X |  | 250
1.1.2 | module chuck | 1 | LBL Carl |  |  | prototype |  | 250
1.1.3 | dark box | 1 | LBL |  |  | to be painted | COMPLETE
1.2 | hybrid assy/test | [6 empty] | 9150
1.2.1 | multi-purpose plate | 25-50 | LBL Goozen |  | LBL | X | for glue, cure, bond, r/w,test
1.2.1.1 | cover plate | 25-50 | LBL Goozen |  | LBL | X | plastic cover for MPP | 4480
1.2.1.2 | template for gluing | 4 | LBL Wirth |  | LBL | X | to spread epoxi for die attach | 320
1.2.1.3 | 6 chip tempate holder | 2 | LBL Goozen |  | LBL | X | holds ABCD for pickup | 160
1.2.1.4 | 6 chip vacuum pickup | 2 | LBL Goozen |  | LBL | X | pickup 6 chips for die attach | 320
1.2.1.5 | 1 chip vacuum pickup | 2 | LBL Goozen |  | LBL | X | pickup 1 chip for die attach | 160
1.2.1.6 | auto bonding holder | 2 | LBL Goozen |  | LBL | X | hold MPP on auto bonder | 320
1.2.1.7 | manual bonding holder | 1 | LBL Goozen |  | LBL |  | hold MPP on manual bonder | 160
1.2.2 | die removal tool | 1 | LBL Goozen |  | LBL |  | hot tip for die removal | 250
1.2.3 | probing jig | 1 | LBL Goozen |  | LBL | prototype | multi plate drops in | 100
1.2.4 | cooled test plate | 2 | LBL Goozen |  | LBL |  | 1 MPP screws down to this | 1280
1.2.5 | cooled burn-in plate | 2 | LBL Goozen |  | LBL | X | 6 MPP screw down to this | 1600
1.3 | module assembly | [6 empty] | 45040
1.3.1 | chucks | 2 | RAL |  | ElectroMec | final |  | 30000 | all ElectroMec
1.3.2 | vacuum pickup | 12 | RAL |  | ElectroMec | prototype
1.3.3 | window frame | 6 | RAL |  | ElectroMec | prototype
1.3.4 | b/b support | 6 | RAL |  | ElectroMec | prototype
1.3.5 | b/b survey | 1 | ? |  | ? | X
1.3.6 | b/b washer mount | 6 | ? |  | ? | X
1.3.7 | hybrid folding | 6 | LBL Goozen |  | LBL | prototype | could be a master and insert | 11200
1.3.8 | module holding tool | 2 | KEK |  | ? | prototype | use KEK design? | 3840
1.3.9 | module bonding | 2 | LBL Goozen |  | LBL | prototype | may be part of 1.3.7
1.4 | module metrology | [6 empty] | 1700
1.4.1 | metrology fixture | 1 | RAL |  | RAL | final (?) |  | 0
1.4.2 | offset fixture for SS | 1 | LBL Goozen |  | LBL | X | COMPLETE
1.4.3 | alignment pins | 12 | LBL Goozen | in progress | LBL | X |  | 1700
1.5 | module test
1.5.1 | test boxes | many | QMW Carter |  | ? | prototype |  | 70000
1.5.2 | burn-in plate | 2 |  |  |  |  | one for LBL one for SC | 1600