| Step | Plan | Actual |  |
| --- | --- | --- | --- |
| Feb. 28 | Install capillary, leak check, OSP bottom blankets, heaters | Capillary installed and leak checked OSP heaters and blankets on. ISP prep completed. ISP prep finished. ISPs attached | -1 |
| Mar. 1 | Finish ISP prep, continuity ISP, Attach ISPs | ENV routing about ¾ done. Fiber routing almost completed. | -0.5 |
| Mar. 2 | Route fibers, start ENV routing | Fiber routing completed. ENV routing completed but one open. Pictures have to be taken | -1.5 |
| Mar. 3 | Slack |  |  |
| Mar. 4 | Slack |  |  |
| Mar. 5 | Continue ENV routing, |  |  |
| Mar. 6 | Finish ENV, put upright |  |  |
| Mar. 7 | Install top optoboards, start testing |  |  |
| Mar. 8 | Finish opto testing, start mech work on opto |  |  |
| Mar. 9 | Finish mech work opto, attach and route heater cables. Start exhaust attach |  |  |
| Mar. 10 | Slack |  |  |
| Mar. 11 | Slack |  |  |
| Mar. 12 | Finish exhaust attach and leak check. Dress heater cables |  |  |
| Mar. 13 | Continuty. Can start |  |  |
| Mar. 14 | Can finish. Continuity |  |  |
| Mar. 15 | Repair. Continuity(if needed) |  |  |
| Mar. 16 | Final prep and box for SR1 |  |  |