## Trial Insertion of SQPs on BPSS A

Version 1.1

October 25, 2006

### Scope

Trial insertion and related includes the following goals

- Establish insertion setup

- Attachment of cans and buckets, bending to insertion position of wires/connectors on SQPs A1-2 and A3-4. Testing but only if possible and allowed by schedule.

- Placement of A1-2 and A3-4 on BPSS A and dummy loads to represent A5-6 and A7-8 and beampipe.

- Insertion of A1-2&A3-4 on BPSS A into forward section of PST and measurement of clearances

- Trial mate of PST to ¼-plate seal plates

- Removal of A1-2 and A3-4 from BPSS A and continuity test and repair(as required – can occur later)

- Removal of insertion setup. Restore BPSS A and PST to readiness.

### Basic Setup

See below.

### Work Plan

| Date | Goal/Tasks |
| --- | --- |
| 10/30 | Get organized. Assist in PST work(as needed to meet this schedule). Assist in prep for A1-2 and A3-4 |
| 10/31 | Unpack BPSS A. Ready foam blocks. Establish area for trial. Assist in PST work. Find/make dummy loads to represent A5-6 and A7-8 and beampipe. |
| 11/1 | Support foam blocks with rails. Attach spare sliders to BPSS A. Trial mount BPSS A on foam blocks. Ready A1-2 and A3-4 for attaching cans/buckets. Ready cans and buckets. Assist in PST work |
| 11/2 | Attach can and bucket to A1-2. Modify as required. |
| 11/3 | Attach can and buckets to A3-4. Modify as required |
| 11/4 | Slack |
| 11/5 | Slack |
| 11/6 | A1-2 wires and A3-4 wires to insertion position |
| 11/7 | Load A1-2 and A3-4 unto BPSS A. Load dummy weights. Align external sliders. |
| 11/8 | Mount PST and rail extensions. Align. |
| 11/9 | Slack |
| 11/10 | Insertion trial and measure clearances. Attach seal plates. |
| 11/11 | Slack |
| 11/12 | Slack |
| 11/13 | Remove A1-2 and A3-4 from BPSS A and unbend. |
| 11/14 | Continuity test A1-2 and A3-4. Identify repairs(as needed).Start setup removal |
| 11/15 | Complete setup removal. Restore BPSS A and PST to readiness |
| 11/16 | Slack |
| 11/17 | Slack |

# Text boxes

Rails on foam blocks

PST

BPSS A

Rails on foam blocks

PP0 end of BPSS