## Sheet1
US-ATLAS-SCT hybrid-module production testing part list |  |  | A. Ciocio - October 24, 2001
LBNL
PARTS | QTY | FROM | STATUS | Est. Delivery | COST | Comments | LBNL | UCSC
Hybrid testing
support cards | 1 | Gareth | there |  | 82 |  | 82
Mustard/Slog | 1 | UK | there |  | 5054 | 3450 GPB |  | 5054
PPR | 1 | Gareth | there |  | 105 |  | 105
cables |  |  | there |  | 100 | material | 100
SCTLV | 1 | Prague | there |  | 1119 | 1800 CHF each |  | 1119
SCTLV cables |  |  | to be made | October | 100 | material | 100
Power supply (-5V) for VME | 1 |  | there
VME crate | 1 |  | there
NI controller/interface | 1 | Nat Instr | there
PC | 1 |  | there
Module Testing
support cards | 1 | Gareth | received | October | 82 |  | 82
Mustard/Slog | 1 | UK | on order | November | 3853 | 2630 GPB | 3853
PRR | 1 | Gareth | there |  | 105 |  | 105
cables |  |  | to be made | October | 100 | material | 100
SCTLV | 1 | Prague | there |  | 1119 | 1800 CHF each |  | 1119
SCTLV cables |  |  | to be made | October | 100 | material | 100
HV-bias /4mod | 1 | Crakow | on order | December | 1026 | 1645 CHF |  | 1026
Power supply (-5V) for VME | 1 |  | to be purchased |  | 500 |  | 500
VME crate | 1 |  | ordered |  | 3500 | 3115 | 3115
NI controller/interface | 1 | Nat Instr | ordered |  | 3400 | 3430 | 3430
PC | 1 |  | ordered |  | 2500 | 2100 | 2100
NI-GPIB-PCI interface | 1 |  |  |  | 500 |  | 500
PARTS | QTY | FROM | STATUS | Est. Delivery | COST | Comments | LBNL | UCSC
Hybrid burn in
patch cards/connectors | many | Lars/CERN | received | October | 621 | 1000 CHF | 621
support cards | 6 | Gareth | received | October | 492 |  | 492
Mustard/Slog | 1 | UK | on order | November | 3853 | 2630 GPB | 3853
PPR | 1 | Gareth | there |  | 105 |  | 105
cables |  |  | to be made | October | 100 | material | 100
SCTLV 2ch | 4 | Prague | there |  | 4476 | 1800 CHF each |  | 4476
SCTLV cables |  |  | to be made | October | 100 | material | 100
Power supply (-5V) for VME | 1 |  | to be purchased |  | 500 |  | 500
VME crate | 1 |  | ordered |  | 3500 | 3115 | 3115
NI controller/interface | 1 |  | ordered |  | 3400 | 3430 | 3430
PC | 1 |  | ordered |  | 2500 | 2100 | 2100
Module burn in
support cards | 6 | Gareth | received | October | 492
Mustard/Slog | 1 | UK | on order | November | 3853 | 2630 GPB | 3853
PPR | 1 | Gareth | there |  | 105 |  | 105
cables |  |  | to be made | October | 100 | material | 100
SCTLV 2ch | 4 | Prague | there |  | 4476 | 1800 CHF each |  | 4476
SCTLV cables |  |  | to be made | October | 100 | material | 100
HV-bias /4mod | 2 | Crakow | on order | soon | 2052 | 1645CHF each |  | 2052
Power supply (-5V) for VME | 1 |  | to be purchased |  | 500 |  | 500
VME crate | 1 |  | ordered |  | 3500 | 3115 | 3115
NI controller/interface | 1 |  | to be purchased |  | 3400 |  | 3400
PC | 1 |  | to be purchased |  | 2500 |  | 2500
Spares
Mustard/Slog | 1 | UK | on order | November | 3853 | 2630 GPB | 3853
PPR | 1 | Gareth | there |  | 105 |  | 105
Support cards | 6 | Gareth | received | October | 492 |  | 492
patch cards/connectors | 660 or less | Lars/CERN or US | to be ordered | January | 9000 | estimate upper limit | 9000
HV-bias /4mod | 1 | Crakow | on order | December | 1026 | 1645 CHF each |  | 1026
UCSC
PARTS | QTY | FROM | STATUS | Est. Delivery | COST | Comments | LBNL | UCSC
Module Testing
support cards | 1 | Gareth | there |  | 82 |  | 82
Mustard/Slog | 1 | UK | there |  | 5054 | 3450 GPB |  | 5054
PPR | 1 | Gareth | there |  | 105 |  | 105
cables |  |  | there
SCTLV 2ch | 1 | Prague | there |  | 1119 | 1800 CHF each |  | 1119
SCTLV cables |  |  | there
HV-bias /4mod | 1 | Crakow | on order | December | 1026 | 1645 CHF each |  | 1026
Power supply (-5V) for VME | 1 |  | there
VME crate | 1 |  | there
NI controller/interface | 1 | Nat Instr | there
PC | 1 |  | there
Hybrid burn in
support cards | 6 | Gareth | received | October | 492 |  | 492
Mustard/Slog | 1 | UK | on order | November | 3853 | 2630 GPB | 3853
PPR | 1 | Gareth |  |  | 105 |  | 105
cables |  |  | to be made | October | 100 |  | 100
SCTLV 2ch | 4 | Prague | there |  | 4476 | 1800 CHF each |  | 4476
SCTLV cables |  |  | to be made | October | 100 |  | 100
Power supply (-5V) for VME | 1 |  | there
VME crate | 1 |  | there
NI controller/interface | 1 |  | there
PC | 1 |  | there
Mustard/Slog/PPR(SPARE) | 1 | UK | on order | November | 3853 | 2630 GPB | 3853
PPR(SPARE) | 1 | Gareth |  |  | 105 |  | 105
TOTALS
[7 empty] | LBNL | UCSC
COST
[7 empty] | 64606 | 32023
Software
long term test macro: |  | UK (Dave Charlton) |  | soon
continuous triggers, but to run
tests periodically to check that
everything works
checks to switch off power
Database |  | LBNL/UK |  | November
Additional comments
In red the cost of item still to be purchased.
The cost of the Mustards systems differ (as you might recall from Andy's message) for the two different orders. The systems we have
already were 3450 GBP each, while the additional 5 systems are 13,150 GBP (2630 each).
The cost for the patch and connectors + soldering at CERN is ~1000 CHF for 42 cards. If we need to fabricate one card for each
hybrid/module we produce, we need 660 more. At some point there will be some recycling therefore we would need less
than that. It will try to investigate how much it would cost to make them in the US once we get the layout from OSLO/CERN.