U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 1) BCP Number: 29 |  | 2) BCP Title: FY2000 ETC Rebaseline for WBS 1.1 |  |
| --- | --- | --- | --- |
| 3) Budget Number: WBS 1.1 |  | 4) MSA Title: U.S. ATLAS |  |
| 5) Date Submitted (Project Office): 5/1/00 |  |  |  |
| 6) Change Designation: Priority [ ] Routine [ X ] | 7) BCP Level Level 0 [ ] Level 2 [ ] Level 1 [ ] Level 3 [X] | 8) Directed Change? Yes [ ] No [X ] |  |
| 10) Point of Contact: M. Gilchriese 11) Phone: 510-486-6790 12) FAX : 510-486-5101 12a) E-mail: gilg@sts.lbl.gov 13) Address: Lawrence Berkeley National Laboratory, MS50B-6208, 1 Cyclotron Rd., Berkeley CA 94720 |  |  |  |
| 14) Change Description: This BCP is to rebaseline the cost and schedule for the Silicon Subsystem. An Estimate-To-Complete(ETC) for WBS 1.1 was performed to determine the costs of completing the Silicon Subsystem from October 1, 1999 to the end of the Project. The major changes relative to the Baseline are summarized here: Pixel Subsystem(baseline development phase only) WBS 1.1.1.1 Addition of funds for design, integration and fabrication of services prototypes and mockups including flex cables, other cables and coolant connections. Addition of funds for procurement of an optical coordinate measuring machine. WBS 1.1.1.4 Addition of funds for additional prototypes of flex hybrids and for loading, testing and assembly of these hybrids. Silicon Strip Subsystem WBS 1.1.2.1 Increased scope of IC procurement, changing baseline scope from about 30% of all ICs need for the ATLAS SCT to 45%. Revised costs based on new baseline IC(ABCD), including acceleration of preproduction fabrication. Addition of funds for systems engineering and administrative support for IC electronics. Additional engineering for IC test systems. WBS 1.1.2.2 Reduction in scope of hybrid activities to eliminate procurement of hybrid substrates. Deliverables:(1) prototype design of beryllia hybrids and (2) assembly/test of hybrids utilizing loaded substrates provided by ATLAS to yield 727 good hybrids for module assembly. WBS 1.1.2.3 Reduction in scope of module activities to eliminate procurement of thermal baseboards. Increased labor for mounting ICs to hybrids, hybrid testing and for module assembly and testing. ReadOut Drivers Revised definition of US deliverables to be 100% of ROD VME boards and associated crates to define precisely the interface with other elements of the SCT and pixel readout/DAQ system(eg. back-of-crate cards and readout controller cards) provided by non-US ATLAS members. Revised estimates for prototype and production parts costs based on more mature design/schematic. |  |  |  |
| 15) Change Justification: A comprehensive estimate to complete the work to be performed to meet the US ATLAS baseline deliverables and goals was conducted at the beginning of FY2000. Cost estimates have been adequately documented and stringently reviewed for completeness and accuracy, and a new schedule to complete the baseline effort has been developed. The results of this effort are summarized on attached pages. This effort represents the best estimate of the time and cost necessary to complete the US ATLAS obligations. |  |  |  |
| 16) Impact of Non-Approval: US ATLAS will not be able to meet its cost and schedule baseline. |  |  |  |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 17) BCP Number: 29 | 18) BCP Title: FY2000 ETC Rebaseline for WBS 1.1 |  |  |
| --- | --- | --- | --- |
| 19) Impact on Cost Baseline: | Baseline (AY$ in Thousands) | Proposed (AY$ in Thousands) | AY$ Change |
| WBS 1.1 | $10,811.2k | $11,351.5k | $540.3k |
| 20) Impact on Funding Profile: None |  |  |  |
| 21) Explanation of Impact on Cost and Funding Baselines: This budget authority is required in FY00. The impact to the currently approved funding profile will be negligible. |  |  |  |
| 22) Impact on Schedule Baseline: See attached pages for change to baseline schedule. |  |  |  |
| 23) Explanation of Impact on Schedule Baseline: None |  |  |  |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 24) BCP Number: 29 | 25) BCP Title: FY2000 ETC Rebaseline for WBS 1.1 |  |  |  |
| --- | --- | --- | --- | --- |
| 26) Impact on Scope Baseline: |  |  |  |  |
| Item |  | Baseline | Proposed | Change |
| 1.1.2.1 IC Electronics(number of good ICs) 1.1.2.2 Hybrids 1.1.2.3 Modules |  | 18,252 Chip sets or Chips (base scope) (30%) 30,420 (goal) 727(substrates &assembly) 670 (including procure thermal baseboards) | 27,104 Chip sets or Chips (base scope) (45%) 39,150 (goal) 727(assembly only) 670 (no procure-ment of thermal baseboards) | +8,852 Chip sets or Chips (15%) +8,730 (goal) -727 substrates -670 thermal baseboards |
| 27) Explanation of Impact on Scope Baseline: This proposed change in scope does not affect the cost for WBS 1.1.2. There is a proposal to increase the amount of the chips deliverable under WBS 1.1.2.1 in exchange for the cost to procure the hybrids for WBS 1.1.2.2. This will increase in number of deliverable ICs as above, with a consequent decrease in procurement of hybrid substrates (WBS 1.1.2.2)(deleted entirely) and decrease in procurement of module thermal baseboards (WBS1.1.2.3)(deleted entirely). The deliverable doesn’t appear to change for WBS 1.1.2.2 because US ATLAS will still provide the labor to assemble the deliverable number of hybrid module assemblies. For WBS 1.1.2.3, there is a reduction in scope of module activities to eliminate procurement of module thermal baseboards. Final deliverables remain the same: 670 barrel modules delivered to UK assembly site. |  |  |  |  |
| 28) Other Impacts: (Health, Safety, Environment, etc.) None |  |  |  |  |
| 29) Interim or Corrective Actions: None |  |  |  |  |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 30) BCP Number: 29 | 31) BCP Title: FY2000 ETC Rebaseline for WBS 1.1 |  |  |
| --- | --- | --- | --- |

PROJECT DISPOSITION - LEVEL 3

| 32) REVIEW RECOMENDATIONS: |  |
| --- | --- |
| U.S. ATLAS Project Manager W. Willis | Disposition [ ] Approve [ ] Reject |
|  | DATE: |
| BNL Associate Laboratory Director T. Kirk | Disposition [ ] Approve [ ] Reject |
|  | DATE: |

# LHC PROJECT MANAGER DISPOSITION – LEVEL 2

| LHC Project Manager J. Yeck | Disposition [ ] Approve [ ] Reject |
| --- | --- |
|  | DATE: |
| NSF Project Manager | Disposition [ ] Approve [ ] Reject DATE: |

## AGENCY DISPOSITION - LEVEL 1

| 33) Joint Oversight Group | RECOMMENDATION |
| --- | --- |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| ATLAS/CERN | RECOMMENDATION |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| DISPOSITION |  |
| Chairperson Date [ ] Endorsed [ ] Approved [ ] Rejected |  |
| 34) Explanation (If Action is Approved with Conditions, or Not Concurred Upon) |  |

|  |  | Access Comparision (Silicon Level 3) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | (Project FY00K$s) |  |  |  |  |
|  |  |  | ETC |  | TPC |  |
|  | Old Access | Old Access | New Access | Actuals | New Access |  |
| WBS | (FY97 $S) | (Converted to FY00 $s) | ( in FY00 $s) | Thru FY99 | Plus Actuals | **Delta |
| 111 | 2,209 | 2,347 | 1,586 | 1,005 | 2,591 | (244) |
| 112 | 5,364 | 5,698 | 4,850 | 911 | 5,761 | (63) |
| 113 | 2,401 | 2,551 | 2,186 | 630 | 2,816 | (265) |
| Total | 9,974 | 10,596 | 8,622 | 2,546 | 11,168 | (572) |
|  | **Delta = Old Access (FY00$s) minus |  |  |  |  |  |
|  | New Access Plus Actuals |  |  |  |  |  |
|  |  |  |  | Table 6-1 | ETC (AY$s) | Difference |
|  |  |  | WBS | (AY$s) | Plus Actuals | (AY$s) |
|  |  |  | 1.1 Silicon | 8,424.5 | 8,760.5 | (336.0) |
|  |  |  | 1.1.1 Pix Pre-Tech |  |  |  |
|  |  |  | Appr. Baseline | 2386.7 | 2,591.0 | (204.3) |
|  |  |  | Total | 10,811.2 | 11,351.5 | (540.3) |
| ETC - Estimate to Complete starting in Oct 1999 |  |  |  |  |  |  |
| TPC - Total Project Costs at Completion |  |  |  |  |  |  |

|  | U.S. ATLAS Silicon Level 2-4 Milestones Comparision |  |  |
| --- | --- | --- | --- |
|  |  | Level 2 Milestones |  |  |  |  |
|  |  |  | Baseline | ETC |  |  |
|  | Schedule |  | Schedule | Schedule |  |  |
| Subsystem | Designator | Description | Date | Date |  |  |
| Silicon | Sil L2/1 | Start Full Silicon Strip Elec Prod | 30-Mar-01 | 23-Apr-01 |  |  |
|  | Sil L2/2 | Start Full Strip Module Production | 15-Oct-99 | 26-Nov-01 |  |  |
|  | Sil L2/3 | ROD Design Complete | 14-Apr-00 | 14-Jun-01 |  |  |
|  | Sil L2/4 | Compl Shipment of Silicon Strip Modules Prod | 8-Aug-03 | 13-Oct-03 |  |  |
|  | Sil L2/5 | ROD Production/Testing Complete | 30-Sep-04 | 13-Mar-03 |  |  |
|  |  | Level 3 Milestones (Goals) |  |  |  |  |
|  |  |  | Baseline | ETC |  |  |
|  | Schedule |  | Schedule | Schedule |  |  |
| Subsystem | Designator | Description | Date | Date |  |  |
| Silicon | Sil L3/1 | Pixel System | N/A | N/A |  |  |
|  | Sil L3/2 | Silicon Strip System | 26-Aug-03 | 13-Oct-03 |  |  |
|  | Sil L4/3 | Read-Out Drivers | 1-Sep-03 | 13-Mar-03 |  |  |

|  |  | Level 4 Milestones (Baseline Scope) |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | U.S. ATLAS | Baseline | Forecast (F)/ |  | Baseline |
|  |  | Responsibility | Scope | Actual (A) | ATLAS | Scope |
| WBS | WBS | Completion | Planned | Baseline Scope | Required | Planned |
|  | Description | Description | Shipping | Shipping | Date | Float |
|  |  |  | Date | Date |  | (Months) |
| Silicon |  |  |  |  |  |  |
| 1.1.2 | Silicon Strip | Compl Shipping of Prod Modules | 10/03 | 10/03 | 4/03 | -6 |
| 1.1.3 | RODs | ROD 45% Production Compl | 4/02 | 4/02 | 6/03 | 14 |