# Disconnnect PP1

Assumptions

The time needed to disconnect PP1 and related items does not include the following

- Time needed to gain access to the PP1 region

- Time needed to establish working platform and temporary “clean” room/humidity controlled area at both Side A and Side C. My guess is 3 days.

- Activation cool-down time needed. No guess. Depends on when 3rd hit is installed.

# Time Estimate

The number of connections assumed for 2-hit system is given below.

| Side C |  |  |
| --- | --- | --- |
| Cooling circuits | 80 |
| Cable bundles | 90 |
| Fiber bundles | 90 |
| Side A |  |  |
| Cooling circuits | 58 |
| Cable bundles | 90 |
| Fiber bundles | 90 |

The time estimated to disconnect cooling fittings, bag the transition pieces and cap the ends(to keep them clean) is

|  |  |  |  | Minutes | Hours |
| --- | --- | --- | --- | --- | --- |
| Disconnect cooling circuits - Side C | Each | Total |
|  |  | Disconnect PP1b | 1 | 1.3 |
|  |  | Disconnect PP1a | 1 | 1.3 |
|  |  | Cover ends/bag | 1 | 1.3 |
|  |  | Move to next | 2 | 2.7 |
|  |  |  | Total | 5 | 6.7 |
|  |  |  |  | Minutes | Hours |
| Disconnect cooling circuits - Side A | Each | Total |
|  |  | Disconnect PP1b | 1 | 1.0 |
|  |  | Disconnect PP1a | 1 | 1.0 |
|  |  | Cover ends/bag | 1 | 1.0 |
|  |  | Move to next | 2 | 1.9 |
|  |  |  | Total | 5 | 4.8 |

The time estimated to disconnect cable bundles is

|  |  |  |  | Minutes | Hours |
| --- | --- | --- | --- | --- | --- |
| Disconnect cables bundles - Side C | Each | Total |
|  |  | Disconnect PP1b | 1 | 1.5 |
|  |  | Disconnect PP1a | 1 | 1.5 |
|  |  | Bag transition | 1 | 1.5 |
|  |  | Fold back/dress | 2 | 3 |
|  |  | Move to next | 1 | 1.5 |
|  |  |  | Total | 6 | 9 |
|  |  |  |  | Minutes | Hours |
| Disconnect cables bundles - Side A | Each | Total |
|  |  | Disconnect PP1b | 1 | 1.5 |
|  |  | Disconnect PP1a | 1 | 1.5 |
|  |  | Bag transition | 1 | 1.5 |
|  |  | Fold back/dress | 2 | 3 |
|  |  | Move to next | 1 | 1.5 |
|  |  |  | Total | 6 | 9 |

The time estimated to disconnect fiber bundles and protect/cap the ends is

|  |  |  |  | Minutes | Hours |
| --- | --- | --- | --- | --- | --- |
| Disconnect fiber bundles - Side C | Each | Total |
|  |  | Disconnect PP1b | 1 | 1.5 |
|  |  | Disconnect PP1a | 1 | 1.5 |
|  |  | Cap ends |  | 1 | 1.5 |
|  |  | Fold back/dress | 2 | 3 |
|  |  | Move to next | 1 | 1.5 |
|  |  |  | Total | 6 | 9 |
|  |  |  |  | Minutes | Hours |
| Disconnect cables bundles - Side A | Each | Total |
|  |  | Disconnect PP1b | 1 | 1.5 |
|  |  | Disconnect PP1a | 1 | 1.5 |
|  |  | Cap ends |  | 1 | 1.5 |
|  |  | Fold back/dress | 2 | 3 |
|  |  | Move to next | 1 | 1.5 |
|  |  |  | Total | 6 | 9 |

The time needed to support the beam pipe at PP1 and to disconnect PP1 from the PST is very uncertain. Here is my guess for each side.

- Lockout PP1 flexures(has to be done before any work on cooling, cables or fibers but included here), remove permanent PP1 bellow attachments to beam pipe(1 hour)

- Attach lockout PP1 bellows and attach beam pipe support to bellows(this may mean not removing permanent attachment to beam pipe collar but maybe not)(2 hours)

- Attach PP1 to internal support. This assumes removable support of PP1 to internal support(maybe not so)(2 hours)

- Remove external beam pipe supports(I’m not clear on when this happens, would be good to do before disconnecting cooling, cabling etc)(2 hours)

- Remove connection to PST(1 hour)

- Verify that package can be moved(1 hour)

So the total to exchange beam pipe supports and to ready package for removal is 9 hours.

# Summary of Time Estimates

I assume there are teams working simultaneously on Side A and on Side C. A minimum team of 2 people per side is needed.

|  | Hours |
| --- | --- |
| Exchange beam pipe supports, disconnect from PST | 9 |
| Disconnect cooling pipes | 7 |
| Disconnect cables | 9 |
| Disconnect fibers | 9 |
| Total | 34 |

A conservative assumption at this stage is to take 7 hours per day of real work time. Thus the total estimated time to disconnect PP1 and be ready for removal is 5 days.

Reconnection of PP1

The time to reconnect PP1 and verify connections will be longer than the time estimate above. I believe there is considerable uncertainty about what electrical tests will be possible at the cable bundle-by-cable bundle level. I assume they can be done but these are not the same as system tests. I also assume safety issues regarding handling the fiber bundles can be solved without impacting the time needed to plug them in.

I assume it takes 10 minutes to do a simple vacuum/pressure test of each coolant circuit. This is an additional (40+29+19+8)x10= 960 minutes or about 16 hours.

I assume it takes an additional 1 minute for electrical testing after connection of a cable bundle and fiber bundle. To this I believe one has to add 2 minutes for communication and logging of the results. I assume this cannot be done simultaneously on Side A and Side C. So there are  2x128 connections to test at 3 minutes each or 768 minutes or about 13 hours. This adds about 4 days to the 5 days above, assuming that cooling testing and continuity checking cannot be interleaved. If they could be totally interleaved, then it’s about an extra 2 days. So the total time to reconnect PP1 is 7-9 days.