U.S. ATLAS MOU NO. ?/00

Amendment

to

Memorandum of Understanding

between

Lawrence Berkeley National Laboratory

and

The U.S. ATLAS Project Office

for Fiscal Year FY 2000

Revision A

April 20, 2000

1.	Introduction

This Amendment is made to provide details of the work agreed to between the parties making the Memorandum of Understanding covering the specific  period of performance from October 1, 1999 through September 30, 2000.  It is subject to all the points of agreement and conditions in the current version of the parent Memorandum and the current version of the U.S. ATLAS Project Management Plan (U.S. ATLAS 97-7). This is a revision to the FY00 Amendment and documents additional funds already provided to LBNL beyond those specified in the original FY00 Amendment.

2.	Personnel

2.1.	List of Scientific Personnel

Participating scientists with anticipated fraction of their research time committed to ATLAS during this period of performance are:

| Name | ATLAS Fraction | Other Research Commitments/Comments |
| --- | --- | --- |
| M. Barnett | 0.2 | Particle Data Group, Theory |
| D. Bintinger | 1.0 |  |
| A. Ciocio | 1.0 |  |
| K. Einsweiler | 0.9 | CDF |
| Jean-Francois Genat | 0.3 | Visiting physicist |
| M. Gilchriese | 1.0 |  |
| C. Haber | 0.5 | CDF |
| I. Hinchliffe | 0.5 | Theory |
| S. Loken | 0.1 | Div. Head |
| H. Niggli | 1.0 |  |
| J. Richardson | 1.0 |  |
| M. Shapiro | 0.2 | CDF |
| J. Siegrist | 0.1 | Div. Head |
| H. Spieler | 0.5 | Instrumentation development |
| G. Trilling | 1.0 |  |
| L. Vacavant | 1.0 |  |
| Additional postdocs | 1.4 FTE |  |

2.2.	Institutional Board Representative

M. Gilchriese is the present representative of Lawrence Berkeley National Laboratory on the U.S. ATLAS Collaboration Board.

2.3.	List of Technical Personnel

Participating technical personnel with the anticipated fraction of their time committed to ATLAS during this period of performance and their source(s) of support are:

Engineers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| E. Anderssen | 1.0 | LBNL |
| F. Goozen | 0.9 | LBNL |
| E. Mandelli | 0.9 | LBNL |
| G. Meddeler | 0.9 | LBNL |
| N. Palaio | 0.05 | LBNL |
| F. Pengg | 0.1 | LBNL |
| TBD | 1.5 | LBNL/ATLAS Project |

Designers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| B. Holmes | 0.25 | LBNL |
| J. Taylor | 0.95 | LBNL |
| P.Luft | 0.3 | LBNL |

Technicians

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| F. McCormack | 1.0 | LBNL |
| T. Weber | 0.9 | LBNL |
| J. Wirth | 1.0 | LBNL |
| G. Zizka | 0.25 | ATLAS Project/LBNL |

Software Professionals

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| P. Calafiura | 0.5 | LBNL |
| C. Leggett | 0.5 | LBNL |
| J. Milford | 1.0 | ATLAS Computing |
| D. Quarrie | 0.15 | ATLAS Computing |
| C. Tull | 1.0 | ATLAS Computing |
| TBN | 0.85 | ATLAS Computing |

ATLAS computing refers to non-project funds for support of ATLAS software development. It is understood that a separate MoU between LBNL and U.S. ATLAS will be written to specify software deliverables.

Others

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| Shop personnel | 0.3 | ATLAS project |
| Shop personnel | 0.2 | LBNL |
| Student testing labor | 0.5 | ATLAS Project |
| Student labor(other) | 0.5 | LBNL |

2.4.	Other Key Personnel

The Environment, Safety and Health officer for Lawrence Berkeley National Laboratory currently responsible for compliance with applicable ES&H policies associated with ATLAS participation by this institution is Kathy Hardy of Lawrence Berkeley National Laboratory.  The Quality Assurance officer for Lawrence Berkeley National Laboratory currently responsible for QA compliance of tasks performed by this institution is M. Gilchriese of Lawrence Berkeley National Laboratory.

3. 	Design, Prototype, Production and Installation Responsibilities

3.1.	Design, Prototype and Production Responsibilities for this Period of Performance

3.1.1	Deliverables: From U.S. ATLAS Project Funds:

LBNL will receive a total of $268.3FY00 ATLAS Project funds for the work and deliverables summarized in the tables below.

| 1.1.1 | Pixel System | 80.5 |
| --- | --- | --- |
| WBS (L5) | Pixel Electronics | 80.5 |
| 1.1.1.3.2 | Development and Prototypes | 80.5 |
|  | Test boards and equipment, chip fabs | 187.8 |
| 1.1.2 | Silicon Strip System |  |
| WBS (L5) | Hybrids | 79.0 |
| 1.1.2.2.2 | Development and Prototypes | 24.8 |
|  | Prototype hybrid fabrication and testing |  |
| 1.1.2.2.3 | Production | 54.2 |
|  | Preproduction hybrid fabrication, assembly and test |  |
| WBS (L5) | Modules | 108.8 |
| 1.1.2.3.1 | Design | 73.0 |
|  | Design of tooling, procedures for module assembly/test |  |
| 1.1.2.3.3 | Production | 35.8 |
|  | Production equipment |  |

3.2.	Coordination and  Reporting

The U.S. ATLAS L2 Manager for the silicon subsystem is M. Gilchriese. The institution contact person for silicon subsystem activities at Lawrence Berkeley National Laboratory is M. Gilchriese. The task managers for silicon subsystem activities carried out at Lawrence Berkeley National Laboratory are as follows:

WBS 1.1.1 Pixel System (M. Gilchriese)

WBS 1.1.1.1 Mechanics (M. Gilchriese)

WBS 1.1.1.3 Electronics (K. Einsweiler)

WBS 1.1.1.5 Modules (M. Gilchriese)

WBS 1.1.2 Silicon Strip System (C. Haber)

WBS 1.1.2.1 Silicon Strip IC Electronics (H. Spieler)

WBS 1.1.2.2 Silicon Strip Hybrids (C. Haber)

WBS 1.1.2.3 Silicon Strip Modules (C. Haber)

- Collaboration with Other Groups and Institutions

No amendments are included in this section.

Design, construction and installation related to the silicon subsystem will be carried out in close communication and collaboration with other groups working on this and related subsystems.

4.	Contribution of Effort, Services and Equipment

4.1.	Effort

Subject to adequate funding by DOE , Lawrence Berkeley National Laboratory will provide support for the scientific and technical personnel as indicated in section 2 during this period of performance.

5. 	Costs and Funding

An amount of $268.3K from ATLAS Project funds will be provided for the period October 1, 1999 - September 30, 2000 to cover work described under 3.1.1.

6.	Administration (no amendments are included in this section)

7.	General Considerations (no amendments are included in this section)

8.	Schedules and Milestones

Lawrence Berkeley National Laboratory will make every effort to carry out their institutional responsibilities consistent with the overall ATLAS schedule.  In this amendment are listed the program milestones for this period of performance.

8.1.	Design, Fabrication and Installation Milestones

The program milestones for this period of performance relevant to Lawrence Berkeley National Laboratory are listed here:

| WBS | Item | Baseline | Current | Milestone |
| --- | --- | --- | --- | --- |
| 1.1.1 | Pixel System | 29-May-00 | 1-Sep-00 | Baseline review |
| 1.1.1.1 | Pixel Mechanics |  |  |  |
| 1.1.1.1.1 | Design/Engineering |  |  |  |
|  |  | 1-Sep-99 | 1-Nov-99 | Select sector baseline concept |
|  |  | 1-Sep-99 | 1-Oct-99 | Module attachment conc. Design rev. |
|  |  | 3-May-00 | 3-May-00 | PRR for sectors |
|  |  | 3-May-00 | 3-May-00 | Disk Preliminary Design Review(PDR) |
|  |  | 3-May-00 | 3-May-00 | Module attach PDR |
|  |  | 3-May-00 | 3-May-00 | Support structure conc. Des. review |
| 1.1.1.1.2 | Development/Protos |  |  |  |
|  |  | 1-Sep-99 | 1-Nov-99 | Complete testing 5-disk prototypes |
|  |  | 21-Dec-99 | 1-Feb-00 | Complete testing of disk prototype |
|  |  | 3-May-00 | 3-May-00 | Complete test of proto module attach |
| 1.1.1.3 | Pixel Electronics |  |  |  |
| 1.1.1.3.1 | Design/Engineering |  |  |  |
|  |  | 5-Mar-99 | 15-Nov-99 | FDR of 1st Honeywell SOI proto |
|  |  | 2-Apr-99 | 15-Jan-00 | Compl. Design of 1st Honey. SoI proto |
|  |  | 12-Jun-00 | 15-Oct-00 | FDR of 2nd rad-hard proto |
|  |  | 7-Jul-00 | 15-Nov-00 | Compl. Design of 2nd rad-hard proto |
| 1.1.1.3.2 | Development/Protos |  |  |  |
|  |  | 9-Dec-99 | 15-Jun-00 | Compl. Testing of 1st DMILL proto |
|  |  | 25-Aug-99 | 15-Apr-00 | Compl. Fab of 1st Honey SOI proto |
|  |  | 15-Feb-00 | 15-Sep-00 | Compl. Testing 1st Honey SOI proto |
|  |  | 19-Jan-00 | 15-Jun-00 | Review design approach |
|  |  | 29-Feb-00 | 15-Jul-00 | Vendor selection |
| 1.1.1.5 | Pixel Modules |  |  |  |
| 1.1.1.5.1 | Design/Engineering |  |  |  |
|  |  | 17-Sep-99 | 25-Sep-99 | 2nd prototype design review |
|  |  | 14-Oct-99 | 14-Oct-99 | Compl. 2nd prototype design |
|  |  | 2-Oct-00 | 2-Oct-00 | 3rd prototype design review |
|  |  | 27-Oct-00 | 27-Oct-00 | Compl. 3rd prototype design |
| 1.1.1.5.2 | Development/protos |  |  |  |
|  |  | 18-Mar-99 | 1-Oct-99 | Compl. Tests of 1st prototypes |
|  |  | 3-Apr-00 | 3-Apr-00 | Compl. Tests of 2nd prototypes |
|  |  | 3-Apr-00 | 3-Apr-00 | Select production module vendors |
| 1.1.2 | Silicon Strip System |  |  |  |
| 1.1.2.1 | Silicon Strip Electronics |  |  |  |
| 1.1.2.1.1 | Design/Engineering |  |  |  |
|  |  | 3-Mar-00 | 3-Mar-00 | Compl. Spec for preprod release order |
|  |  | 3-Mar-00 | 3-Mar-00 | Final Design Review |
| 1.1.2.1.3 | Production |  |  |  |
|  |  | 12-Dec-99 | 12-Dec-99 | Select approach/IC vendor |
|  |  | 31-Mar-00 | 31-Mar-00 | Start preproduction run |
|  |  | 1-Sep-00 | 1-Sep-00 | Complete preproduction fab |
| 1.1.2.2 | Silicon Strip Hybrids/Cables |  |  |  |
| 1.1.2.2.1 | Design/Engineering |  |  |  |
|  |  | 11-Feb-00 | 11-Feb-00 | Compl. preprod substrate design |
|  |  | 11-Feb-00 | 11-Feb-00 | Compl. preprod cable design |
|  |  | 11-Feb-00 | 11-Feb-00 | Compl. preprod fanout design |
|  |  | 11-Feb-00 | 11-Feb-00 | Hybrid Final Design Review |
|  |  | 11-Oct-00 | 11-Oct-00 | Start procurement prod. hybrids |
| 1.1.2.2.2 | Development/Protos |  |  |  |
|  |  | 8-Dec-99 | 8-Dec-99 | Compl test of 2nd proto hybrids |
| 1.1.2.2.3 | Production |  |  |  |
|  |  | 10-Dec-99 | 10-Dec-99 | Select hybrid substrate type |
|  |  | 23-Jun-00 | 23-Jun-00 | Compl fab of preprod substrate |
|  |  | 23-Jun-00 | 23-Jun-00 | Compl fab of preprod cable |
|  |  | 23-Jun-00 | 23-Jun-00 | Compl fab of preprod fanout |
|  |  | 23-Jun-00 | 23-Jun-00 | Compl proc of preprod components |
|  |  | 13-Oct-00 | 13-Oct-00 | Compl preproduction assembly |
| 1.1.2.3 | Silicon Strip Modules |  |  |  |
| 1.1.2.3.1 | Design/Engineering |  |  |  |
|  |  | 14-Jun-99 | 15-Nov-99 | Compl design of proto tooling |
|  |  | 27-Dec-99 | 27-Dec-99 | PDR of module assembly |
|  |  | 10-Nov-00 | 10-Nov-00 | FDR of module assembly |
| 1.1.2.3.2 | Development/Protos |  |  |  |
|  |  | 14-Jun-99 | 15-Nov-99 | Compl. Fab Tooling for proto assembly |
|  |  | 29-Nov-99 | 29-Nov-99 | Compl assembly of prototype modules |
|  |  | 27-Dec-99 | 27-Dec-99 | Compl tests of proto modules |
| 1.1.2.3.3 | Production |  |  |  |
|  |  | 10-Nov-00 | 10-Nov-00 | Compl fab of tools for preprod modules |

9.	Makers and Concurrence

The following persons concur in the terms of this Amendment.  These terms will be updated as appropriate in later Amendments to this Memorandum.

Makers of this Memorandum:

William J. Willis	date	Jim Siegrist	date

U.S. ATLAS Project Manager		Director, Physics Division

Lawrence Berkeley National Laboratory

M. Gilchriese	date

Silicon Subsystem L2 Manager

Concurrence:

Thomas B.W. Kirk	date

Associate Director, BNL