U.S. ATLAS MOU NO. ??/00

Amendment

to

Memorandum of Understanding

between

University of Oklahoma

and

The U.S. ATLAS Project Office

for Fiscal Year FY 2000

November 23, 1999

1.	Introduction

This Amendment is made to provide details of the work agreed to between the parties making the Memorandum of Understanding covering the specific  period of performance from October 1, 1999 through September 30, 2000.  It is subject to all the points of agreement and conditions in the current version of the parent Memorandum and the current version of the U.S. ATLAS Project Management Plan (U.S. ATLAS 97-7).

2.	Personnel

2.1.	List of Scientific Personnel

Participating scientists with anticipated fraction of their research time committed to ATLAS during this period of performance are:

| Name | ATLAS Fraction | Other Research Commitments/Comments |
| --- | --- | --- |
| P. Gutierrez | 0.15 | D0 |
| T. McMahon | 0.15 | D0 |
| H. Severini | 0.25 | CLEO |
| J. Snow | 0.15 | D0 |
| P. Skubic | 0.45 | CLEO |
| M. Strauss | 0.15 | D0 |

2.2.	Institutional Board Representative

Pat Skubic is the present representative of the University of Oklahoma on the U.S. ATLAS Institutional Board.

2.3.	List of Technical Personnel

Participating technical personnel with the anticipated fraction of their time committed to ATLAS during this period of performance and their source(s) of support are:

Engineers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |
| ATLAS Project |
| Rusty Boyd | 1.0 | UNIVERSITY OF OKLAHOMA |

Designers

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |
| ATLAS Project |
| None |
| UNIVERSITY OF OKLAHOMA |

Technicians

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| A. Wade | 0.25 | UNIVERSITY OF OKLAHOMA |
| None |
| ATLAS Project |

Software Professionals

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| None |

Others

| Name | ATLAS Fraction | Source of Support |
| --- | --- | --- |
| S. Krishnama (EE MS stu.) | 0.50 | UNIVERSITY OF OKLAHOMA |

2.4.	Other Key Personnel

The Environment, Safety and Health officer for the University of Oklahoma currently responsible for compliance with applicable ES&H policies associated with ATLAS participation by this institution is P. Skierkowski of the University of Oklahoma.  The Quality Assurance officer for the University of Oklahoma currently responsible for QA compliance of tasks performed by this institution is P. Skubic of the University of Oklahoma.

3. 	Design, Prototype, Production and Installation Responsibilities

3.1.	Design, Prototype and Production Responsibilities for this Period of Performance

3.1.1	Deliverables:  From U.S. ATLAS Project Funds:

The UNIVERSITY OF OKLAHOMA will receive a total of $51.0K for work on the Silicon Subsystem(WBS 1.1.1) FY99 ATLAS Project funds for the work and deliverables summarized in the tables below.

| WBS (L5) | Pixel System | 51.0 |
| --- | --- | --- |
| 1.1.1.2 | Pixel Sensors | 10.0 |
| 1.1.1.2.3 | Production | 10.0 |
|  | U.S. contribution to purchase of preproduction and production sensors. |
|  | 1.1.1.4 | Pixel Hybrids | 41.0 |
| 1.1.1.4.1 | Design of pixel flex hybrids | 17.0 |
| 1.1.1.4.2 | Procurement of prototype flex hybrids for prototype modules, assembly and test of prototype hybrids, and purchase of equipment, materials and supplies for assembly and test | 24.0 |

Infrastructure funds will be provided by DOE to support Electrical Engineer Rusty Boyd as indicated in the table below.

| WBS (L5) | Pixel System | 60 |
| --- | --- | --- |
| 1.1.1.4 | Pixel Hybrids | 60 |
| 1.1.1.4.1 | Design of pixel hybrids for prototype modules and conceptual of production module hybrids | 60 |

3.2.	Coordination and  Reporting

The U.S. ATLAS L2 Manager for the silicon subsystem is M. Gilchriese. The institution contact person for silicon subsystem activities at University of Oklahoma is P. Skubic. The task managers for silicon subsystem activities carried out at University of Oklahoma are as follows:

WBS 1.1.1.2 Pixel Sensors(P. Skubic)

WBS 1.1.1.4 Pixel Hybrids(P. Skubic)

WBS 1.1.1.5 Pixel Modules(P. Skubic)

3.3.	Collaboration with Other Groups and Institutions(no amendments are included in this section)

Design, construction and installation related to the silicon subsystem will be carried out in close communication and collaboration with other groups working on this and related subsystems.

4.	Contribution of Effort, Services and Equipment

4.1.	Effort

Subject to adequate funding by DOE or NSF, University of Oklahoma will provide support for the scientific and technical personnel as indicated in section 2 during this period of performance.

5. 	Costs and Funding

An amount of $51.0K from ATLAS Project funds will be provided for the period October 1, 1999 - September 30, 2000 to cover work described under 3.1.1.

An amount of $20K(matching funds) will be provided by the University of Oklahoma for the period October 1, 1999 - September 30, 2000 to cover work described under 3.1.1.

6.	Administration (no amendments are included in this section)

7.	General Considerations (no amendments are included in this section)

8.	Schedules and Milestones

University of Oklahoma will make every effort to carry out their institutional responsibilities consistent with the overall ATLAS schedule.  In this amendment are listed the program milestones for this period of performance.

8.1.	Design, Fabrication and Installation Milestones

The program milestones for this period of performance relevant to University of Oklahoma are listed here:

| WBS | Item | Baseline | Current | Milestone |
| --- | --- | --- | --- | --- |
| 1.1.1 | Pixel System | 29-May-00 | 1-Sep-00 | Baseline review |
| 1.1.1.2 | Pixel Sensors |
|  | 1.1.1.2.1 | Design/Engineering |
|  | 20-Jan-00 | 20-Jan-00 | Final Design Review |
| 19-Jul-00 | 19-Jul-00 | Complete preproduction design |
| 1.1.1.2.2 | Development/protos |
|  | 20-Jan-00 | 20-Jan-00 | Complete testing 2nd prototypes |
| 1.1.1.2.3 | Production |
|  | 20-Jan-00 | 20-Jan-00 | Select production detector type |
| 20-Jan-00 | 20-Jan-00 | Select detector vendors |
| 24-Feb-00 | 24-Feb-00 | Start preproduction procurement |
| 22-Jun-00 | 22-Jun-00 | Complete preproduction procurement |
| 1.1.1.4 | Pixel Hybrids |
|  | 1.1.1.4.1 | Design/Engineering |
|  | 10-Jul-00 | 10-Jul-00 | 3rd prototype design review |
| 4-Aug-00 | 4-Aug-00 | Compl. 3rd prototype design |
| 1.1.1.4.2 | Development/protos |
|  | 8-Feb-00 | 8-Feb-00 | Compl. Tests of 2nd protots |
| 8-Feb-00 | 8-Feb-00 | Select hybrid production vendor(s) |

9.	Makers and Concurrence

The following persons concur in the terms of this Amendment.  These terms will be updated as appropriate in later Amendments to this Memorandum.

Makers of this Memorandum:

William J. Willis	date	Debbie Jennings	date

U.S. ATLAS Project Manager		University of Oklahoma

M. Gilchriese	date	Patrick Skubic

Silicon Subsystem L2 Manager		Institutional Subsystem Representative

University of Oklahoma

Concurrence:

Thomas B.W. Kirk	date

Associate Director, BNL