## Response to US ATLAS Pixel Review

***DRAFT***

November 28, 2000

### WBS 1.1.1.1 Mechanics

Since the review, there have been a number of developments in the pixel mechanics.

A revised radial envelope for the pixel system(including the support tube) was fixed by mid-November. This radial envelope is smaller than that presented at the review. However, the pixel support tube no longer must act as a thermal barrier for the forward SCT(a separate structure will now do this), somewhat simplifying the design of the support tube. But the design of the space frame and rail system becomes more challenging(less space) than that presented at the review.

The US ATLAS management requested that we include the design and fabrication of the pixel support tube in the US baseline scope or find an alternative outside the US. The ATLAS management has formally requested us to accept this responsibility, no other alternative being available to maintain the schedule(see minutes of the Inner Detector Steering Group Meeting of November 16).

We have therefore accepted this responsibility and done our best to update our preliminary cost estimate.

The estimated cost of this element was modified based on design work done in the first two weeks of November, after a final definition of envelopes and the creation of preliminary requirements document.

The "thermal barrier" has been renamed "support tube" to more clearly identify its function.

WBS 1.1.1.1.1.2.4 Support Tube(Design). Design costs have been moved into baseline scope.

WBS 1.1.1.1.2.4 Support Tube(Prototype). Costs for prototype have been moved into baseline scope.

WBS 1.1.1.1.3.5 and 1.1.1.1.3.6(added element).  Fabrication costs have been updated.

Some elements of the schedule we presented for the mechanics were felt by the pixel Project Leader to be too aggressive. In particular, the Production Readiness Review of the local supports(barrel staves and disk sectors) was felt to be too early for the staves, a non-US responsibility. Although the disk sectors could easily be ready for PRR on the schedule shown at the review, the barrel staves and other barrel elements being designed in Europe may not be ready for review on the schedule shown. We have therefore modified the US schedule by adding up to about four months in some milestones(reviews). Practically, the US and European design efforts should be reviewed at the same time.

It may be possible to streamline the support structure design to reduce cost.

We have scrubbed the WBS elements 1.1.1.1.1.2.2(Disk Support Rings and Mounts) and 1.1.1.1.1.2.3(Support Frame). The cost of 1.1.1.1.1.2.2 has not been reduced. The reduction in radial envelope(beyond that presented at the review) may require a partial redesign of the support ring to meet space requirements, and the only practical means to assess the viability of such a design is by analysis by Hytec. This may require more analysis than originally planned.

The cost of 1.1.1.1.1.2.3 ascribed to Hytec has been reduced from about 369K to 325K. The test program of the support frame prototype attached to a prototype support cone and endplate has been shifted to LBL. These tests are assumed to be carried out by LBL mechanical technicians(supported by base program. We assume the use of tooling already made by Hytec and the TV holography system now being commissioned at LBL.

In reviewing the estimate for this item, we identified tasks that had not been included. In particular, the modifications(precision holes) that must be put into the support frame. We have determined that this work should be done at LBL and have made an estimate of the tooling required based on preliminary design sketches. We have included these costs, assuming one prototype round for the existing support frame and one for production.

We understand the reviewers concerns that these design costs may appear high after some years of development. But we note that

- some months have been added to the schedule at the request of the pixel Project Leader.

- a substantial design revision has occurred(going to an insertable-layout) with very tight clearances

- the design of disk ring mounting has not yet been tested

- the design of the frame has not been completed and significant uncertainties remain in some areas(services supports, interface to barrel shells being designed in Europe, overall mounting scheme....)

- all design effort on the pixel mounting scheme within the SCT remains to be done, and this is critical for the stability of the system

- the frame will be a "build to print" bid overseen by Hytec throughout the bid and construction. All fabrication drawings must be completely redone as a result of the recent layout change and the final dimensions of the frame are still uncertain. All tooling drawings created for the prototype must be redone.

- the disk ring fabrication will be done in a similar manner(although the fabrication may be sole-sourced)

In short, it is the strong opinion of the subsystem leader that considerable engineering effort must be devoted to these critical items, and that LBL engineering cannot be substituted, given the very significant other mechanical commitments in the project. We will, of course, make every effort to minimize the overall expenditure for design, consistent with meeting requirements and schedule.

Review installation issues again early next year.

Installation issues will be part of the conceptual design review of the support frame and related elements. In addition, the overall ATLAS installation scenario is being revised and a new baseline installation plan and schedule should appear by Spring 2001.

WBS items 1.1.1.1.1.2.7 and 1.1.1.3.8 need clarification.

We have reorganized the WBS as follows

WBS 1.1.1.1.1.2.7 has been renamed to be Final Assembly and no longer includes design effort for installation at CERN - only assembly at LBL or surface assembly at CERN.

A new WBS element 1.1.1.1.1.2.10 Installation now includes design effort related to installation(insertion of the pixel system) at CERN.  This design effort is now in Management Contingency with a release date of  9/2002.

The design effort in WBS 1.1.1.1.1.2.6(Disk Assembly) and 1.1.1.1.1.2.7(Final Assembly) now maps into the sum of the Production elements 1.1.1.1.3.7 and 1.1.1.1.3.8.

The Production element 1.1.1.1.3.10(Installation) is now all Management Contingency with a release date of 9/2002.

The design effort in Integration(WBS 1.1.1.1.9) has been increased at the request of the ID subsystem leader but the increased effort is all in Management Contingency with a release date of 9/2002.

There may be opportunities to reduce cost by examining tolerances

We agree but this will naturally following during the design and early fabrication process. We note that a requirements document exists so far only for the local supports(disk sectors and barrel staves) but will be created for reviews of the support structures. This will provide an opportunity to systematically review all tolerances and reduce fabrication costs if appropriate.

### WBS 1.1.1.2 Sensors

No recommendations were made by the reviewers.

### WBS 1.1.1.3 Electronics

This plan (development of 0.25( CMOS FE chip) is supported by the committee to reduce risk. However, it results in a large design effort for the transfer of the design, which needs to be supported in regards to schedule, cost and manpower. In particular, the presented schedule has serious resource conflicts in FY01 when major design and test tasks will be pursued on large chips in two technologies in parallel.

We agree with this concern, and we intend to give the 0.25 development higher priority when there is a resource conflict with work required for the original DMILL effort. We also intend to make the critical go/no-go decision on the use of DMILL as soon as it seems practical to do so, in order to focus all effort on one solution.

SEU performance needs to be predicted using cross section estimates, and then measured for each design.

We agree that SEU effects are a significant concern for microelectronics located very close to the IP. We are pursuing a significant design, prototype, and measurement program to address this concern. In our first 0.25 test chip, we will already include several different FF designs, with different levels of SEU tolerance. One will be a standard cell design, one will involve three-fold majority logic to resolve bit flips, and one will use a special SEU-tolerant FF design developed by CERN and RD-49. We expect to compare the measured upset rates for structures in our test chip with the estimated SEU cross-sections and thresholds predicted by RD-49. This work will initially concentrate on the 55MeV protons available at LBL, and then be extended to the CERN PS (24GeV protons) and ultimately to PSI where the 300MeV pions are an excellent model for an LHC underlying event.

In our 0.25design, we will use a very robust technique such as redundant storage (perhaps three-fold majority logic) for our critical configuration information. The exact choice on what approach to use will depend on our measurements of relative sensitivities, but we believe that a redundant scheme is the only way to achieve the desired reliability (integrity) of the stored information. For less critical information, whose disruption would affect only a single channel in a 50K channel module, we presently plan to use the SEU-tolerant FF design, which offers reduced sensitivity but no redundancy.

In addition, we are specifically examining the effects of upset events (small amount of charge deposited in a specific FET) on the performance of our critical digital logic blocks using simulations, and depositing spurious hits directly in the Verilog simulations. We are attempting to ensure that all state machines and logic blocks will suffer only minor transient effects after an upset, rather than longer term disruption of the chip operation.

Radiation degradation results for the TSMC process are similar, but must be verified by ATLAS.

We intend to perform initial irradiations of TSMC test chips in early 2001, in order to verify the impact of irradiation on our designs. However, at this time we do not intend to carry out a complete qualification of the radiation hardness of the TSMC process (as has been carried out by RD-49 and others over the last few years for the IBM process), as this is a very significant program. Rather, we see TSMC primarily as a rapid prototyping process with properties very similar to those of our primary vendor (IBM). Should problems arise with our primary vendor, we would already have a functional design in TSMC, whose performance under irradiation was roughly characterized, and we would then undertake to fully qualify the TSMC version of the design for ATLAS pixels. This appears to be the best compromise with our existing resources.

A more detailed plan on how many submissions of test chips is needed....The committee feels that the schedule, which contains no float, is overly optimistic.

We have worked out a more detailed plan for all activities required to reach production quality 0.25 pixel electronics. We have prepared a revised summary schedule and milestone list based on this detailed work plan. Our planning now includes two TSMC test chips(via MOSIS) prior to the submission of the first IBM engineering run in July 2001.

The first test chip, referred to as a digital test chip even though it also contains some analog blocks, will contain many individual circuit blocks that will be used in the pixel chips. It would be submitted in the Jan 8 2001 MOSIS run, to provide early feedback on our evolving design. We intend to include the current reference and current-mode DACs used for bias control, the revised LVDS I/O blocks, several shift registers based on different FF designs for SEU studies, the present SRAM storage cell used in the pixel, and several synthesized digital blocks from the bottom of the pixel chip (timestamp generator for example). The intention of this first test chip is to check our understanding of the design rules and basic SPICE parameters, and then to evaluate in detail the analog performance of some actual design blocks. Finally, it will be irradiated and serve to check our understanding of the process and some basic design blocks under irradiation.

The second test chip is similar to ones we have built for previous submissions to DMILL and HP. It would be an analog test chip, including a small array of the preamp/discriminator design to be used in the final pixel array, as well as the complete analog support for these circuit blocks (current reference, current DACs, bias generation, calibration circuitry). Our schedule would have first versions of all of these blocks available in time to submit a test chip to the Mar 5 2001 TSMC MOSIS run. With the expected 10-week delivery time from MOSIS, there would still be adequate time to characterize the performance of this chip before submitting the engineering run.

Finally, we have delayed the submission date for the FE-I1 engineering run in order to provide adequate verification time for the final design. We have also shifted the planned second engineering run date to allow for final test beam characterization of complete FE-I1 modules in the 2002 testbeam. The original schedule had very little float before the 2001 testbeam window would be missed, and would very likely have forced us to compromise on our verification of the FE-I1 submission in order to get devices in time for 2001 testbeam. We prefer a schedule where the testbeam verification comes at the end of the FE-I1 evaluation period, in order to be able to test fully irradiated modules and to benefit from the accumulated understanding of the chips which we would have by this time.

The consensus of the committee is that the contingency (36%) of the electronics cost estimate is insufficient.

We believe the contingency for the fabrication costs of the front-end electronics and testing of same is adequate. However, we agree that the contingency associated with the design labor is not large enough, primarily resulting from uncertainties in base program support. Therefore we have raised the contingency on the design effort from 25% to 54%.

The group has to increase the confidence level by tests whether the 0.25( (process) will meet the requirements in the high-radiation B-(Layer) location.

We would like to first emphasize that in terms of total dose, there is not a large difference between the B-layer and the outer layers. The outer layers should withstand a total dose of about 50Mrad (including several safety factors), over their design lifetime of ten years. The B-layer was never anticipated to survive ten years, but was expected to be replaced regularly as technology improved, and to have the same total dose lifetime as the outer layers. In addition, the performance of the B-layer, in terms of spatial precision and efficiency, has a large impact on ATLAS physics capabilities, and hence it is expected that there will be very strong interest in replacing this layer before its lifetime has been reached. A second issue is whether our initial electronics design can cope fully with the high occupancies and rates at the small radius of the B-layer. As we noted at the review, the fallback position is to use exactly the same electronics for the B-layer as for the outer layers in case (a) the radiation resistance is found inadequate or (b) insufficient design time is available to modify the outer layer design to meet the more demanding requirements for the B-layer. The initial (lower luminosity) operation of the B-layer should be adequate with electronics designed for the outer layers. The ability to replace the B-Layer during a short access scenario is built into our design. Thus an upgrade would be the most natural path in case there are difficulties with the B-layer-specific design.

A thorough test of system functionality in beam tests should be planned.

We have performed typically three beam tests at the CERN SPS per year on pixel prototypes since 1997, and plan to continue doing so into the future. In particular, we will be testing complete irradiated modules in the 1.5T magnetic field of the SPS H8 beam at the latest by June 2002. This work is carried out using the same VME-based readout electronics that we use in our labs, and allows us to carefully cross-correlate testbeam and lab results. The SPS provides special 25ns bunched-beam running periods as well. We have already used the first such run to verify that the performance we have measured in non-bunched beam tests is really identical to that measured with the real beam time structure. Finally, the next major step in the testbeam, originally scheduled to occur in 2001, but now delayed by the problems with DMILL chips, involves readout of multiple modules using the real off-detector electronics (what in ATLAS are called RODs), and the opto-link prototypes. This complete system test would occur in 2002 in our current planning.

No specification on the power supply rejection ratio of the FE- and opto-chips has been presented

We find this difficult to specify. We have tried to make our designs as insensitive to power supply noise as possible, and we are planning to evaluate a differential front-end design for our 0.25 prototypes to see how much this could help. We have measured the power supply rejection versus frequency for our front-end chips by modulating the power supply voltages with a small AC component, and characterizing the noise and threshold (extracted from error-function fits to individual electronics channels) as a function of amplitude and frequency of the injected noise. We have then optimized our decoupling network on the module Flex Hybrid to provide optimal power supply  noise rejection in the frequency range of maximum noise sensitivity. We are working on SPICE level simulations of the power distribution (long power cables, and components at intermediate patch panels), including the Flex Hybrid, to try to further optimize their performance. We have recently constructed electrical prototypes of our power cables, and plan to test single modules with these prototypes and to measure the noise sensitivity of the entire system of pixel module and power cable (however, this is still using our old rad-soft electronics, so it is only the beginning).

More work in regards to transient protection and fusing of low voltages is required to establish a power distribution system.

We agree completely with this recommendation and note that the fabrication of multiple prototype, full-length, low-voltage cables is underway with the intention of testing modules with prototype power supplies in the next few months. This will provide a natural test bed for transient protection studies. For the original DMILL electronics, we had selected a ceramic surface mount varistor part for transient protection. This appeared to work well in the lab, and sample parts were irradiated in the SPS in May 2000 and were shown to work well after irradiation. However, this technology does not have a steep enough I/V curve to protect devices running at 2.0V (our planned 0.25 operating voltage) as opposed to the 3.5V-4.0V operating voltage planned for our DMILL chips. We have located a new type of transient protection, using an optimized punch-through diode, which looks ideal for protecting 0.25 chips. The particular design used for this diode looks promising in terms of radiation hardness, and so we have ordered a large number of these devices for evaluation and irradiation. Once they pass basic lab characterization tests, we plan to use the prototype power cables and prototype power supplies to study the types of transient waveforms that can be induced in our power distribution system, and how well they are suppressed by these devices. We expect that this series of measurements will have largely validated our power distribution design within the next 6 months.

Radiation qualification of the custom ICs is a major task and the manpower and milestones must be carefully planned.

We completely agree on the scale of this effort. The present activity in this area is largely carried by our European collaborators. During this year, the following irradiations have been performed: (1) total dose and SEU studies of opto-link components at PSI, in collaboration with ATLAS SCT; (2) irradiation of single DMILL transistors, and complete Analog Test chips in April at the PS, (3) irradiation of opto-link electronics in May at the PS, (4) irradiation of MCC chips in Oct at the PS, including real-time evaluation of functionality and SEU rates. These tests were all performed on devices contained on our FE-D1 wafers. The FE-D chips themselves were not irradiated in these periods because there were too many yield problems with the existing devices to warrant such effort. We intend to perform similar irradiations on most of the die from the FE-D2 run. We also have inserted appropriate milestones into our overall schedule for this work for the FE-I1 wafers. We are establishing an irradiation effort based at LBL as well, using 55MeV protons, in order to allow irradiation studies to continue during the 5-6 months per year that the CERN PS is not operating for irradiation work. The detailed studies of the MCC under irradiation have already been performed with their complete lab test system, with additional boards added to support irradiation studies in situ. Similarly, for the FE chips, we have already designed a rad-hard support card to interface single chips or modules to our existing test system, and allow full in situ characterization to be performed during irradiation, in the same way that we do this work in our labs. We intend to perform these irradiations using 55MeV protons (LBL), 24 GeV protons (CERN SPS), and 60Co gammas. In addition, we will try to perform realistic SEU studies at PSI using their 300MeV pion beams.

In general, the schedule needs to include more detailed task descriptions to be able to develop a complete schedule and work plan

We have developed a preliminary detailed schedule for all of the electronics activity over the next 18 months, including the FE-I1 submission, its characterization, and the submission of the revised FE-I2. We have inserted additional milestones into the overall pixel project schedule for the test chips associated with the FE-I1 design effort, and for the evaluation of the FE-I1 wafers. The detailed schedule for the FE-I1 design includes schedules for the individual circuit blocks, both at the schematic and layout level, as well as top-level simulations at the schematic and post-layout levels. The revised review and submission dates in the summary schedule reflect this more detailed planning. An ATLAS Design Review has also been included prior to submission of FE-I1. The submission date for FE-I has been delayed by approximately 6 weeks to provide additional verification time in the design flow.

Management needs to be more project oriented.......

As we noted in the review, we have included funding for systems/project engineering. Peter Denes, who has considerable experience in electronics management and who is now a senior member of the LBNL Engineering Division (as of November 1), has just started working with the ATLAS team in the area of IC and overall system design. In addition, the pixel Project Leader is exploring the possibilities of enhancing the senior engineering presence in Europe.

The approach to IC design verification should become more rigorous.....

Our overall approach to design verification includes the following:

- specifications for each chip

- the design is judged to be successful when simulations indicate that the specifications are met

- a complete top-level(full-chip) simulation will be performed at the "schematic" level and a design review held

- a complete top-level post-layout simulation will be performed and similarly reviewed

Each time we submit a new version of the pixel chips (we have now made five versions in three different processes), we improve our verification methodology. The present plan for FE-I1 includes the following steps: (1) simulate and verify all individual blocks using SPICE and Verilog with the vendor corner models; (2) simulate and verify at higher levels using Verilog, including annotation for interconnection parasitics; (3) simulation of large SPICE netlists, including all layout parasitics, for large critical blocks like the column-pair; (4) many Verilog simulations at the top level, using random data patterns to look for potential design problems. In addition, we have worked with a newer verification tool (TimeMill) which allows simulation of very large circuit blocks with SPICE-like accuracy. If time and manpower permit, we will try to use this tool during the final verification steps to insure there are no timing errors at the highest level of the chip integration.

In our first DMILL submission (FE-D1), the global verification using Verilog did not include proper back-annotation of parasitics. In addition, the post-layout SPICE simulations of critical blocks were not completed prior to chip submission. The result was a chip which worked correctly, but had several internal buffering problems occuring at the top level in the chip integration. These errors were not fatal, but were not caught prior to submission because of the incomplete verification methodology used. We believe that the revised methodology proposed here does provide an adequate safety net to catch any significant errors in the design.

It would be prudent for the collaboration to develop fallback plans in case additional IC iterations are needed, or if planned levels of base manpower do not materialize.

The only realistic fallback plan is the one that we presented at the review: installation of the pixel system in 2006. We have increased the contingency on the design effort in the US to respond to this recommendation. In addition, every effort is being made to utilize design resources outside the US, and some modest additional manpower in Europe has been identified since the review and is being integrated into the effort.

The overall coordination of the electronics effort needs to be strengthened

We believe this can be accomplished to some extent by adding systems/project engineering at LBNL, as we proposed at the review and have described above. However, we note that the electronics coordination within the global collaboration has been a rotating position, and that the US does not, and cannot, have final authority in all areas of the pixel electronics system.

Double counting error of 75K(too much) fixed in 1.1.1.3.2.4.1

A WBS element for the costs of TSMC test chips done via MOSIS has been added(1.1.1.3.2.3.1).

### WBS 1.1.1.4 Flex and Optical Hybrids

Flex Hybrids

No changes made regarding flex hybrids.

Optical Hybrids

A milestone in June 2001 has been added to decided between the use of the OSU and Taiwan optical packages.

The committee indicated some concerns about reliability, the effects of low temperature operation and irradiation.

The reliability of the opto-packages has been studied using accelerated aging tests AFTER irradiation.  The PIN diode has passed the irradiation and accelerated aging test up to to the pixel dosage.  The VCSEL has been tested to the SCT dosage and tests up to the pixel dosage are planned.  The cap of the opto-pack is fabricated uses ULTEM, which according to CERN's Compilation of Radiation Damage Test Data (CERN 98-01), is rad-hard to 10 Grad.  We irradiated the cap with Co60 up to 50 Mrad and no degradation was observed.  We plan to do accelerated aging test after irradiation of the completed packages.  We also plan to do temperature cycling between -20 and +20 C on the packages.

The committee also had concern about "single-point" failure resulting in no read out of multiple modules.

We agree, of course, with this concern and understand that the design of the optical hybrids must be as fail-safe as possible. This includes both the optical and electrical components, and power distribution to these components. We expect through the extensive prototype program(three rounds included) to be able to arrive at a very robust system. We also note that the design concept for the optical hybrids allows them to be replaced(unplugged and new ones inserted), albeit with some considerable time for access.

### WBS 1.1.1.5 Module Assembly/Test

Wire bonding is a critical step and we recommend that it either be concentrated at LBL or other sites be extensively qualified and monitored. LBL should explore the purchase of an additional wirebonder.

We concur with these concerns but believe it premature to include now in the baseline cost estimate another wire bonder at LBNL. We intend to move forward with qualifying university sites(and LBL). We note that UC Santa Cruz is planned to share wire bonding for the SCT and some capacity there may also be available for pixel construction.

We have added a WBS element during the prototype phase for production of dummy wafers. It appears the cost of doing this in the US is the lowest, and 8" capability appears to exist. This adds about 20K to the cost estimate.

Based on our experience with wire bonding to flex hybrids, we have added the cost of a plasma cleaner. In addition, have added the cost of a more sophisticated wire bond pull tester, since this will be needed routinely during production for QA. This adds about 20K to the cost estimate.

We have also internally scrubbed this estimate.

Errors have been corrected in 1.1.1.5.1.3.2.

WBS 1.1.1.5.2.4.1 One of two additional tooling iterations has been eliminated.

WBS 1.1.1.5.2.4.3  Electrical technician time has been reduced with better estimate. Most of this work will be done by physicists.

WBS 1.1.1.5.2.5.1 Errors corrected

### WBS 1.1.1.6 Beam/System Test Support

Made level of effort(hence contingency set to zero) and total effort cost reduced from 143K to 105K.