## Sheet1
Wafer Count:
|  |  |  | US Purchase |  | US Cost ($)
Yield Assmd | Total # wafers |  |  | 45% | 65% | 45% | 65% |  | Euro/wafer= | 4642
26% | 949 |  |  | 427 | 617 | 1732460.9794 | 2503345.256 |  | US$/Euro= | 0.87404 | (now fixed)
32% | 757 |  |  | 341 | 492 | 1383534.4121 | 1996184.5477 |  | US$ paid CERN= | 2146638
38% | 638 |  |  | 287 | 415 | 1164440.9862 | 1683773.5514
|  |  |  | US Budget (ETC00) |  | US Budget (ETC01)
|  |  |  | Baseline | 2146638 | Baseline | 1732389.7368
|  |  |  | Mgmt Cont | 954100 | Mgmt Cont | 769950.9941 | {Are these correct?}
|  |  |  | Total | 3100738 | Total | 2502340.7309
Lead Times:
* | Fabrication time according to Frame Contract is 20weeks from Release Order.
* | Atmel must order raw wafers in large batches based upon our release orders. Lead time for raw wafers is 4months.
* | First release order set to 520 wafers to lock in >500 piece price break.
* | In order to accommodate the anticipated first release order, ATLAS issued a contingent release order for 520wafers in Sep-2000,
contingent upon passing of PRR. ATLAS is obligated to 190,578Euro (7.9% of fab cost) if release order never placed.
* | Anticipating successful PRR in June or July, Atmel started 75 wafers in March to be completed in July.
* | Assuming successful PRR on 4-Jul-2001 and following release order for 520wafer by 16-Jul-2001, Atmel should be ready to deliver
the pre-started 75 wafers in early August. They will then also start wafers for remaining 445 wafers.
* | SCT has requested a delivery schedule of ~200wafers every 8weeks which is slightly faster than anticipated test rate.
* | In order to maintain this delivery schedule, we need a second release of at least 155 wafers to be delivered on 25-Mar-02.
* | Given lead times (above), this release will have to be on same date, 16-Jul-2001, as first release order.
* | We could again issue another contingent release order with commitment to pay for raw wafers if full release order never given
and then issue unqualified release order sometime later (~ October) after first 75 wafers are tested.
* | If we wish to test first 200wafer batch (delivered in Dec-01) before making last release order, we could issue third contingent release
order in Dec-01 with unqualified release for fabrication as late as 1-Apr-02.
* | This runs the risk that wafer testing may go dry for roughly 2-4 weeks before wafers from last order start to arrive.
Delivery Schedule
|  |  |  | US Purchase (cum) |  | US Cost ($ cum)
| 1st Relse | 2nd Relse | 3rd Relse | 45% | 65% | 45% | 65% | Limits at 65% contribution rate
2001-08-01 | 75 |  |  | 33.75 | 48.75 | 136933.3912 | 197792.6762
2001-12-03 | 200 |  |  | 123.75 | 178.75 | 502089.1012 | 725239.8128
2002-01-28 | 200 |  |  | 213.75 | 308.75 | 867244.8111 | 1252686.9494
2002-03-25 | 45 | 155 |  | 303.75 | 438.75 | 1232400.5211 | 1780134.086 | <- limit assuming 45% of total @ |  |  | 1732460.9794
2002-08-19 |  |  | 200 | 393.75 | 568.75 | 1597556.231 | 2307581.2226 | <- limit for total sent to CERN @ |  |  | 2146638
2002-10-14 |  |  | 75 | 427.5 | 617.5 | 1734489.6223 | 2505373.8988 | Extra needed to reach goal = |  |  | 358735.8988
Total/Release | 520 | 155 | 275
Total wafers | 950