US Pixel Installation Plan

Version 1.02

July 11, 2002

# Summary

This document describes the installation plan for the U.S. pixel deliverables at CERN. It does not include commissioning or operations. We describe what the U.S. will deliver and our assumptions for deliverables from non – U.S. collaborators. Technical manpower estimates are given. A schedule is provided. We only cover here the period from about mid-2004 until commissioning starting 2006. Not covered here is the plan for possible removal of the pixel system after the first run to add a 3rd hit. Contributions to the M&O budget from the U.S. are not covered here. The assumption here is that the M&O contributions cover general infrastructure items at CERN. The essential assumption is that this installation budget presented here will only cover U.S. personnel costs at CERN and related travel and other expenses. All other costs are from some other budget.

# Overview of Tasks

This note describes the installation of the U.S. pixel deliverables. In brief the U.S. deliverables are:

- Pixel support tube(PST) in three sections and tooling for bonding the mount for the barrel section into the SCT barrel

- Pixel support frame in three sections, barrel and two disk sections.

- Pixel disks, tooling for insertion of disks into support frame, testing hardware for verification of functionality before and after insertion into support frame

- Pixel service panels, handling tooling for the service panels and testing hardware to verify functionality

- Patch panel 1(PP1)

- Beam pipe and service panel support

- All pixel RODs, including software for operation of the RODs

The installation of the U.S. pixel deliverables includes the following:

I. The barrel section of the pixel support tube(PST) is installed into the SCT/TRT barrel in the SR building. This requires bonding(gluing) mounts in place. The forward sections of the PST are bolted to the barrel and the alignment checked. The forward sections are then removed and stored.

II. The barrel ID, including the barrel section of the PST, is lowered into the pit and installed into the solenoid magnet. The heater elements of the barrel PST are cabled and checked. The forward sections of the PST are bolted to the barrel section and the alignment is checked. The forward parts for the SCT/TRT can then be installed.

III. In the SR building. Integration of the disks into the support frame sections. Verification of their functionality. Integration of two disk sections with the barrel section. Integration of the beam pipe support and beam pipe. Integration of services panels and PP1. Verification of functionality using about 10% of the RODs temporarily installed in SR building. Insertion of the pixel “package” into an installation tube/support to be lowered into the pit.

IV. Installation of all RODs and verification of performance.

V. Lowering of the pixel package in its installation/support into pit. Insertion of the pixel system into the PST. Cabling, fiber and pipe connection. Verification of functionality using installed RODs.

# Overview of Manpower

The detailed task list, durations and manpower estimates are given in the sections that follow. In this section we provide an overview of the technical manpower estimates that follow from the more detailed estimates.

- The initial PST installation occurs in mid-2004. The lead engineer and tech for this are at CERN for 6 weeks.

- The pixel RODs(some of them) have been in use at the barrel and disk assembly sites. They are all shipped to CERN by October 1, 2004. About 90% are installed in their final locations. About 10% are installed in the SR building for testing the pixel system during surface integration. The pixel systems engineer(J. Richardson) becomes resident at CERN as of October 1, 2004 and is the lead engineer for installation(and later commissioning) of the RODs and of the system test capability in the SR building. The lead engineer for the ROD design(currently J. Joseph) is at CERN for the initial phase of ROD installation.

- The remaining pixel deliverables(disks, beam pipe support, service panels, PP1) arrive at CERN in January 2005. The lead mechanical engineer for pixel integration and installation is from the U.S. and becomes resident at CERN at this time. Mechanical technical manpower from the U.S. unpacks, inspects and assembles the U.S deliverables on the surface. The final PST assembly in the pit is done primarily by U.S. personnel under the direction of the lead mechanical engineer.

- Testing of the assembled pixel system is done on the surface. The pixel systems engineer(Richardson) is the lead engineer for this. Additional electrical engineering for the readout system(RODs) and for electronics participates at CERN but is not resident at CERN. The lead mechanical engineer is simultaneously coordinating the effort to install the pixel system in the pit.

- The pixel system is lowered into the pit, inserted into the PST. Cables, fibers and pipes are connected. Verification of functionality is done during the connection process. Richardson is the lead systems engineer for the electrical testing. The lead mechanical engineer is responsible for the cooling, cabling etc. Mechanical technicians from the U.S. are part of a team doing the connections, focusing on the critical region at PP1 that was done in the U.S.

- Commissioning follows the verification of installation. Richardson remains resident at CERN as the lead systems engineer for this and later for operations. All other personnel return to the U.S.

# Initial Pixel Support Tube Installation

The three sections of the PST have been shipped to CERN. Tooling for bonding the mounts of the PST to the corresponding mounts in the barrel SCT interlinks has also been shipped.  Tools and supplies for the U.S. team are a U.S responsibility. We assume that non-U.S. collaborators will provide the following:

- Space for unpacking and inspecting the PST sections upon delivery to CERN

- Some technician manpower for handling the PST sections and tooling.

- Temporary supports for holding the PST sections. We are assuming that the barrel section is inserted by hand into the SCT. This remains to be verified. Temporary supports will be needed for the forward PST sections when they are bolted to the barrel section for checking.

- All survey and alignment equipment and expert personnel

The estimated tasks and durations(in weeks) are the following:

| Task | Duration(weeks) |
| --- | --- |
| Get organized. Unpack PST sections | 1 |
| Inspect, continuity test of heaters, repair | 1 |
| Install barrel, bond mounts, survey | 2 |
| Fit forwards, survey | 1 |
| Remove forwards, pack and store | 1 |

The lead mechanical engineer responsible for the PST design must be present throughout this period. A trial assembly of the PST sections will have been done in the U.S. The lead tech that did this assembly must also be present throughout this period. We assume that we can get additional technical manpower at no cost to the U.S. for handling the PST sections during the operations above. The manpower estimates are the following:

| Type of manpower | FTE(hours) FY04 |
| --- | --- |
| Mechanical engineer | 240 |
| Lead mechanical technician | 240 |

Travel costs are one round trip to CERN for these two people(6K) + expenses at CERN(6K).

# II. Final PST Installation

The barrel ID with the barrel section of the PST is lowered into the pit and installed into the solenoid. Continuity of the barrel PST heaters is checked. The forward PST sections are lowered, brought into the solenoid and bolted to the barrel section. Heater continuity is checked. Alignment of the forward sections is checked.

The tasks and durations for U.S. manpower are given below.

| Task | Duration(weeks) |
| --- | --- |
| Barrel heater continuity, cabling, check | 0.5 |
| Install forward PST sections, survey | 1 |
| Forward heater continuity, cabling, check | 0.5 |

The manpower estimates are:

| Type of manpower | FTE(hours) FY05 |
| --- | --- |
| Mechanical engineer | 80 |
| Junior mechanical technician | 80 |

Since this occurs during the same period as the pixel surface installation, the travel is included there.

# III Surface installation(not including RODs)

The pixel disks, disk frame sections, tooling for insertion and testing of these, beam pipe and service panel support, service panels and PP1 are at CERN. The barrel sections being fabricated in the EU have also arrived at CERN. All work takes place in the SR building. We assume that testing electronics(RODs, crates, racks, PCs) have arrived previously and are ready to be used for testing(see IV).  We assume that our non – U.S. collaborators will provide the following:

- Space and facilities for unpacking and assembly of the U.S. deliverables(the SR building + tables, benches, etc)

- Cooling system for surface testing

- Cables and fibers for surface testing

- All alignment and survey instrumentation and expert personnel

- The installation and test tool(ITT) for the surface installation and testing of the parts of the pixel detector and the final assembled detector

A high-level schedule for this period and for ROD installation is given later.

The U.S. technical team during this period will consist of: 1 FTE lead pixel systems engineer for testing(Richardson), 1 FTE lead mechanical engineer, 2 FTE mechanical technicians(this will be 3-4 people sharing the load, traveling to CERN as particular expertise is needed), 0.5 FTE electrical engineer for  pixel electronics debugging.

The manpower estimates are detailed below.

| Type of manpower | FTE(hours) FY05 |
| --- | --- |
| Systems engineer | 1760 |
| Electrical engineer | 880 |
| Mechanical engineer | 1320 |
| Senior mechanical technician | 880 |
| Junior mechanical technician | 880 |

Travel and supplies costs are estimated as below. Travel includes relocation costs to CERN or relocation to US, which we take as $30K and $10K, respectively.  Costs for non-CERN-resident personnel are taken as $3K per trip and $100 per day at CERN.  Supplies include stores items at CERN, other minor consumables and computers for personnel use. We have rounded costs to the nearest 5K.

| Type of manpower | Travel(FY05) | Supplies(FY05) |
| --- | --- | --- |
| Systems engineer | 40K | 5K |
| Electrical engineer | 30K | 5K |
| Mechanical engineer | 40K | 10K |
| Senior mechanical technician | 30K | 10K |
| Junior mechanical technician | 30K | 5K |

# IV ROD Installation

We assume the RODs are at CERN by October 1, 2004. We assume 90% are installed in their final location and 10% in the SR building for testing the pixel system as it is integrated there. Systems integration engineering is covered under III above. The lead design engineer will participate in the installation at CERN and be available for handling problems as they arrive later during pixel installation.

The manpower estimate is given below. Systems engineering for this is covered under III already.

| Type of manpower | FTE(hours) FY05 | FTE(hours) FY06 |
| --- | --- | --- |
| Electrical engineer | 300 | 300 |

Travel and supplies are estimated below.

| Type of manpower | Travel(FY05) | Supplies(FY05) | Travel(FY06) | Supplies(FY06) |
| --- | --- | --- | --- | --- |
| Electrical engineer | 10K | 5K | 10K | 0K |

# V In-pit installation

Installation of the pixel detector occurs in FY06. We assume that the mechanical installation and verification of installation is completed by the middle of FY06. As we have already noted, we assume that the lead mechanical engineer coordinating the installation is from the U.S. Since the U.S. deliverables include the PST rails, pixel mounts and PP1, we have included technical manpower from the U.S. for in-pit installation, the delicate cabling and checkout of PP1 and for verifying PST performance with the pixel detector in place. Richardson will continue to be the lead systems engineer for installation verification and later commissioning. Only the installation part is given in the table below.

| Type of manpower | FTE(hours) FY06 |
| --- | --- |
| Systems engineer | 880 |
| Electrical engineer | 440 |
| Mechanical engineer | 880 |
| Senior mechanical technician | 220 |
| Junior mechanical technician | 440 |

Travel and supplies costs are estimated below.

| Type of manpower | Travel(FY06) | Supplies(FY06) |
| --- | --- | --- |
| Systems engineer | 10K | 5K |
| Electrical engineer | 20K | 0K |
| Mechanical engineer | 20K | 5K |
| Senior mechanical technician | 10K | 5K |
| Junior mechanical technician | 20K | 5K |

# Schedule

A preliminary schedule for the U.S. pixel installation has been created. A summary is shown below. Note that calendar(not fiscal) years are used in the schedule. The schedule is based on version 5.0a of the ATLAS installation schedule.

# Summary Costs

Summary costs are given below in FY02 $K.

| WBS 1.1.1 Pixel System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | FY04 | FY05 | FY06 |
|  | Hours | FY02($K) | Travel | Supplies | Hours | FY02($K) | Travel | Supplies | Hours | FY02($K) | Travel | Supplies |
| Systems engineer |  |  |  |  | 1760 | 135 | 40 | 5 | 880 | 68 | 10 | 5 |
| Mechanical engineer | 240 | 18 | 6 |  | 1400 | 107 | 40 | 10 | 880 | 68 | 20 | 5 |
| Electrical engineer |  |  |  |  | 880 | 75 | 30 | 5 | 440 | 38 | 20 | 0 |
| Senior tech | 240 | 20 | 6 |  | 880 | 74 | 30 | 10 | 220 | 18 | 10 | 5 |
| Junior tech |  |  |  |  | 960 | 59 | 30 | 5 | 440 | 27 | 10 | 5 |
|  | Subtotal | 38 | 12 | 0 | Subtotal | 450 | 170 | 35 | Subtotal | 218 | 70 | 20 |
| TOTAL WBS 1.1.1 | 50 |  |  |  | 655 |  |  |  | 308 |  |  |  |
| WBS 1.1.3 RODs(Pixels only) |  |  |  |  |  |  |  |  |  |  |
|  | FY04 | FY05 | FY06 |
|  | Hours | FY02($K) | Travel | Supplies | Hours | FY02($K) | Travel | Supplies | Hours | FY02($K) | Travel | Supplies |
| Electrical engineer |  |  |  |  | 300 | 26 | 10 | 5 | 300 | 26 | 10 | 0 |
|  | Subtotal | 0 | 0 | 0 | Subtotal | 26 | 10 | 5 |  | 26 | 10 | 0 |
| TOTAL WBS 1.1.3 | 0 |  |  |  | 41 |  |  |  | 36 |  |  |  |
| Pixels only |  |  |  |  |  |  |  |  |  |  |  |  |

Summary costs in the U.S. ATLAS format are given below through FY05.

|  |  |  | U.S. ATLAS Silicon |
| --- | --- | --- | --- |
|  |  |  | Baseline + Management Contingency Installation (FY02k$s) |
|  |  |  | FY02 | FY03 | FY04 | FY05 | Total |
| WBS | Description | Category | Labor | Mat'l | Total | Labor | Mat'l | Total | Labor | Mat'l | Total | Labor | Mat'l | Total | Labor | Mat'l | Total |
| 1.1 | Silicon | Total | 50.0 | 10.8 | 60.8 | 52.4 | 10.8 | 63.2 | 84.5 | 16.7 | 101.2 | 502.0 | 236.1 | 738.1 | 688.9 | 274.4 | 963.3 |
|  |  | Baseline | 50.0 | 10.8 | 60.8 | 52.4 | 10.8 | 63.2 | 46.5 | 4.7 | 51.2 | 26.0 | 16.1 | 42.1 | 174.9 | 42.4 | 217.3 |
|  |  | MC | - | - | - | - | - | - | 38.0 | 12.0 | 50.0 | 476.0 | 220.0 | 696.0 | 514.0 | 232.0 | 746.0 |
| 1.1.1 | Pixels | MC | - | - | - | - | - | - | 38.0 | 12.0 | 50.0 | 450.0 | 205.0 | 655.0 | 488.0 | 217.0 | 705.0 |
| 1.1.1.7 | Installation | MC | - | - | - | - | - | - | 38.0 | 12.0 | 50.0 | 450.0 | 205.0 | 655.0 | 488.0 | 217.0 | 705.0 |
| 1.1.3 | RODs | Total | 50.0 | 10.8 | 60.8 | 52.4 | 10.8 | 63.2 | 46.5 | 4.7 | 51.2 | 26.0 | 16.1 | 42.1 | 174.9 | 42.4 | 217.3 |
| 1.1.3.9 | SCT/Pixel RODs install | Baseline | 50.0 | 10.8 | 60.8 | 52.4 | 10.8 | 63.2 | 46.5 | 4.7 | 51.2 | - | 1.1 | 1.1 | 148.9 | 27.4 | 176.3 |
| 1.1.3.9 | Pixel RODs install | MC |  |  |  |  |  |  |  |  |  | 26 | 15 | 41.0 | 26.0 | 15.0 | 41.0 |

Summary labor hours and FTEs in the U.S. ATLAS format are given below through FY05.

| FTEs in Hours |  |  | Labor Hours |  |  | FTEs (Hours Divided by | 1762 | ) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS | Description | Category | FY02 | FY03 | FY04 | FY05 | Total |  |  | FY02 | FY03 | FY04 | FY05 | Total |
| 1.1 | Silicon | Total | 598 | 638 | 1,018 | 6,180 | 8,434 | 4.8 | - | 0.3 | 0.4 | 0.6 | 3.5 | 4.8 |
| EE |  |  | 298 | 298 | 298 | 1,180 | 2,074 |  | - | 0.2 | 0.2 | 0.2 | 0.7 | 1.2 |
| ME |  |  | - | - | 240 | 1,400 | 1,640 | - | - | - | - | 0.1 | 0.8 | 0.9 |
| Techs |  |  | 300 | 340 | 480 | 1,840 | 2,960 | - | - | 0.2 | 0.2 | 0.3 | 1.0 | 1.7 |
| S/W |  |  | - | - | - | 1,760 | 1,760 | - | - | - | - | - | 1.0 | 1.0 |
| CL |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Student |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Shops |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Other |  |  | - | - | - | - | - | - | - | - | - | - | 0.3 | 0.3 |
| 1.1 | Silicon | Total Baseline | 598 | 638 | 538 | - | 1,774 | 1.01 | - | 0.34 | 0.36 | 0.31 | - | 1.01 |
| EE |  |  | 298 | 298 | 298 | - | 894 | - | - | 0.17 | 0.17 | 0.17 | - | 0.51 |
| ME |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Techs |  |  | 300 | 340 | 240 | - | 880 | - | - | 0.17 | 0.19 | 0.14 | - | 0.50 |
| S/W |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| CL |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Student |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Shops |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Other |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| 1.1 | Silicon | Total MC | - | - | 480 | 6,180 | 6,660 | 4 | - | - | - | 0.3 | 3.5 | 3.8 |
| EE |  |  | - | - | - | 1,180 | 1,180 |  | - | - | - | - | 0.7 | 0.7 |
| ME |  |  | - | - | 240 | 1,400 | 1,640 | - | - | - | - | 0.1 | 0.8 | 0.9 |
| Techs |  |  | - | - | 240 | 1,840 | 2,080 | - | - | - | - | 0.1 | 1.0 | 1.2 |
| S/W |  |  | - | - | - | 1,760 | 1,760 | - | - | - | - | - | 1.0 | 1.0 |
| CL |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Student |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Shops |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Other |  |  | - | - | - | - | - | - | - | - | - | - | 0.3 | 0.3 |
| 1.1.1 | Pixels | MC | - | - | 480 | 5,880 | 6,360 | 3.61 | - | - | - | 0.3 | 3.3 | 3.6 |
| EE |  |  | - | - | - | 880 | 880 |  | - | - | - | - | 0.50 | 0.5 |
| ME |  |  | - | - | 240 | 1,400 | 1,640 | - | - | - | - | 0.14 | 0.79 | 0.9 |
| Techs |  |  | - | - | 240 | 1,840 | 2,080 | - | - | - | - | 0.14 | 1.04 | 1.2 |
| S/W |  |  | - | - | - | 1,760 | 1,760 | - | - | - | - | - | 1.00 | 1.0 |
| CL |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Student |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Shops |  |  | - | - | - | - | - | - | - | - | - | - | - | - |
| Other |  |  | - | - | - |  |  | - | - | - | - | - | 0 | 0 |
| 1.1.1.7 | Pixels Install | MC | - | - | 480 | 5,880 | 6,360 | 3.61 | - | - | - | 0.3 | 3.3 | 3.6 |
| EE |  |  |  |  | - | 880 | 880 |  |  | - | - | - | 0.50 | 0.5 |
| ME |  |  |  |  | 240 | 1,400 | 1,640 | - |  | - | - | 0.14 | 0.79 | 0.9 |
| Techs |  |  |  |  | 240 | 1,840 | 2,080 | - |  | - | - | 0.14 | 1.04 | 1.2 |
| S/W |  |  |  |  | - | 1,760 | 1,760 | - |  | - | - | - | 1.00 | 1.0 |
| CL |  |  |  |  | - | - | - | - |  | - |  | - | - | - |
| Student |  |  |  |  | - | - | - | - |  | - |  | - | - | - |
| Shops |  |  |  |  | - | - | - | - |  | - | - | - | - | - |
| Other |  |  |  |  | - |  |  | - |  |  |  | - |  |  |
| 1.1.2 | Silicon Strips |  | - | - | - | - | - | - | - | - | - | - | - | - |
| EE |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| ME |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Techs |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| S/W |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| CL |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Student |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Shops |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Other |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| 1.1.3 | RODs | Baseline | 598 | 638 | 538 | - | 1,774 | 1.01 | - | 0.34 | 0.36 | 0.31 | - | 1.01 |
| EE |  |  | 298 | 298 | 298 |  | 894 |  |  | 0.17 | 0.17 | 0.17 | - | 0.51 |
| ME |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Techs |  |  | 300 | 340 | 240 |  | 880 |  |  | 0.17 | 0.19 | 0.14 | - | 0.50 |
| S/W |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| CL |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Student |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Shops |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| Other |  |  |  |  |  |  | - |  |  | - | - | - | - | - |
| 1.1.3 | RODs | MC |  |  |  | 300 | 300 | 0.17 |  |  |  |  | 0.2 | 0.2 |
| EE |  |  |  |  |  | 300 | 300 |  |  |  |  |  | 0.17 | 0.2 |
| ME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Techs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Student |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Shops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Footnotes

The amount of U.S. M&O funding is not yet fixed but is intended to support the SR building operation.

Funding for the beam pipe support is currently in the Technical Coordination part of Management Contingency.

Funding for fabrication of all pixel RODs is currently part of Management Contingency.

We assume 40 hour weeks.