Cost Comparison

Below is a cost comparison of the DSP-based and FPGA-based options, and a comparison with the U.S. baseline cost estimate. A number of assumptions are made to make this comparison

- 48 links/board are assumed for the preprotoype cost estimate and the costs are entered into the SCT column.

- The L1 trigger rate is 100 KHz

- The S-link is assumed to operate at 40 Mwps

- A Region-of-Interest trigger is assumed

- The number of links per ROD for the B-layer is given in ( )

- TOT pixel readout is assumed

- Only component costs are shown. Raw-board cost, board loading and board debugging have not been included. These costs were included in the production baseline ROD estimate and were taken at that time to be $952(FY97) per board.

- The preprototype baseline cost was $84K(FY97) for fabrication of 16 cards + 2 "prototype" cards. This cost included the bare-board, board loading etc. Thus to make a comparison with the estimates presented at the review, I have calculated a component cost per board as follows: $84K/16= $5250 - $952 = $4298(FY97).

- The production baseline component estimate of $4059 - $952 = $3107(FY97) was inflated by 6% to FY99 and is $3293(FY99).

- The preprototype baseline component estimate of $4298(FY97) was inflated by 6% to $4556.

- No attempt was made to scale either the FPGA-based or DSP-based preprototype cost estimates to production quantities. Thus the production costs shown below are obtained from current estimates for the preprototypes.

|  | SCT Links per rod | PIXEL LINKS PER ROD | Sct COST | PIXEL COST |
| --- | --- | --- | --- | --- |
| Preprototype baseline | Not specified |  | 4556 |  |
| ROD production baseline | 32 | 32 | 3293 | 3293 |
| FPGA-based preprototype | 48 |  | 2759 |  |
| FPGA-based production | 96 | 36(12) | 4392 | 3309 |
| DSP-based preprototype | 48 |  | 2680 |  |
| DSP-based production | 96 | 36(9) | 5035 | 5035 |

Schedule Comparison

The baseline milestone for the completion of fabrication of the first preprototype ROD was 30-Mar-99. A comparison with the milestones presented at the review is given below. A five month delay is projected in the case of the FPGA-based design and a six month delay in the case of the DSP-based design.

|  | First preprototype complete |
| --- | --- |
| Baseline schedule | 30-Mar-99 |
| FPGA-based | 1-Sep-99 |
| DSP-based | 30-Sep-99 |

Manpower

A summary of the physicist, electrical engineer, technical and student manpower available through the expected debug-period of the preprototype ROD is given below.

| UW | FTE | UCI | FTE |
| --- | --- | --- | --- |
| Dao(EE) | 0.10 | Baron(Phys) | 0.7 |
| Fasching(Phys) | 1.0 | Dailing(EE) | 0.9 |
| Hayes(Phys) | 1.0 | Fahland(Phys) | 0.9 |
| Jared(EE) | 0.25 | Hawkins(Phys) | 1.0 |
| Marks(EE) | 1.0 | Lankford(Phys) | 0.25 |
| Nagel(EE) | 1.0 | Nguyen(Tech) | 0.7 |
| Students | 0.5 | Pier(EE) | 1.0 |
|  |  | Rezzonico(Tech) | 0.5 |
|  |  | Schernau(Phys) | 1.0 |
|  |  | Students | 1.0 |